## SSA Assurance Tracker
SS&A Assurance Tracker
*This tracker contains all SS&A Assurance activity to be shared within the SZC Integrated Assurance and Audit Plan (IAAP). This covers activities with start dates running till the end of December 2026; Any assurance/audit activity post March 2026 may still yet need to be added and items showing could be subject to sudden changes recognising ongoing development of the SZC project . TC Ref: 101388569.
*Please ensure you Column F (Commentary) to initial, date, and comment on any changes to current activities, along with dating, initialling and commenting on new activities added. Any removal of entries, or sharing of the tracker, needs to be cleared through Alex Boyce or Fran Gradie. Items from 2024 can be found on the 'Archive 2024' tab.
Planning Information | [18 empty] | Assurance Outputs | [19 empty] | Internal Quality Audit information
Activity ID | Task / Assurance or Audit Activity Name | Assurance Activity Description | Commentary - Please use to indicate date and new additions, and any changes. | Category (See Category Types sheet) | Interest from the Regulator? | Will this activity Necessitate site access and support? | Assuring Function | Line of Defence | Planned Start Date | Planned End Date / Report published | Actual End Date | Head of Function | Manager | Assurance Tool Used (See Assurance Tools sheet) | Function Assured | Linked Milestone | Linked Risk | Progress BRAG Status | Outcome RAG Status | Key findings/Comments | Related Licence Condition (If applicable) | Environmental Permit or Consent Linkage | Hold Point Linkage ID (If applicable) | Teamcenter document number | Insight Learning Report number | Number of Areas for Improvement (AFI's) | Number of observations | No of Opportunities for Improvement (OFI's) | No of Good Practices | No of Minor Non-conformances at end of activity | No of Minor Non-conformances LIVE | No of Major Non-conformances at end of activity | No of Major Non-conformances LIVE | Due date for Major non-conformances to be closed out | Actual date Major non-conformances closed out | No of Process Non-conformances at end of activity | No of Process Non-conformances LIVE | Are non-conformances raised 'pre-certification'? | Insight Audit Report Number | Lead Auditor | 2nd auditor / observer | SME/Technical expert | Procedure Lead Name / Lead Auditee | Level 2 ID Process Owner(s) | Process Owners Directorate (Audit only) | Source | Level 1 ID | Level 2 ID | Related Prodcures | Procedures | ISO 9001 | ISO 140001 | ISO 45001 | PAS 2080 | ISO 27001 | Activity line cancelled?
8 | LC & PC Review of Self-assessment programme assurance report | Stand back review of all annual LC/PC self assessments to verify conformance with process and capture any operational or strategic risks to NSL compliance. | 10.12.24 TB: We have updated the tool to correctly reflect 'review' of the self-assessments, this does not fall into the general 'review of self assessment' tool that has recently been added primarily for auditors though as this is around conformance with NSL compliance. 04.02.25 TB: Sent to FG yesterday for final review of outcomes/outputs and technical review. | B | Yes | No | SS&A - Nuclear Licence Compliance | Line 2 - Corporate Functions | 2024-06-03 | 2025-01-31 | 2025-01-31 | Fran Gradie | Thomas Brazendale | Review | Overall Project | LC & PC - Self-assessment programme assurance report | Nuclear Safety Risk | Blue | Green | Following the completion of work, the 2024 Nuclear Compliance Self-Assessment Report was delivered which highlights the improving maturity of SZC’s arrangements and defines areas for focus in 2025. Improvements made in 2024 include: Emergency arrangements (Licenece Condition 11), instructions to persons on the site (LC 8); and safety and security culture. Areas needing focus in 2025 include: streamlining arrangements and procedures as these are adopted by SZC (under management system, LC 17), better use and training for record management (Teamcenter, LC 6); and contractor onboarding, e.g. specifying contract requirements and responsibilities in SZC’s Contract Baseline Library (several LCs, CDM and permit requirements). | 2,4,5,6,7,8,9,11,13,14,18,19,20 | N/A | N/A | 101148763 / V2 | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
12 | Assurance of Security Measures to Enable Opening and Accreditation of 25 Copthall Avenue | To review and approve security designs and budget, assure the installation programme to enable the office to open on time as currently planned in Q1 and Q2 2025, and review the Surreptitious Threat Mitigation Process inspection to ensure that appropriate measures are installed to enable the SZC floorplate to be accredited and recorded on ONR's List N to handle, process and store Sensitive Nuclear Information at the OFFICIAL-SENSITIVE: SNI category. | 20.11.24 AS/AW: Some discussions on the POD ongoing, potentially proceeding with a shotbolt, TBC. 6.3.25: All design requirements edited and agreed and being put in place. 23.4.25: End date pushed out to end of May due to delays because of EDF Corporate and Vodafone. No additional risk, so still Green. 30.5.25 AS: End date pushed back to end of July now, some delays with EDF/Dalkia completing their activities, off plan but recoverable, BRAG changed to Amber to reflect this. 24.6.25 AS - Back on plan now, move BRAG to Green, should be no issues with end of July (regulation). | A | No | No | SS&A - Security & Conventional Safety Assurance | Line 2 - Corporate Functions | 2024-08-01 | 2025-07-31 | 2025-07-25 | Andrew Wilkinson | Andrew Wilkinson | Assessment | Overall Project | New Offices - Secured for London and Manchester | Health, Safety & Wellbeing | Blue | Green | 25 CA 4th floor did not meet the STAMP survey requirements but additional security measures have been installed to meet the standards required for a regulated area. A technical solution is being designed. | N/A | N/A | N/A | 101578899 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
72 | MEH Alliance Cat A MoC | RWA Assessment for permitting impacts | 6.3.25 AB - BH to check, as this line if complete from 2024, just needs to be added to archive sheet, and potentially new line added for 2025 activity. 13.03.25 was completed in 2024. This line to be archived to 2024 tab. 14.3.25 - AB - Action for Becky: Please can you check with Emma if this line is 2025, as I think item 74 (if you see archive tab), which looks similar was the one archived and belive this is for 2025?. 3.4.25 BH - Leave in for now will check with Emma next month. 3.4.25 bh - established that this should be in 2024 so moved to archive, in line 901. | B | No | No | SS&A - Operational Permits | Line 1 - Corporate Functions | 2024-10-20 | 2024-10-30 | 2024-10-30 | Stuart Woodings | Emma Wells | Assessment | SS&A - Operational Permits | MEHA – Contract Signed | Environment | Green | Green | 12.12.24 BH: 1 opportunity identified, Informally engage with the EA on this topic to make them aware of the change opportunities completed. No insight report raised as findings were not major | N/A | N/A | N/A | 101373169 | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | Yes
31 | Critical IT platforms (IMS, EDRMS, Tenancy) - Available (Cybersecurity - Cyber Essentials+) | Assuring deployed config meets CE requirements and fulfil DBS expectation. Q4 2024 CE and CE+ recertification | 20.11.24 - End date moved to end of March 25, to allow further time for CE+ completion. 17.3.25 JC - On-track for completion. 3.4.25 AW - Activity complete. 6.5.25 - JC is reviewing the initial draft of the report, this is to follow. | A | Yes | No | SS&A - Security & Conventional Safety Assurance | Line 2 - Corporate Functions | 2024-10-24 | 2025-03-30 | 2025-03-30 | Andrew Wilkinson | James Costello | Inspection | Overall Project | Critical IT platforms (IMS, EDRMA, Tenancy) - Available | Cyber security | Blue | Green | 6.5.25 - JC is reviewing the initial draft of the report, this is to follow. | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
53 | EEW30 - Construct Launch Platform for Marine Bulk Import Facility (SZB/C Security Interface) | Ensure that no EEW30 activity undertaken by SZC could justify trigger of SZB OPA. This is focussed activity until proposed go live date (28/04/2025). After which this will form part of our broader routine SZB/C Security Interface assurance activity. This will run on a monthly basis including a site visit and interface meeting. | 20.11.24 AS/AW: Please add HP Linkage to MBLF. 08.1.25 AW/AS - Speaking with John Brookes over POAP and confirmed date will move to the right till at least end of June 2026 at present. 5.2.25 AW - Will chase JB over POAP. 6.3.25 AW - Have chased up POAP again with John Brookes. 31.3.25 AS: Please change from Inspection to assessment as closely matches the activity better. 12.5.25 AS: We now have POAP from David Mugliston, please move out end date to October 2026. | A | Yes | Yes | SS&A - Security & Conventional Safety Assurance | Line 2 - Corporate Functions | 2024-10-24 | 2026-10-31 |  | Andrew Wilkinson | Andrew Wilkinson | Assessment | Delivery - Site Programme | MBIF Hold Point Release | Health, Safety & Wellbeing | Green | N/C |  | N/A | N/A | 2.1.8 U1 - Commence construction of the Marine Bulk Import Facility |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
54 | New Offices - Secured for London and Manchester (25CA London: VMS & Personnel Security Assurance) | Review of access control measures and procedures are assured against and compliant with: • List N requirements • NSSP • Control Access of People to Sites • EDF/SZC Security Plan • Manage Leavers • Visitor Management Standard This is focussed activity until proposed go live date (Feb 2025). After which this will form part of our broader routine assurance activity. This will run on a monthly basis. SZC VMS requirements are likely to require assurance check-ins until between April - June 2025, we await clarification from EDF Corporate Security. | 20.11.25 AS - Closure date goes past the milestone date to allow for snagging. 05.02.25 AS - Pushing back end date for July, solely owing to Manchester office. No major impact. 31.3.25 AS: Please change from Inspection to assessment as closely matches the activity better. 12.5.25 AS: Please just push this back to end of July from start of July. 30.5.25 AS: Tied into support needed from EDF and Dalkia, we will move to Amber, still currently scheduled for end of July (mainly for London). 24.6.25 AS - Back on plan now for London, but Manchester is Amber, keep BRAG Amber overall, should be no issues with end of the end of September which we shall move the end date too (previously July). 15.8.25 AS: Still proceeding as planned, no further updates, please check with Andrew on Secondary Risks; keep as Amber. 2.9.25 AW - Still waiting on Vodafone, could take longer so please push out from end of September, into end of October. | A | Yes | No | SS&A - Security & Conventional Safety Assurance | Line 2 - Corporate Functions | 2024-10-24 | 2025-10-31 |  | Andrew Wilkinson | Andrew Wilkinson | Assessment | Overall Project | New Offices - Secured for London and Manchester | Health, Safety & Wellbeing | Amber | N/C |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
56 | New Offices - Secured for London and Manchester (25CA London: Physical Security & Design Assurance) | Review of physical security measures and procedures are assured against and compliant with: • List N requirements • NSSP • EDF/SZC 25CA Security Plan • Any requirements from STAMP Assessment This is focussed activity until proposed go live date (Feb 2025). After which this will form part of our broader routine assurance activity. This will run on a monthly basis. | 20.11.25 AS - Closure date goes past the milestone date to allow for snagging. 05.02.25 AS - Pushing back end date for July, solely owing to Manchester office. No major impact. 31.3.25 AS: Please change from Inspection to assessment as closely matches the activity better. 12.5.25 AS: Please just push this back to end of July from start of July. 30.5.25 AS: Tied into support needed from EDF and Dalkia, we will move to Amber, still currently scheduled for end of July (mainly for London). 24.6.25 AS - Back on plan now for London, but Manchester is Amber, keep BRAG Amber overall, should be no issues with end of the end of September which we shall move the end date too (previously July). 15.8.25 AS: Still proceeding as planned, no further updates, please check with Andrew on Secondary Risks; keep as Amber. 2.9.25 AW - Still waiting on Vodafone, could take longer so please push out from end of September, into end of October. | A | Yes | No | SS&A - Security & Conventional Safety Assurance | Line 2 - Corporate Functions | 2024-10-24 | 2025-10-31 |  | Andrew Wilkinson | Andrew Wilkinson | Assessment | Overall Project | New Offices - Secured for London and Manchester | Health, Safety & Wellbeing | Amber | N/C |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
61 | EEW31 - Bailey Bridge Open for Use (CWA Physical Security) | Review of Physical Security aspects with CWA/P including design, measures, and procedures that also are assured against and compliant with: • CSSP • NSSP (Supporting SSSI works and UXO clearance will form part of security design considerations) This is focussed activity until go live date after which this will form part of our broader routine Physical Security assurance activity. This will run on a monthly basis including a site visit. | 11/11/24 - Potential overlap activity with Stuart woodings and Env team. 08.1.25 AW/AS - Speaking with John Brookes over POAP and confirmed date will mvoe to the right till at least end of June 2026 at present. 5.2.25 AW - Will chase JB over POAP. 6.3.25 AW: Chasing up with JB over POAP. 31.3.25 AS: Please change from Inspection to assessment as closely matches the activity better. 12.5.25 AS: We now have POAP from David Mugliston, please push out planned end date to end of October 2026. 15.8.25 AS: Still proceeding as planned, no further updates, please check with Andrew on Secondary Risks; keep as Green. | A | Yes | Yes | SS&A - Security & Conventional Safety Assurance | Line 2 - Corporate Functions | 2024-10-24 | 2026-10-31 |  | Andrew Wilkinson | Andrew Wilkinson | Assessment | Delivery - Site Programme | EEW31 - Bailey Bridge Open for Use | Health, Safety & Wellbeing | Green | N/C |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
62 | EEW31 - Bailey Bridge Open for Use (SZB/C Security Interface) | Ensure that no EEW31 activity undertaken by SZC could justify trigger of SZB OPA. This is focussed activity until go live date (30/05/2025 - will seek clarification on this date as it may now be due for Oct 2025, we will adjust plans accordingly ). After which this will form part of our broader routine Physical Security assurance activity. This will run on a monthly basis including a site visit. | 08.1.25 AW/AS - Speaking with John Brookes over POAP and confirmed date will mvoe to the right till at least end of June 2026 at present. 5.2.25 AW - Will chase JB over POAP. 31.3.25 AS: Please change from Inspection to assessment as closely matches the activity better. 12.5.25 AS: We now have POAP from David Mugliston, please push out planned end date to end of October 2026. 15.8.25 AS: Still proceeding as planned, no further updates, please check with Andrew on Secondary Risks; keep as Green. | A | Yes | Yes | SS&A - Security & Conventional Safety Assurance | Line 2 - Corporate Functions | 2024-10-24 | 2026-10-31 |  | Andrew Wilkinson | Andrew Wilkinson | Assessment | Delivery - Site Programme | EEW31 - Bailey Bridge Open for Use | Health, Safety & Wellbeing | Green | N/C |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
66 | MDS Roads - Start on Site (L3 Reporting Milestone) (SZB/C Security Interface) | Ensure that no MDS roads activity undertaken by SZC could justify trigger of SZB OPA. This is focussed and current activity current as part of wider Roads Design and Security Interface Assurance. | 20.11.24 AS: We'd like to change this to a CAT A following some discussion/reflection on the activity and potential implications of issues with this assurance activity. Slight correction to start date. 08.01.25 AW/AS - Currently no change, but potential to move to the right as dependent on site delivery. 5.2.25 AW - Will chase JB over POAP. 31.3.25 AS: Please change from Inspection to assessment as closely matches the activity better. 12.5.25 - AS: Please push planned end date out to end of August for now; planned end date is currently uncertain from Civils Team. 25.7.25 AW - Due date still very uncertain, alter BRAG to Amber, and push out from August to September for now for the end date till we recieve further information. 15.8.25 AS: Still proceeding as planned, no further updates, please check with Andrew on Secondary Risks; keep as Amber. 2.9.25 AW: Please keep BRAG the same, but push out planned end date to October from September. 15.10.25 AW: I'll enquire with Rob Eddy and come back to you on this shortly. | A | Yes | Yes | SS&A - Security & Conventional Safety Assurance | Line 2 - Corporate Functions | 2024-10-24 | 2025-10-30 |  | Andrew Wilkinson | Andrew Wilkinson | Assessment | Delivery - Site Programme | MDS Roads - Start on Site (L3 Reporting Milestone) | Health, Safety & Wellbeing | Amber | N/C |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
76 | EEW31 - Bailey Bridge Open for Use (LAPEC/BPSS Personnel Security ) | Bespoke Assurance activity to ensure correct LAPEC or BPSS procedures are deployed for EEW31 workforce. Await decision on future use of LAPEC. Assures against: • CSSP • NSSP • Provide Managed Service Worker, Rehire and Terminated Access to SZC • Provide Limited Access for Managed Service Worker, Rehire and Terminate Access to SZC • Provide Temporary Managed Service Worker Access • Control Access of People to Site This is focussed activity until go live date (30/05/2025 - will seek clarification on this date as it may now be due for Oct 2025, we will adjust plans accordingly ). Also we await decision on future use of LAPEC, currently engaging with relevant stakeholders. | 08.1.25 AW/AS - Speaking with John Brookes over POAP and confirmed date will mvoe to the right till at least end of June 2026 at present. 5.2.25 AW - Will chase JB over POAP. 5.2.25 AW - Will chase JB over POAP. 31.3.25 AS: Please change from Inspection to assessment as closely matches the activity better. 12.5.25 AS: We now have POAP from David Mugliston, please push out planned end date to end of October 2026. 25.7.25 AW - Please push back end date to Nov 2026 following update (previously October). 15.8.25 AS: Still proceeding as planned, no further updates, please check with Andrew on Secondary Risks; keep as Green. 15.8.25 AS: Still proceeding as planned, no further updates, please check with Andrew on Secondary Risks; keep as Green. | A | Yes | Yes | SS&A - Security & Conventional Safety Assurance | Line 2 - Corporate Functions | 2024-10-24 | 2026-11-19 |  | Andrew Wilkinson | Andrew Wilkinson | Assessment | Delivery - Site Programme | EEW31 - Bailey Bridge Open for Use | Health, Safety & Wellbeing | Green | N/C |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
77 | MCA HBL-1 BLF Operating Building Available (Personnel Security Access Control) | Review of access controls measures and procedures are assured against and compliant with: Assures against: • CSSP • NSSP • Manage Leavers • Provide Managed Service Worker, Rehire and Terminated Access to SZC • Provide Limited Access for Managed Service Worker, Rehire and Terminate Access to SZC • Provide Temporary Managed Service Worker Access • Control Access of People to Site • Visitor Management Standard This is focussed activity until go live date (25/06/2025 - will seek clarification on this date as it may now be due for Oct 2025, we will adjust plans accordingly ). After which this will form part of our broader routine Personnel Security assurance activity. This will run on a monthly basis including a site visit. | 20.11.24 AS/AW: Please add HP Linkage to MBLF. 31.3.25 AS: Please change from Inspection to assessment as closely matches the activity better. 3.4.25 FG: Can we engage with Tom Brazendale to see if there's any support he can provide or advise on. 12.5.25 - Please push out end date for this activity till at least end of December 2026, as we've had the plan on a page from David Mugliston, but we will still need further clarity. 15.8.25 AS: Still proceeding as planned, no further updates, please check with Andrew on Secondary Risks; keep as Green. | A | Yes | Yes | SS&A - Security & Conventional Safety Assurance | Line 2 - Corporate Functions | 2024-10-24 | 2026-12-31 |  | Andrew Wilkinson | Andrew Wilkinson | Assessment | Delivery - Site Programme | MCA HBL-1 BLF Operating Building Available | Health, Safety & Wellbeing | Green | N/C |  | N/A | N/A | 2.1.8 U1 - Commence construction of the Marine Bulk Import Facility |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
60 | 7.1 Manage Safety Case | This audit was originally planned for earlier in 2024 and covered only SZC-MSC-PRO-003 - Manage Safety Reports Note TWO other procedures in section 7.1 are not being covered in this audit as the scope has already been agreed with auditee sometime ago. (Circa March 2024) SZC-MSC-PRO-001 - Control Modifications During Construction & Commissioning SZC-MSC-PRO-002 - Manage Generic Design Assessment Findings. | 17.10.24 PL: Already arranged - conduct prior to self assessment . Originally planned for Oct 24 but Audit date pushed back to Nov due to other auditee committents 5.11.24 AG: 1st Audit session conducted, requires follow up audit session on 13.11.24 29/JAN/2025 CC: Fieldwork complete and draft report complete. Final meeting with auditees to agree report due 11th Feb 2025. 4.2.25 FG: Please can we review what the outcomes were from this audit once complete. 11.3.25 CC: meeting for agreement performed on 10/03/25 with Catherine Wood , and the audit to discuss a OBS; audit report reviewed and aproved on Insight/Audit Module. Audit Report / results distributed by email 10.04.2025 FD: Added Level 2 ID Process Owner name to column AU and added Procedure Lead Names to column AT. 09.05.2025 AB - Noting due dates for OFI's and Obs is in October, all are currently still open and being worked on. | C | No | No | SS&A - Quality Assurance | Line 2 - Corporate Functions | 2024-11-04 | 2025-01-03 | 2025-01-03 | Fran Gradie | Vanessa Tsanang | Audit | Technical | N/A - No specific Milestone | Nuclear Safety Risk | Blue | Green | Please see Audit report, no Major issues to report back on, Green outcome. | LC14 | N/A | N/A | N/A | N/A | 0 | 2 | 6 | 1 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A | AUD-2387 | Camila | Peter | N/A | Veronique Phillips Jonathan Jones Paul Marks | Catherine Wood | Technical | Internal IMS Audit | 7.0 - Manage Safety Case | 7.1 - Manage Safety Case | Control Modifications During Construction & Commissioning Manage Generic Design Assessment Findings Manage Safety Reports | SZC-MSC-PRO-001 SZC-MSC-PRO-002 SZC-MSC-PRO-003 | 8.2.4 8.3.6 8.2.1 8.3.2 | 8.1 | 6.1.1 8.1.3 |  |  | No
64 | Record Retention | SZC HIGH_LEVEL Retention Schedule for documents and data - TC No. 100951533 Focussed on on-site records for safety and environmental management - risk assessments . Full scope to be agreed | 16.1.25 CT: On-track for a few weeks time. 04.2.25: VT - Adrian confident will be issued shortly, talking to Tom Armstrong. 13.2.25 AG: preliminary results added today subject to internal review, and this will be concluded, along with Insight report added to Insight by 21.2.25. 04.3.25 VT - All non-conformances are now closed. 09.05.25 AB - Recognising most remaining Obs and OFI's are due by Aug and not yet complete, record 8331 is due at the end of May. | C | Yes | No | SS&A - Quality Assurance | Line 2 - Corporate Functions | 2024-11-11 | 2025-02-09 | 2025-02-09 | Fran Gradie | Vanessa Tsanang | Audit | SS&A - Quality Assurance | N/A - No specific Milestone | Quality | Blue | Amber | 2 NC's raised during this audit. 1.There should be alignment between the “Discipline” category that defines the RR in EDRMS (Teamcenter)and the RR definition of discipline in 100951533 SZC High-level retention schedule for documents and data. Assurance generates RR06 from the 5 samples reviewed during this audit whilst 100951533 defines “Assurance” as RR07. This is important because the retention period of RR06 is lower than RR07 in terms of duration, 12 years verses 30 years respectively. 2.The retention criteria stated in the procedure RR10 does not align with the retention criteria selected in EDRMS (Teamcenter) RR07. As demonstrated in the evidence presented above. 4.3.25 VT - All non-conformances are now closed. | LC6 | N/A | N/A | N/A | N/A | 0 | 2 | 2 | 1 | 2 | 0 | 0 | 0 |  | N/A | 0 | 0 | No or N/A | AUD-2385 | Adrian | N/A | N/A | Tom Armstrong Christopher Nunn Fran Gradie Lynne Kellett Richard Bull | Tommy Clarke | PMO | Internal IMS Audit | 9.0 - Project Management & Controls | 9.1 - Scope Management | Manage Documents | SZC-PMC-PRO-008 | 7.5.2 7.5.3 | 7.5.1 7.5.2 7.5.3 | 7.5.1 7.5.2 7.5.3 |  |  | No
119 | Self-assessment. How does sizewelll c track and communicate legislation and regulatory position statements (RPS)? | Conduct self-assessment into how the Sizewell C legal register is maintained, updated and communicated to all relevant parties. | 10.12.24 BH: New item following EA inspection. 06.02.25 BH: End date moved back to end of Feb (was end of Jan), owing to team availability, no risk to other items. 9.5.25 AB: Chased up current OFI's and Minor N/C with Ella/Becky, as some showing as currently overdue (due in May). | C | Yes | No | SS&A - Environmental Services and Assurance | Line 1 - Corporate Functions | 2024-12-10 | 2025-02-27 | 2025-02-27 | Stuart Woodings | Sam Bulmer | Self Assessment | SS&A - Environmental Services and Assurance | N/A - No specific Milestone | Environment | Blue | Amber | Self assessment completed, theme for finding include procedural update required and communication. All actions are listed in the report and tracked on insight | N/A | N/A | N/A | 101439182 | 30810 | 0 | 0 | 11 | 0 | 1 | 0 | 0 | 0 |  |  | 1 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
22 | Self-Assessment Review of SZC emergency plan Q1/Q2 2025 | Review of site emergency Plan 101037577 (conducted by LoD1) | 29.11.24 PG: End date brought forward to end of March as seems reasonable. 6.3.25 PG: Have now handed over site emergency plan to site, who are now having it checked by Suffolk County Council and Emerg services. 2.4.25 - PG: Currently chasing site as should hopefully be near completion, will continue to chase, please extend end date to end of April as not critical right at this time. 12.5.25 pg - Insight ref to follow. 30.5.25 pg: Still chasing Insight ref and numbers, based on Site audit of LC11. 04.07.25 PG - 101561570 and LR31672, Site Compliance Assessment Report Licence Condition 11 added for reference | C | Yes | Yes | SS&A - Emergency Preparedness | Line 1 - Corporate Functions | 2025-01-01 | 2025-04-30 | 2025-04-30 | Andrew Wilkinson | Paul Gomar | Review | Delivery - Site Programme | N/A - No specific Milestone | Health, Safety & Wellbeing | Blue | Green | Emergency Plan updated and version 004 now on teamcentre. 101037577. Main findings are RVPSs have been reduced to improve liaision with emergency services and internal response. Muster locations in the MCA have increase and theis will be a L2 assurance activity we'll be keeping a close eye on. One outstanding action is the plan under DCO agreement is that it's shared with Suffolk CC and Emergency Services. This has been picked up in audit comepleted by the nuclear site compliance team (TC ref to follow) | 8, 11 | N/A | N/A | 101561570 | 31672 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
36 | Permit Readiness Review - IED | Readiness review for incoming permits - IED Permit. MDS/CAP/1. | 06.02.25 BH - Being led by Russel Grinham, kick-off meeting held and a working group will be convened towards this. Permit expected potentially mid-March. 6.3.25 BH - Still on-track and continuing. 3.4.25 BH - Activity completed, Amber as some significant findings including needing a robust mechanism for managing responsibilities for site-wide permits. 9.5.25 AB: Noted that all actions (OFI's - 5 new / 3 existing) are still open, with due dates showing in June. | B | No | Yes | SS&A - Environmental Services and Assurance | Line 2 - Corporate Functions | 2025-01-01 | 2025-03-31 | 2025-03-31 | Stuart Woodings | Sam Bulmer | Review | SS&A - Environmental Services and Assurance | IED Permit Grant | Environment | Blue | Amber | Lack of defines permit management framework, disconnect between permitting and site ops, assignment of compliance ownership of on-site generators, challenges in assigning compliance ownership and need for formal change management framework post-issuance. | N/A | Combustion Activity Permit | N/A | 101492010 | 31164 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
71 | BAT Arrangements Self Assessment | Self assessment of Manage Environment Case procedure and supporting documents (External Contractor). | 6.3.25 BH - In progress and on-track. 26.03.25 - BH on track. 30/04/25 BH - end date push back, resourcing personnel on paternatity leave. 18.06.25 - EJ - final review happening this week, but EW requested deadline pushback to end of July due to urgent EA permit request. 26.06.25 on track. 31.07.25 EJ - JH confirmed that the report is complete, just awaiting confirmation on one of the actions and will be uploaded to TC by 06.08 closing meeting. | C | No | No | SS&A - Operational Permits | Line 1 - Corporate Functions | 2025-01-01 | 2025-07-31 | 2025-07-31 | Stuart Woodings | Emma Wells | Self Assessment | SS&A - Operational Permits | N/A - No specific Milestone | Environment | Blue | Green | Report is completed, awaiting finalisation on TC. | N/A | N/A | N/A | TBC | TBC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
121 | Northern abstraction point investigation | Deviation from requirements of the abstraction permit, 7 storage tanks where 2 were specified in the drawing which is assoicated with the variation letter. | 06.02.25 BH: New item added, reactive assurance, covering investigation on Northern Abstraction Point. Being supported by Ryan and Marcel. 9.5.25 AB - Checked existing actions, 3 look to be in draft with 5 in progress, some due dates appear to have been extended, if we could get an update asap on these, as 4 are minor N/C's, that would be great. 11.9.25 AB - Noting this is a P3 Investigation, going forwards we shall just be capturing P1 Investigations into significant events or HiPO's (High Potential Investigation). | B | No | Yes | SS&A - Environmental Services and Assurance | Line 2 - Corporate Functions | 2025-01-01 | 2025-02-28 | 2025-02-28 | Stuart Woodings | Sam Bulmer | Invesitgation | Overall Project | N/A - No specific Milestone | Environment | Blue | Amber | Inspection complete, this related to a minor non conformance of the abatstraction permit. There were 8 actions arising. The key themes include communications, not following procedure, and recording meeting accurately. | N/A | Water Resources Abstraction Licence - for the abstraction of water during construction | N/A | 101439881 | 30326 | 0 | 0 | 4 | 4 | 4 | 1 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | Yes
136 | Review of Interim second line assurance on site based modifications | To ensure adequate resources and capability within the Site Environment and Sustainability team (line 1) and the site env oversight team to provide second line assurance of FCR and NCR's. | 28.3.25 AB: Was previously down as activity 84, plesae see activity 72, as this was a duplicate, therefore removed. Just added and removed for audit capture purposes. | C | No | No | SS&A - Operational Permits | Line 2 - Corporate Functions | 2025-01-01 | 2025-12-31 |  | Stuart Woodings | Emma Wells | Review | SS&A - Environmental Services and Assurance | N/A - No specific Milestone | Environment | Green | N/C |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | Yes
69 | Critical IT platforms (IMS, EDRMS, Tenancy) - Available (Cybersecurity - Annual IT Health Check) | Assuring wider estate and arrangements aligned to NCSC/HMG expectations. Supports aspects of HMG expectation Internal and External parts. | 17.3.25 JC - On-track for completion. 27.6.25 - AW - Was June, please move to end of October, simply due to workload, poses no major risk. 30.9.25 JC - Internal part came out ok with some findings, the external part, we are just waiting for Pen test partners to come back to us on. Please move deadline to back-end of November, there is no risk for this movement. 15.10.25 AW: Push back to end of year as working on this alongside annual IT healthcheck. | B | Yes | No | SS&A - Security & Conventional Safety Assurance | Line 2 - Corporate Functions | 2025-01-02 | 2025-12-31 |  | Andrew Wilkinson | James Costello | Inspection | Overall Project | Critical IT platforms (IMS, EDRMA, Tenancy) - Available | Cyber security | Green | N/C |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
142 | IR-53492 | The extent and effectiveness of CFSI management at SZC (Steven Heard) | 01/05/25 JB: Added post-Inspection after it was identified it was not listed in the IAAP. | R | Yes | No | External Review - ONR | Line 4 - External | 2025-01-09 | 2025-03-10 | 2025-03-10 | Fran Gradie | Thomas Brazendale | Inspection | Commercial | N/A - No specific Milestone | Nuclear Safety Risk | Blue | Amber | Key findings, inspector’s opinions and reasons for judgement made Sizewell C, and each of the suppliers, demonstrated knowledge of CFSI risks, and their impact on safety. There were good practices in place. However, management of CFSI by any supplier includes managing the risks from, and thereby reducing the likelihood of: dishonesty and malpractice within that supplier’s own organisation; and 'importing' sub-standard items, or receiving unsatisfactory services, from other organisations in relation to that supplier’s final products. The inspections found evidence that suppliers had weaknesses in the implementation of their arrangements for CFSI against these two areas, with a consequent increase in the risk that counterfeit or fraudulent items could be supplied to Sizewell C. | LC17 | N/A | N/A | 101489917 | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
10 | Review of PC Arrangements for managing the Project in the Construction Phase (Review of CPP/ONR Focus) | A root and branch review of the Principal Contractor's Construction Phase Plan for the Sizewell C Main Development Site to provide assurance that previous actions identified have been incorporated, early learning and appropriate mitigating actions from the Construction Risk Register are embedded and the plan is fit for purpose to address all foreseen activities required to support fully the delivery of the Civil Works Programme and the mobilisation of the Civil Works Alliance. | 11.11.24 - Potential crossover with Licence compliance and IMS from NCAPI. 6.3.25 SM: Seen draft report, has a Green meeting. | A | Yes | Yes | SS&A - Security & Conventional Safety Assurance | Line 2 - Corporate Functions | 2025-01-13 | 2025-03-31 | 2025-03-31 | Andrew Wilkinson | Stephen Mason | Assessment | Delivery - Site Programme | LC & PC - Self-assessment programme assurance report | Health, Safety & Wellbeing | Blue | Green | The current Construction Phase Plan is fit for purpose and covers the works taking place currently therefore given a green rating’. There were 4 actions raised on the back of this, as agreed with the delivery team, which are: eview and update of the CPP to Rev 8 with the comments provided. • Refer and link out to the Project Risk Register, this should be being used to inform the CPP • Gather and review all Contractors Management plans as it states, at the time of the review these could not be located • Night working – Shift work medicals are required as per the CPP, G4S are currently the only ones working night shifts. G4S do not currently completed these and were unaware of the requirement. Following the discussion with G4S they are now looking at getting these completed. | N/A | N/A | N/A | 101446589 | 30905 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
122 | SSSI Land Drainage Consent and Flood Risk Activity Permit Self Assessment Audit | Audit based on the Self-Assessment Learning Report 29493 and Teamcenter 101266197. | 25.2.25 CG: New line added. Audit added in the programme. CC: Closing meeting was conducted with the auditee on 19/02/25. Audit report under work. 19/03/25 CC: The audit report reviewed and approved is stored on Insight / Audit Module and on Teamcenter. Audit Report / results distributed by email 10.04.25 FD: Added Level 2 ID Process Owner(s) name to column AU and added Procedure Lead Name(s) to column AT 9.5.25 AB: 1 OFI completed, 1 showing as overdue, and the other observation due in June. | C | No | No | SS&A - Quality Assurance | Line 2 - Corporate Functions | 2025-01-15 | 2025-02-28 | 2025-02-28 | Fran Gradie | Vanessa Tsanang | Audit | SS&A - Operational Permits | N/A - No specific Milestone | Environment | Blue | Green | Please see Audit report, no Major issues to report back on, Green outcome. | LC17 | Flood Risk Activity Environmental Permit | N/A | N/A | N/A | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 1 | No or N/A | AUD-2388 | Camila | Peter | N/A | Hannah Dixon Stuart Woodings | Stuart Woodings | Safety, Security and Assurance | Internal IMS Audit | 6.0 - Health, Safety, Security & Environment | 6.4 - Environmental & Sustainability Management | "Perform Environmental Monitoring Apply for and Maintain Nuclear and Environmental Consent, Permit or Licence Perform Self Assessment Procedure " | SZC-HSE-PRO-042 SZC-HSE-PRO-032 SZC-ACQ-PRO-021 | 8.3.4.1 10.3 | 6.1.4 6.2.1 8.1 9.1.1 9.2 6.1.3 | 9.1.1 |  |  | No
14 | Review of Implementation of SZC UXO Management Plan 2025 v1 (SHEC Focus) | Review of the management controls, and implementation of controls aligned to the UXO Management plan. | 18.10.24 AB - Added to IAAP following consultation with Stephen Mason and Emma Bentley. 05.02.25 SM - Added a further week just to cover off the writing up of the final report. 6.3.25 SM: Finished report last Thursday (draft report), passed across for final comments, Green rating, just management plan to be reviewed. | A | No | Yes | SS&A - Security & Conventional Safety Assurance | Line 2 - Corporate Functions | 2025-02-03 | 2025-03-07 | 2025-03-07 | Andrew Wilkinson | Stephen Mason | Assessment | Delivery - Site Programme | LC & PC - Self-assessment programme assurance report | Health, Safety & Wellbeing | Blue | Green | ‘On completion of the review, a Green rating has been determined’ The only recommendation from this review is to undertake a review and revision of the SZC Main Site UXO Management Plan (101248441 – Rev 2) | N/A | N/A | N/A | 101449913 | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
98 | Review of FCR/NCR procedure and processes | review of FCR/NCR procedure and processes. Looking at the FCR procedure, responsibilities of those named, number of people trained/signed off, how many people envolved in | 29/01/25- BH - This line item has been changed to a self assessment looking at the FCR procedure, responsibilities of those named, number of people trained/signed off, how many people involved in completing FCR categorisation. 14/03/25 EW: My team (Emma's) need to be involved in this assurance process, therefore we have removed the 'review of interim 2nd line assurance on site based modifications', as similar/the same (previously line 84). 30/04/25 BH - this is being changed to a review, the environmental categorisation is a small part of the overall process. This will be looked at by Environmental delivery manager, the procedure is being updated by owner and stakeholders for the process needs to be identified and updated. 29.5.25 EJ: Nearly complete, please push to end of June, this doesn't impact other elements of the programme. | C | No | No | SS&A - Environmental Services and Assurance | Line 1 - Corporate Functions | 2025-02-10 | 2025-06-30 | 2025-05-30 | Stuart Woodings | Sam Bulmer | Review | SS&A - Environmental Services and Assurance | N/A - No specific Milestone | Environment | Blue | Green | FCR procedure currently being split out and updated. Actions relate to stakeholder engagement for procedure update, reviewing ERC training and improving process with triage/screening ensure correct governance process is used. | N/A | N/A | N/A | 101519778 | 31353 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
127 | Client Engagement - Trust Farm MDS Roads | Site visit undertaken / Client engagement | 26.02.25 BH New Item. 3.4.25 BH - Will follow-up on assurance reference numbers (T/C / Insight). 13.5.25 AB - Have asked Ella if she can provide updated commentary, as commentary added mirrored a different assurance activity undertaken by alternative function. | C | No | Yes | SS&A - Environmental Services and Assurance | Line 2 - Corporate Functions | 2025-02-24 | 2025-02-28 | 2025-02-28 | Stuart Woodings | Sam Bulmer | Inspection | Overall Project | N/A - No specific Milestone | Environment | Blue | Green | Liaised with L1 who need to complete additional environmental inspection when the compound is operational e.g. checking generator permits and waste arrangements. | N/A | N/A | N/A | N/A | n/a | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
128 | Client Engagement - SSSI Veg clearance and Silt Curtain | Site visit undertaken / Client engagement | 26.02.25 BH New Item 3.4.25 BH - Will follow-up on assurance reference numbers (T/C / Insight). | C | No | Yes | SS&A - Environmental Services and Assurance | Line 2 - Corporate Functions | 2025-02-24 | 2025-02-28 | 2025-02-28 | Stuart Woodings | Sam Bulmer | Inspection | Overall Project | N/A - No specific Milestone | Environment | Blue | Green | Findings (condition of silt curtain) shared with Line 1 Site Environment & Sustainability Team. Inspections to be undertaken by the team | N/A | N/A | N/A | N/A | n/a | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
129 | Client Engagement - Bucklewood Compound | Site visit undertaken / Client engagement | 04/03/25 BH New item. 3.4.25 bh - complete. | C | No | Yes | SS&A - Environmental Services and Assurance | Line 2 - Corporate Functions | 2025-02-25 | 2025-02-28 | 2025-02-28 | Stuart Woodings | Sam Bulmer | Inspection | Overall Project | N/A - No specific Milestone | Environment | Blue | Green | It has been confirmed that work will start on this document on Monday 10 March, ready for an internal review no later than 28 March. | N/A | N/A | N/A | N/A | 30838 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
16 | Review of the PVPI Compliance - OSI Works 2025 v1 (ONR Focus) | Review of PVPI against the SZC Contractor Standard. | 18.10.24 AB - Added to IAAP following consultation with Stephen Mason and Emma Bentley. 3.4.25 sm - awaiting further details from Site delivery team (Keith and others). | A | Yes | Yes | SS&A - Security & Conventional Safety Assurance | Line 2 - Corporate Functions | 2025-03-03 | 2025-03-28 | 2025-03-28 | Andrew Wilkinson | Stephen Mason | Assessment | Delivery - Site Programme | LC & PC - Self-assessment programme assurance report | Health, Safety & Wellbeing | Blue | Green | This has been completed and given a GREEN status (TC No. 101489959). Actions are: 1. RB22 Barriers, across a majority of the projects it was seen that many of the RB22’s was not adequately filled and, in some instances, secured together using the specified plate and bolts, in accordance with the specification for these. 2.The signage on the pedestrian gates needs to be consistent across all sites and on both sides of the gate to provide suitable warning/safe directional signage. 3. The records of PVPI Co-ordinators and duties have been appointed but the signed records are not stored within the High-Risk Activities folder on sharepoint. | N/A | N/A | N/A | 101489959 | 31128 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
80 | Quarterly review of environmental monitoring data, incidents and actions Q1 | Collaborative review of specialist environmental monitoring data, environmental incidents and open actions | 22/10/24 - Note: Combine with ESG team activities 06.3.25 bh - activity started early. | C | Yes | Yes | SS&A - Environmental Services and Assurance | Line 2 - Corporate Functions | 2025-03-03 | 2025-04-30 | 2025-04-30 | Stuart Woodings | Sam Bulmer | Review | SS&A - Environmental Services and Assurance | N/A - No specific Milestone | Environment | Blue | Green | Data analysed for key themes or trends in Q1 to influence future assurance activities based on Risk, no major issues found. | N/A | N/A | N/A | TBC | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
7 | Bi-annual review of Categorisation | Trend analysis on design mod categorisation of first line DC assurance (of RD and NNB pilot) | 31.3.25 - EW: Duplicate of 13 - removed | C | Yes | No | SS&A - Operational Permits | Line 2 - Corporate Functions | 2025-03-04 | 2025-03-31 |  | Stuart Woodings | Emma Wells | Review | Overall Project | N/A - No specific Milestone | Environment | Green | N/C |  | N/A | N/A |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | Yes
108 | Site Environmental Documentation Review - Q1 | Quarterly review of CEMP/SWMP/RAMS Q1 | 06.3.25 bh - activity started early (was April now March). 3.4.25 bh - now completed. 9.5.25 AB - 1 OFI in review, and 2 in progress, due in June. | C | No | Yes | SS&A - Environmental Services and Assurance | Line 2 - Corporate Functions | 2025-03-04 | 2025-04-30 | 2025-03-31 | Stuart Woodings | Sam Bulmer | Review | SS&A - Environmental Services and Assurance | N/A - No specific Milestone | Environment | Blue | Amber | Actions relating to Delivery and Site E&S needing to ensure environmental doc review process is written in a clear procedure (in accordance with existing PNC 30649), Quality to provide training on Manage Documents procedure. | N/A | N/A | N/A | 101490165 | 31134 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
140 | Independent review of Furgro Offshore (Office and Offshore combined) | ESP-Renewables on behalf of Sizewell C conducted an assurance review of the marine contractor Fugro The first element of the review was an assurance audit conducted by ESP-Renewables on behalf of Sizewell C at Fugro House in Oxford with a terms of references developed against the answers provided in the questionnaire. The second element (operational verification) was executed at the Sizewell C site on the Fugro vessel “Wavewalker1”. | 29.4.25: SM - Following converstaion with Alex, we have retrospectively added this item in for this month (was not previously in the plan). 12.5.25 SM: Looking to re-look at this before we put on Insight, check again in June. 8.9.25 SM - Advised that Steve will follow up on remaining Two as they become complete, but 1 more has been closed out in terms of non-conformances. | R | No | No | SS&A - Security & Conventional Safety Assurance | Line 4 - External | 2025-03-07 | 2025-04-14 | 2025-04-14 | Andrew Wilkinson | Stephen Mason | Review | Delivery - Civils Programme | N/A - No specific Milestone | Health, Safety & Wellbeing | Blue | Amber | The independent offshore assurance report by ESP has been received and communicated to all stakeholders. The offshore verification review sampled fundamental processes and evidence gathered has indicated generally good compliance to Fugro’s overarching management system. A meeting with Fugro and all stakeholders is being planned to discuss the report and to address any outstanding issues. The ESP report highlights that, “a more robust verification process from Fugro would have identified some of the findings within the report”. | N/A | N/A | N/A | 101502674 - ESP Assurance Summary Fugro 101502667 - SZC ESP - Assurance Audit Fugro 101502666 - SZC Vessel Inspection | N/A | 0 | 26 | 4 | 31 | 5 | 2 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
40 | 10.5 - Manage Configuration Change | SZC-CON-PRO-001, Issue (DEN) Design Evolution Notice SZC-CON-PRO-003, Manage Contract Transfer Sheet SZC-CON-PRO-004, Manage Design Change SZC-CON-PRO-006, Manage Design Open Point SZC-CON-PRO-007, Manage Evolutions in the Project List of Applicable Documents SZC-CON-PRO-008, Manage Exemption in the Lists of Applicable Documents SZC-CON-PRO-009, Manage Non-Permanent Baseline Change Note Two other procedures not Published in IMS at time of planning (31/10/2024) Note: there are three other procedures not in IMS framework at time of planning that possibly need to be considered. Combined audit (NCAPI / Env / Security and Conv Safety). | 18.10.24 ACG - From PAP where procedures are Implemented and Published in IMS 11.11.24: Combined audit (NCAPI / Env / Security and Conv Safety). Start date pushed to March 2025. 04.2.25 - Notification issued to Paul Sutherland, date just tbc following further conversations with him. 04.3.25 - Audit start date pushed back to the 14th March, no impact. 26.3.25 VT: Ongoing. 31.3.25 ACG; Fran chased for furtherdates 9.4.25 ACG - End date changed. No further update on dates at present. 10.04.25 FD: Added Level 2 ID Process Owner(s) name to column AU and added Procedure Lead Name(s) to column AT. Removed procedure from SZC-CON-PRO-013 Column AZ as no longer on IMS. 14.4.25 VT: Audit started but is delayed, therefore BRAG is Red, highlighted to Fran as current action we are trying to achieve related to LRQA - OFI. 24.4.25 VT: We now have additional information, audit back-on-track. 21.5.25 VT: BRAG now Green, keep outcome as NC as not yet complete, but nearly there. 27.5.25 VT: Updated to show early completion now and Amber outcome. The list referred to in feedback is the SZC List of Authorised Nuclear Categorisers (TC101033611 V10). 10.SEPT.25 AG, Changing commentry in column W as per VT request. | C | No | No | SS&A - Quality Assurance | Line 2 - Corporate Functions | 2025-03-14 | 2025-06-01 | 2025-05-23 | Fran Gradie | Vanessa Tsanang | Audit | Technical | N/A - No specific Milestone | Nuclear Safety Risk | Blue | Amber | 1 NC raised In SZC-Con-PRO-004 Revision SZC 004 “Manage Design Change” Section 1.5 – Specify DC It states clearly that both Nuclear Safety Categorisers and Authorised Environmental Categorisers must be on the respective approved lists. As defined within the report, the approval was not done by a nuclear categoriser and in the BAT form the respective environmental categoriser was also not on the respective list. | LC16,LC20 | N/A | N/A | 101514520 | N/A | 0 | 2 | 0 | 1 | 1 | 1 | 0 | 0 |  |  | 0 | 0 | No or N/A | AUD-2827 | Adrian | Camila | N/A | Paul Sutherland Tim Wilbraham | Tilly Spencer Paul Sutherland | Technical | Internal IMS Audit | 10.0 - Configuration & Replication Management | 10.5 - Manage Configuration Change | Issue (DEN) Design Evolution Notice Manage Construction Change - Field Change Request (FCR) Manage Contract Transfer Sheet Manage Design Change Manage Design Open Point Manage Evolutions in the Project List of Applicable Documents Manage Exemption in the Lists of Applicable Documents Manage Non-Permanent Baseline Change Manage Post-Handover Open Point Manage NNB Engineering Design Development Manage Referential Change | SZC-CON-PRO-001 SZC-CON-PRO-011 SZC-CON-PRO-003 SZC-CON-PRO-004 SZC-CON-PRO-006 SZC-CON-PRO-007 SZC-CON-PRO-008 SZC-CON-PRO-009 | 8.3.6 8.5.2 8.2.4 8.5.6 8.3.4.1 7.1.6 8.3.3 8.2.4 | 8.1 7.5.3 |  |  |  | No
104 | IR-53489 | Implementation of organisational control arrangements through Nuclear Baseline and MoC - (Marta Carnicero) | 04.02.25 TB: May be defferred to a later date, will advise of new date in due course. 27.02.25 JB: Officially still going ahead, but we have heard that this could well be cancelled. 04.03.25 TB: No technical assurance required by Licensing SS&A, business as usual, brought forward from original April date to March. 27.3.25 TB/JB: Please remove, this did not proceed in the end. | R | Yes | No | External Review - ONR | Line 4 - External | 2025-03-18 | 2025-03-19 |  | Fran Gradie | Thomas Brazendale | Inspection | Human Resources | N/A - No specific Milestone | Nuclear Safety Risk | N/C | N/C |  | LC 36 | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | Yes
114 | IR-53490 | Planned inspection Nuclear Services Company to look at progress of the 7 focus areas highlighted in previous inspection - (Jonathan Jones / Marta Carnicero) ONR Assessment of NSCo Change of Ownership / Implementation. See Letter from ONR (December 2023) under 101211735 (7 focus areas are identified within this). | 25/03/2025 JB: ONR RAG is Green, one or more regulatory issues (Level 4) expected to be raised in relation to Management Systems Manuals for Nuc Services, SZC, HPC and NO. Report expected by ONR in coming weeks. 04.02.25 TB: Start date moved back to 18th March, with Marta and Jonathan Jones leading on this. Due to changes in ONR Senior leadership, there may be some further changes in when dates land for upcoming ONR Inspections. 27.3.25 JB: Updated, teamcenter ref will be 'to follow' once the report is finalised. | R | Yes | No | External Review - ONR | Line 4 - External | 2025-03-18 | 2025-03-19 | 2025-03-19 | Fran Gradie | Thomas Brazendale | Inspection | Technical | N/A - No specific Milestone | Nuclear Safety Risk | Blue | Green | Generally positive inspection with limited findings, Green RAG provisionally given. One or more regulatory issues (Level 4 - advice) expected to be raised in relation to Management Systems Manual and documentation of working arrangements. Report expected by ONR in coming weeks. | LC17 | N/A | N/A | 101501615 | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
9 | PAS2080 Certification - Stage 2 Audit | Certification of Management System Against PAS2080 | 10.1.25 PL: PAS 2080 is on the 31st March for 5 days (previous start date down was showing as January). 25.3.25 PL: Planned end date changed to 18/04/25 due to the timming to release the audit report. The actual audit dates were not changed. Included query related to the ownership and Milestones linked (included as comment). 09.4.25 PL Include BRAG / RAG changes plus insert 1 finding (OFI) plus incude key finding and remove values from major live and end of activity cells according to audit report 10.04.25 PL Awaiting results of LRQA technical review. 9.5.25 AB - Noted that for the 1 OFI, due date is end of October 2025. | R | Yes | No | External Review - LRQA | Line 4 - External | 2025-03-31 | 2025-04-18 | 2025-04-04 | Fran Gradie | Christopher Thompson | Audit | Overall Project | PAS 2080 - gap analysis complete | Reputation & Social License | Blue | Green | One OFI raised - It may be prudent to consider other roles in the business and where they may benefit from a tailored formal or mandated element of training. | LC17 | N/A | N/A |  |  | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | Yes | AUD-3084 | Graham Colebeck (LRQA) | Peter Long | Mark Fenton | [13 empty] | No
11 | Inspection of NSL Interface Boundary with SZB | Conduct periodic inspection of the NSL interface boundary with SZB as part ofSZC/SZB relicensing programme | 04.02.25 TB: Still being planned for April time. 04.03.25 TB: Discussions with Alex Beer are ongoing (Site nuclear comliance manager). 3.4.25 - AW: Potential for Andrew's team joining forces, Rob Eddy to invite if possible please. | C | Yes | Yes | SS&A - Nuclear Licence Compliance | Line 2 - Corporate Functions | 2025-04-01 | 2025-04-30 | 2025-04-15 | Fran Gradie | Thomas Brazendale | Surveillance | Overall Project | N/A - No specific Milestone | Nuclear Safety Risk | Blue | Green | There remains good clarity between SZB and SZC of the work required to address both SZB and SZC's boundary requirements as each licensee progresses its applications with the ONR and EA to carry out relicensing this year, subject to Relocated Facilities programme delivery. | LC2 | N/A | 1.3.10 U1 - Fuel reciept onto the site |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
15 | Review of Life Fire Safety in Design Process 2025 v1 (ONR Focus) | To review the effectiveness of the maintained design integrity branch, process, for Life fire safety and design (ONR Focus topic). Mike Hind to support. | 18.10.24 AB - Added to IAAP following consultation with Stephen Mason and Emma Bentley. 3.4.25 SM - Liam has scoped assessment and he's speaking with stakeholders. 12.5.25 SM: We still need the Strategy/scope from Paul Marks Team, Mike is supporting, please push back end date till TBC, SM will respond shortly. 16.5.25 LR: Liam Rawcliffe has confirmed this is on-track for the end of this month. 30.05.25 LR: Pending internal review, this should result in a Green RAG based on the recommendations raised. TC/Insight reports to follow. | A | Yes | No | SS&A - Security & Conventional Safety Assurance | Line 2 - Corporate Functions | 2025-04-01 | 2025-05-30 | 2025-05-30 | Andrew Wilkinson | Stephen Mason | Assessment | Delivery - Site Programme | LC & PC - Self-assessment programme assurance report | Health, Safety & Wellbeing | Blue | Green | 5 findings, 3 around design and 2 with construction. 1. Complete and adopt forthcoming SZC Fire Replication Strategy (July 2025) 2. Identify key stakeholders and complete organogram (July 2025) 3. Confirm Client touch points for continued engagement throughout the project lifecycle (July 2025) 4. Implement risk-based assurance programme (Q4 2025) 5. Site Delivery Fire Team Lead or delegate to attend future Fire Co-Ord meetings (June 2025) | N/A | N/A | N/A | 101545118 | N/A | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
18 | Site Emergency Arrangements 2025/2026 | On-site emergency arrangments dip checks - includes document reviews (Incident Management Plans, RAMS), site attendnace - Emergency Arrangment Forums and onsite inspections - ongoing. | 29.11.24 PG: To be led by site team which we will dip into as part of our planned surveillence. 6.3.25 PG: Assurance strategy now published on teamcenter. Quarterly plan alongside site delivery to be agreed by end of March. 12.5.25 PG: Some challenges from Site delivery, plan to go back again in the next few weeks with a more detailed plan to share with them. 2.7.25 CJ: Please update, Function assurred will be Site Delivery, and Line of defence will be Line 2 (not 1). 15.07.25 PG: Planned start and end date changed to 01 Apr25 - 31 Mar26 as this is an annual assurance task - alligning with the SZC year Apr to Mar 15.10.25 PG - Have now altered timelines so we capture this 6 monthly instead. | C | Yes | Yes | SS&A - Emergency Preparedness | Line 2 - Corporate Functions | 2025-04-01 | 2025-10-31 |  | Andrew Wilkinson | Paul Gomar | Surveillance | Delivery - Site Programme | N/A - No specific Milestone | Health, Safety & Wellbeing | Green | N/C | 03/04/2025 EP Construction Strategy Document published and reviewed ready for PCSR. | 8, 11 | N/A | N/A | 101270587 Emergency Arrangements Assurance Strategy |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
137 | LC08 Warning Notices | Ensure that suitable and sufficient notices are kept on the site and posted in positions and characters as to be conveniently read for the purposes: 1.) of informing persons of any warning signal, 2.) ensuring exits and measures to be taken in the event of a fire or emergency. | 03/04/2025 LC08 inspections and documentation review schedule has been added to the EP Assurance Plan and will be discussed with site delivery in April. 3.4.25 FG: Please have a conversation with Tom Brazendale on arrangements for handover of LC8 to Andrew. 8.4.25 AW: Spoken to Tom, I shall now look to take up the role as manager for LC's 2 and 8 as well as LC 11 which I currently own, pending MoC. 12.5.25 PG - Will follow-up with LC8 Compliance Audit outcome details from Site Delivery. 30.5.25 PG: Raised that MOC still going through, Marta is chasing, speaking with David Barrett for L1 Assurance Plan. 27.6.25 - Met with Dave and discussed way forward. | C | Yes | Yes | SS&A - Emergency Preparedness | Line 2 - Corporate Functions | 2025-04-01 | 2026-03-31 |  | Andrew Wilkinson | Paul Gomar | Surveillance | Overall Project | N/A - No specific Milestone | Health, Safety & Wellbeing | Green | N/C |  | 8, 11 | N/A | N/A | 101406973 | 30277 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
27 | ISO 27001 (Cybersecurity - Information Security) prep and Gap Analysis | ISO 27001 assurance requirements Assures against: • SZC Statement of Applicability for ISO 27001:2022 ISMS • SZC Controls Framework Gap Analysis 3rd and 4th of April 25 | 20.11.24 AW: End date moved from March to December 2025, as achieving ISO Accreditation will potentially take a little more time. 20.11.24 AW: Item linked to NCISF as this assurance activity supports this milestone. 06.3.25 AW: Gap analysis - April this year, Stage 1 in September 2025, then stage 2, potentially end of March 2026. 17.3.25 JC: Agree that the assuring function for this needs to be LRQA, update to end dates (final end date was end of Dec 2025), as Stage 1 will be Dec (not July), and we anticipate Stage 2 to be in March 2026. 25.3.25 PL: Stage 1 and Stage 2 of the ISO 27001 separated in the ID 132 and 133. 09.04.25 PL - The results of the gap analysis have been populated with 26 Gaps categorised as OFI's , The finding column is populated with the summary of the audit - BRAG and RAG updated, Auditor , Observer and auditee inserted . AUD name inserted. 9.5.25 - Noted that all OFI's have due dates of the 2nd June (less than a month away now). | R | Yes | No | External Review - LRQA | Line 4 - External | 2025-04-03 | 2025-04-18 | 2025-04-04 | Andrew Wilkinson | James Costello | Audit | Overall Project | National Institute of Standards and Technology Cyber Security Framework Maturity Score of 3 | Cyber security | Blue | Amber | Based on the objective evidence sampled, the organisation should seek to continue with the great start that has been made implementing the information security management system. Various GAPs have been highlighted during the assessment and the organisation should look to implement these before conducting their stage 1 and 2 assessment. | LC17 | N/A | N/A |  |  | 0 | 0 | 26 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A | AUD-3196 | Lee Davies (LRQA) | Peter Long | James Costello | James Costello | [12 empty] | No
86 | Review of COMAH arrangments against HPC | Review to support a SZC COMAH plan and ensure adequate arranegements are captured. | 11.12.24 BH Start and end dates have been pushed back, to start in March rather than Jan. this is due to the COMAH arrangements not being fully established. This will have no effect or risk on other activities. 05.03.25 BH Issy undertaking training 06.03.25. Further Kick off will be April, pre-planning work already commenced though, as COMAH plan not yet setup. 26.03.25 BH - Issy completed. Kick off meeting to start in April, so move start date to April. 3.4.25 - Please check with Isabel Simpson on this activity. 01.07 - BH - Underway and on track. 02.10.25 Underway and on track. IS now attends HPC COMAH working group. 20.10.24 BH Spoke to Emma, this is on track | C | No | No | SS&A - Operational Permits | Line 1 - Corporate Functions | 2025-04-03 | 2025-12-20 |  | Stuart Woodings | Emma Wells | Review | Overall Project | N/A - No specific Milestone | Environment | Green | N/C |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
35 | SSSI Protection Review - (Drain Diversion) | Review for the protection of the SSSI Q2/Q3. | 22/10/24 - Note: Only Carly and Hannah Auditor Trained. 3.4.25 - Please look to liase with Andrew's team for security considerations. 2.5.25 - BH: This has kicked off early in May, was previously scheduled to kick off in July. 29.5.25 SB: Has already kicked off, please adjust end date to September from Dec 2025, so Q2/Q3 (rather than Q3/Q4). 26.06.25 - changed to a review, review underway and on track. 17.07.25 EJ: item completed. | C | No | Yes | SS&A - Environmental Services and Assurance | Line 2 - Corporate Functions | 2025-04-07 | 2025-09-30 | 2025-07-17 | Stuart Woodings | Sam Bulmer | Review | Delivery - Site Programme | SSSI Drain Diversion | Environment | Blue | Green | Actions relating to CWA self-assurance (documentation updates, sharing information for review) and SEST to plan proportionate schedule of inspections for high-risk permitted works. | N/A | Flood Risk Activity Environmental Permit | N/A | 101569379 | 31784 | 0 | 0 | 5 | 1 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
51 | 8.3 - Quality | SZC-ACQ-PRO-006, Conduct Management Review SZC-ACQ-PRO-013, Manage External Audit of SZC Activities SZC-ACQ-PRO-016, Manage Non-Conformance SZC-ACQ-PRO-020, Perform Internal Audit -Excluded to ensure independancy (PNC-359) SZC-HSE-PRO-047, Manage Physical Sample - Excluded because introduced in 8.3 on 25/03 after the audit planification date. Rest of procedures captured in Audit Activity ID 138 | 18.10.24 ACG - From PAP where procedures are Implemented and Published in IMS. 04.3.25 VT - Start date will be w/c 14th April (previously start of April). 02.04.25 VT - 1st part to kick-off on the 15th April now (just 1 day difference), 2nd part will be in June with INA, so there will be a 2nd line to come in due course. 10.04.25 FD- Added Level 2 ID Process Owner(s) name to column AU and added Procedure Lead Name(s) to column AT FD 24.04.25- Updated with audit outcomes. AB 1.5.25 - Corrected owners for audit, as Fran asked that we please remove Steven Heard as his will come later (Audit). VT - 9.5.25: Report still not issued yet, will update when it is. 12.5.25 VT: Updated now, with an Amber rating. | C | No | Yes | SS&A - Quality Assurance | Line 2 - Corporate Functions | 2025-04-15 | 2025-05-05 | 2025-05-23 | Fran Gradie | Vanessa Tsanang | Audit | SS&A - Quality Assurance | N/A - No specific Milestone | Quality | Blue | Amber | • Incomplete and inconsistently followed procedures • Deficiencies in action management and tracking • Lack of performance trend analysis and reporting • Non-compliance in the 2024 Management Review process | LC6 LC17 | N/A | N/A | N/A | N/A | 0 | 4 | 2 | 2 | 4 | 4 | 0 | 0 |  |  | 0 | 0 | No or N/A | AUD-2909 | Vanessa | Faun | N/A | Fran Gradie | Fran Gradie | Safety, Security and Assurance | Internal IMS Audit | 8.0 - Assurance, Compliance & Quality | 8.3 - Quality | Conduct Supply Chain Audit Manage Contractor Site Non-Conformance Manage End of Manufacturing Report Manage Quality Execution Conduct Management Review Manage External Audit Of SZC Activities Manage Non-Conformance Perform Internal AuditSite Non-Conformances, Field Change Requests and Request for Information | SZC-ACQ-PRO-027 SZC-ACQ-PRO-004 SZC-ACQ-PRO-031 SZC-ACQ-PRO-018 SZC-ACQ-PRO-006 SZC-ACQ-PRO-013 SZC-ACQ-PRO-016 SZC-ACQ-PRO-020 SZC-ACQ-PRO-032 | 8.4.1 8.7 10.2 7.5.2 8.5.1 8.5.6 8.6 8.1 4.1 9.3 10.3 8.2.1 9.2 8.2.4 8.7 | 8.1 6.1.4 10.1 10.2 10.3 7.5.2 9.3 9.2 | 8.1.4.1 6.1.4 10.1 10.2 10.3 9.3 9.2 |  |  | No
47 | ISO 45001 Stage 1 assessment 2025 | LRQA ISO 45001 Stage 1 assessment | 18.10.24 AB - Added to IAAP following consultation with Stephen Mason and Emma Bentley. Sam Parker is contact. 11.12.24 PL: ISO 45001 has been postponed following consultation with LRQA till April 2025 (was Jan 2025), this is to ensure further time is given for preparatory work and should not result in any immidiate issues. 05.02.25 SM: Still on-track for Mid-April. 3.4.25 CT: Georgina supporting actions on the insight system. 10.04.25 PL added audit number, auditor and SME information. 28.04.25 PL - In the gap analysis - 8 Major NC's now closed out as a result of the stage 1 visit. In the stage 1 just formally agreeing the final report now. Provisionally we have 1 Major NC, and 8 minor NC's for this visit. Requested to input information from the stage 1 into the SSA tracker today (Monday 28th April 25). 9.5.25 AB: Noted that all non-conformances (major and minors), have due dates in August 2025. 2.9.25 AB: Live n/c's - the 1 Major is closed, and all other minor's have been brought forward onto the Stage 2 line for consistency and tracking. | R | No | No | External Review - LRQA | Line 4 - External | 2025-04-23 | 2025-04-25 | 2025-04-25 | Andrew Wilkinson | Stephen Mason | Audit | Overall Project | ISO 45001 Certification | Health, Safety & Wellbeing | Blue | Amber | Minor NCR regarding the process for identifying the organisations internal and external issues. Minor NCR regarding the process for setting the framework for objectives and targets. Minor NCR regarding the evaluation of the effectiveness of training. Minor NCR regarding the inclusion of diversity considerations within the communications procedure. Minor NCR regarding the process for planning how to achieve the organisations OH&S objectives. Minor NCR regarding the process for communicating audit findings. Minor NCR regarding the process for communicating the outputs from the management review. Minor NCR regarding the process to review existing risks, following an accident or incident. Major NCR regarding the process to describe and complete the evaluation of legal compliance. | LC17 | N/A | N/A |  |  | 0 | 0 | 3 | 0 | 8 | 0 | 1 | 0 | 18th July 2025 | 4th August 2025 | 0 | 0 | Yes | AUD-3200 | Matt Evans (LRQA) | Peter Long | Sam Parker / Steve Mason | [13 empty] | No
123 | IR-53470 | SZC Design Maturity - Inspection of LC 14 Implementation - (Catherine Wood) | 27.02.25 JB: Officially still going ahead, butwe have heard that this could well be cancelled. 27.02.25 JB: ONR are developing their intervention strategy, therefore all forthcoming inspections may well be cancelled or re-purposed. 3.4.25 TB - Please remove, this will no longer be proceeding as ONR are re-considering their future inspection regime. | R | No | No | External Review - ONR | Line 4 - External | 2025-04-23 | 2025-04-24 |  | Fran Gradie | Thomas Brazendale | Inspection | Technical | N/A - No specific Milestone | Nuclear Safety Risk | N/C | N/C |  | LC 14 | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | Yes
92 | Pre-ISO 14001 Review (June) - Main Site Activities | Inspection: Internal audit of main site activities. This will be related to the topic chosen for the June 14001 Audit | 06/02/25 BH: Will double-check dates with Carly and come back to you. 06.03.25 BH Changed due to audit being brought forward to 3rd/4th/5th June. This should be a review (changed from self-assessment). 29.5.25 EJ: Will catch up with Carly and update this afternoon. | C | No | Yes | SS&A - Environmental Services and Assurance | Line 2 - Corporate Functions | 2025-04-24 | 2025-05-31 | 2025-05-31 | Stuart Woodings | Sam Bulmer | Inspection | Delivery - Site Programme | N/A - No specific Milestone | Environment | Blue | Green | Minor issues identified associated with waste management (used spill kits in non haz waste bins, waste missing labels) and a minor stockpile issue which has now been rectified. Sites visited: SSSI Southern and Northern Abutment Compounds, and Expanded Compound | N/A | N/A | N/A | N/A | 31399, 31419 and 31426 | 0 | 0 | 13 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
105 | IR-53471 | Quality assessment at Framatome (Sizewell C overview). (Daniel Otamendi Salazar). The inspection will assess whether SZC has adequate control over Framatome’s quality management arrangements and the quality achieved for both the components themselves and for records relating to their production | 04.02.25 TB: May be defferred to a later date, will advise of new date in due course. 27.02.25 JB: Officially still going ahead, but we have heard that this could well be cancelled. 23.04.25 JB: Pushed back a week to the end of April. | R | Yes | No | External Review - ONR | Line 4 - External | 2025-04-29 | 2025-04-30 | 2025-04-30 | Fran Gradie | Thomas Brazendale | Inspection | Technical | N/A - No specific Milestone | Nuclear Safety Risk | Blue | Green | The inspection was rated GREEN (adequate) with several good practices identifies including strong safety/ quality culture and process for management of non-conformance reporting. ONR also highlighted areas of focus including SZC ensuring robust arrangements are place at Framatome manufacturing plant following its transformation project, recognising that SZC would be one of the first major customers post-transformation. Other areas for future focus included CFSI. INA was present during the inspection and agrees with the rating and ONR’s finding. | LC 19 | N/A | N/A | 101543776 | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
131 | HSE records | Compare ‘work happening on site’ vs ‘records kept into the system’ in compliance with Record Retention Schedule. (Audit supported by Environment and Health and Safety SME's) Wide range of H&SE documents: Induction & Safety records, Daily safety logs, RAMS, permit to work records, waste management and disposal records, PPE compliance and usage logs, contractor safety audits/inspections, Incident records, contractors’ licences & certificates, safety performance metrics, etc. Training on SZC Documentation requirements provided to the Supply Chain AND defined training criteria for SZC people managing documentation. | 11.Mar.25 ACG - New Audit - Dates to be confirmed within April/May Window. 11 .Mar.25 ACG - Columns Q and S have been filled in as H&S however this audit also will cover Environmenatal records. 20.MAR.25 ACG - Date to start confirmed W/C 28th of April 9 APR 2025 ACG - ADDED SME's 10.04.25 FD: Added Level 2 ID Process Owner(s) name to column AU and added Procedure Lead Name(s) to column AT. 21.5.25 VT: Audit is ongoing, report is looking like Amber, but still tbd when report is issued. 27.5.25 VT: Updated as now completed, with an Amber outcome due to minor non-conformances. 12.9.25. LiveMinor NC changed | C | No | Yes | SS&A - Quality Assurance | Line 2 - Corporate Functions | 2025-04-29 | 2025-06-28 | 2025-05-23 | Fran Gradie | Vanessa Tsanang | Audit | SS&A - Security & Conventional Safety Assurance | N/A - No specific Milestone | Health, Safety & Wellbeing | Blue | Amber | 3 NC Raised 1. A RAMS document reviewed was two issues out of date. (Expanded Compound MCA) Whilst the correct revision was found once this was pointed out by a follow up email, it does bring into question how the RAMS are distributed and how older revisions are taken out of circulation, so they are not used unintentionally. Pictures in the attached file on the “RAMS tab” clearly show document photographed during the audit was at revision P04 or 04. Photographs subsequently provided by Fernando Galan Bienes were at revision P06 or 06.Thus, there is clear evidence that obsolete information was present in the compound. This type of information needs to be put beyond use. 2. Paper copies of CEMPs were viewed on site all present. However, when reviewing the RR status on EDRMS (Teamcenter) the RR is incorrect in the auditor’s opinion, based on the criteria set in 100951533 SZC HIGH-LEVEL RETENTION SCHEDULE FOR DOCUMENTS AND DATA All CEMPs are stored under RR03 (Health and Safety). It should be RR02 Environment & Land. 5 examples out of 8 checked all at RR03. Note: it is a time consuming job to compare paper copies to EDRMS due to missing/incorrect EDRMS references. Need to search via contract references or approval sheet references, if available. 3. The CEMP at OCA TVB presented was revision 1 and the approval document was for revision 2. However the document is actually at revision 4. | LC 6 | N/A | N/A | 101511995 | N/A | 0 | 4 | 2 | 2 | 3 | 1 | 0 | 0 |  |  | 0 | 0 | No or N/A | AUD-3054 | Adrian | N/A | Andrew Swindell Becky Hudson | Tommy Clarke Fran Gradie Steven Heard Timothy Wilbraham | Tommy Clarke | PMO | One-off audits | 9.0 - Project Management & Controls | 9.1 - Scope Management | Manage Documents | SZC-PMC-PRO-008 | 7.5.2 7.5.3 | 7.5.1 7.5.2 7.5.3 | 7.5.1 7.5.2 7.5.3 |  |  | No
39 | 10.2 - Manage Interfaces | SZC-CON-PRO-018, Manage Delivery Interfaces Note ONE other procedure not Published in IMS at time of planning. SZC-CON-PRO-016 - Manage Construction Interface Data | 18.10.24 ACG - From PAP where procedures are Implemented and Published in IMS 11.11.24: Combined audit (NCAPI / Env / Security and Conv Safety). 26.03.25: Initial aligment is being conducted related the Manage Delivery Interfaces procedure with Anne Christie and George Riley. 26.3.25 - VT: This won't need to be a combined audit. 08.04.25 - CC: Audit on the Manage Delivery Interfaces Procedure Scheduled to 29/04 with George Riley. Audit for the procedure Manage Design Interfaces still need agreement with Paul Sutherland (awaiting response) 10.04.25 FD: Added Level 2 ID Process Owner(s) name to column AU and added Procedure Lead Name(s) to column AT. 01.05.25: AB: Spoke with Camila following meeting with Fran, as question on if the Manage design interfaces needs to be pushed back a little seeing as the team will have already gone through large audit with Manage configuaration changes. 08.05.25: CC: Change in the audit scope was made; the procedure SZC-CON-PRO-005, Manage Design Interfaces, from Technical Directorate will be verified in the future; the reason is due to the large audit that Paul Sutherland and Team is going through at the moment (Manage Configuration Change). 21.05.25: CC: Interviews still being conducted this week; closing meeting is booked to 23/05/25. 23.05.25: CC: closing meeting rescheduled to 04/06/2025, as requested by the Interface Team. 06.06.25: CC: Closing meeting performed, audit report on going, to be released on 12/06/25. 17.06.25: CC Audit report was released/approved. | C | No | Yes | SS&A - Quality Assurance | Line 2 - Corporate Functions | 2025-05-01 | 2025-07-30 | 2025-06-12 | Fran Gradie | Vanessa Tsanang | Audit | SS&A - Nuclear Licence Compliance | N/A - No specific Milestone | Quality | Blue | Amber | Two Minor Non-Conformities were identified during the audit: 01) - Lack of clarity regarding inputs and outputs of procedural activities, which may lead to gaps related to understanding of the process and activities execution; - Information missing/or incomplete related "Record Requirements", "Resources" , "Supoorting Documentation" and "Records" chapter. - Lack of clarify for some responsiilities defined in the chapter "Activities / RASI chart table". 02) - Insufficient documented evidence of competence, raising concerns about the robustness of competency assurance and the knowledge retention. | LC17 LC20 | N/A | N/A | 101453292 | N/A | 0 | 1 | 1 | 1 | 2 | 2 | 0 | 0 |  |  | 0 | 0 | No or N/A | AUD-2939 | Camila | Faun | N/A | David Redpath | Paul Sutherland | Technical | Internal IMS Audit | 10.0 - Configuration & Replication Management | 10.2 - Manage Interfaces | Manage Construction Interface Data Manage Delivery Interfaces Manage Design Interfaces | SZC-CON-PRO-016 SZC-CON-PRO-018 SZC-CON-PRO-005 | 8.1 8.3.2 |  |  |  |  | No
145 | Review of Aspects and Impacts Register | Environmental Consenting and Assurance review of Environmental Aspect and Impact Assessment Register to identify all relevant activities under each aspect and any impacts from abnormal situations. Control measures, probability and severity scores reviewed and checked to ensure relevant legislation is up to date. | 30.5.25 EJ: New item retrospectively added. 26.06.2025 Aspects and Impacts register was reviewed and updated by multiple people within the wider Environment team. The register itself is the deliverable in this case, and has been up-rev’d on TC accordingly. The register is to be reviewed every six months, according to the Aspects and Impacts procedure, but no other findings in this case. | C | Yes | No | SS&A - Environmental Services and Assurance | Line 2 - Corporate Functions | 2025-05-01 | 2025-06-02 | 2025-06-09 | Stuart Woodings | Emma Wells | Review | Risk | N/A - No specific Milestone | Environment | Blue | Green | N/A - Impacts nad Aspects register has been reviewed and updated | N/A | N/A | N/A | 101030949 | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
146 | Review of Ecological Clerk of Works Competency Standard | Production of SZC ECOW competency standard, and subsequent review of whether contractors are meeting the required standard. | 30.5.25 EJ: New item retrospectively added. 19.06.25 EJ - PH clarified that an investigation was not required, but he is completing a review of ECoW CVs against the standard. 30.06 BH extented to finalise report (previously June end date). 18.07.25 EJ - catching up with Pat to progress this next week, extending deadline to end of July. 22.07.25 EJ - PH provided Insight number but unable to submit for review until CWA have confirmed actions. 25.07.25 EJ - item now completed on Insight. | B | No | Yes | SS&A - Environmental Services and Assurance | Line 2 - Corporate Functions | 2025-05-01 | 2025-07-31 | 2025-07-25 | Stuart Woodings | Sam Bulmer | Review | SS&A - Environmental Services and Assurance | N/A - No specific Milestone | Environment | Blue | Green | Issues identified with ECoW Competency on site, leading to requirement to produce ECoW Competency and Training Standard. Subsequent review of all ECoW CVs undertaken against the standard. Actions identified where ECoW(s) did not meet the standard. | N/A | N/A | N/A | 101428025 | 31829 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
147 | Noise Monitors Investigation | Investigation of unsafe installation of batteries for nois monitors. Investigation to cover procurement processes, installation and arcadis/szc inspections of monitors. | 30.5.25 EJ: New item retrospectively added. 30.5.25: Whilst the Investigation itself is completed and was presented at SIRG on 14/05, actions are still under review and will be presented again at next SIRG 11/06. Actions and LR reference have been provided. TC reference to follow when finalised. 18/06/2025 EJ - Investigation to be presented at July SIRG but report is finalised and actions agreed. 11.9.25 AB - Noting this is a P3 Investigation, going forwards we shall just be capturing P1 Investigations into significant events or HiPO's (High Potential Investigation). | B | No | Yes | SS&A - Environmental Services and Assurance | Line 2 - Corporate Functions | 2025-05-01 | 2025-06-30 | 2025-06-20 | Stuart Woodings | Sam Bulmer | Invesitgation | SS&A - Environmental Services and Assurance | N/A - No specific Milestone | Environment | Blue | Amber | Actions relating to noise monitoring equipment (downtime, inspection, status checks) and notification of breaches. Investigation presented at May SIRG, follow-up presentation by Steve Mannings / Scott Miller at June SIRG. | N/A | N/A | N/A | 101554087 / 101558426 (SIRG) | 30687 (Action 66028) | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | Yes
148 | Review of Risk Register | Review of Risk Register to be completed by Environmental Managers | 30.5.25 EJ: New item retrospectively added. 27.6.25 BH: Report just being finalised, please move to 14th July (was end of June). 25.7.25 SW: Please push back to end of September (previously end of July), just some final elements required but it's progressing well. 23.9.25 BH: I'll check with Naoise, push back to Mid-October for now. 16.10.25 BH: Please push out to mid-Nov as some work ongoing in this area with risk champions. Champions for every team and then fed up to a mangers meeting | C | No | No | SS&A - Environmental Services and Assurance | Line 2 - Corporate Functions | 2025-05-01 | 2025-11-15 |  | Stuart Woodings | Emma Wells | Review | SS&A - Environmental Services and Assurance | N/A - No specific Milestone | Environment | Green | N/C |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
151 | Review of Event Categorisation Register | Review and update of event categorisation register | 10.06.25 EJ new item added | C | No | No | SS&A - Environmental Services and Assurance | Line 2 - Corporate Functions | 2025-05-01 | 2025-06-30 | 2025-06-01 | Stuart Woodings | Sam Bulmer | Review | Overall Project | N/A - No specific Milestone | Environment | Blue | Green | Register updated for implementation | N/A | N/A | N/A | 100931287 | 63625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
87 | Inspection based on EA Site Env Report | The EA need to submit an SER which will detail any inspcetions they are due to perform | 06.02.25 BH: Will catch up with Emma on this one. 06.03.25 BH: Expected SERP due to be issued April 2025. Time frame for completion dependant on report contents (was previously Jan for kick-off). 25.03.25 BH following questions from AB can confirm this is an external audit, waiting on EA information. 3.4.25 BH - Move to May still awaiting official kick-off date from EA. 29.5.25 EJ: Will need to check with Emma when she's back from leave and update BRAG. 16.10.25 BH: I'll check with Emma on this one for current status and tool. 16.10.25 BH: EA Report is now through, this is a Green outcome, report details to follow, but we also now have an inspection plan within this plan. | B | Yes | No | External Review - EA | Line 4 - External | 2025-05-05 | 2025-10-27 | 2025-10-16 | Stuart Woodings | Emma Wells | Inspection | Overall Project | N/A - No specific Milestone | Environment | Blue | Green | Output of this is a Green and the main output is we have a list of EA Compliance Inspections which are now included on this Assurance plan. | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
91 | Pre-ISO 14001 Review (June) - Internal Resource and Competency | Review topic: Internal resource and competency. This will be related to the topic chosen for the June 14001 Audit | 22/10/2024: Note - May share with ESG team to help guide future PAS audits. 06.03.25 BH Changed due to audit being brought forward to 3rd/4th/5th June. (Originally due to start on 1st March). 29.5.25 EJ: Will catch-up with Carly and update this afternoon. 4.6.25 CM: Updated to reflect Insight number although this is confidential so please speak to myself (Carly Merrett) for any further questions on this Insight report. 5.6.25 AB - Please can the outcome RAG be double-checked as looking at the audit RAG's, it states that any MNC would neccesitate an Amber outcome rather than the Green shown? 10.6.25 CC: Spoke with Carly Merret about the RAG status being changed from Green to Amber, following the definition of the SSA Quality Column tab. | C | No | Yes | SS&A - Environmental Services and Assurance | Line 2 - Corporate Functions | 2025-05-05 | 2025-05-31 | 2025-06-02 | Stuart Woodings | Sam Bulmer | Review | Overall Project | N/A - No specific Milestone | Environment | Blue | Amber | Review of environmental competency (internal) and confirmation from managers that training profiles have been completed prior to the ISO audit. Action relates to training profiles not being completed / managers not confirming team training up to date. | N/A | N/A | N/A | N/A | 31458 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
106 | IR-53491 | Inspection to assess the effectiveness of the Governance Framework, post the implementation of the Esha - (Bene Howard) | 04.02.25 TB: Could be defferred to a later date, will advise of new date in due course. 27.02.25 JB: This inspection is subject to us agreeing and implementing the ESHA, so subject to change. 3.4.25 TB - Please remove, this will no longer be proceeding as ONR are re-considering their future inspection regime. | R | Yes | No | External Review - ONR | Line 4 - External | 2025-05-05 | 2025-05-06 |  | Fran Gradie | Thomas Brazendale | Inspection | Overall Project | Financial Close (L0) | Nuclear Safety Risk | N/C | N/C |  | LC 36 | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | Yes
141 | Heather Bryant Follow-up Review on CDM Arrangements | The purpose of this 2nd review, which could be termed an extension to the 1st review, is to consider the SZC responses to each of the recommendations and confirm that the original support given to the HWGTW proposal, notably SZC being the PC, remains valid. | 29.4.25: SM - New activity added today. 27.5.25: MH - Initial report is under 'legal priveledge' and a further interview is required mid-June, so please push the end date to the end of June, this should not cause any immidiate risk to the schedule. 23.6.25: SM - Report is still under legal privilidge but being finalised and will then be sent for comment to certain people. 25.6.25: EB/SM - Please move planned end date back to end of July until we know more on Legal privilidge and report finalisation. 23.7.25: EB - Still under legal privilidge at present, please push back from 30th July to 5th August till we hear more, and I shall check with Steve following his return from leave. 14.8.25 SM: Advised that report complete, shared with relevant parties, and there were 9 actions from it, with owners identified, escalated query regarding if we can share TC report via legal contact Emma Franck-Gwinell. | A | Yes | Yes | SS&A - Security & Conventional Safety Assurance | Line 4 - External | 2025-05-13 | 2025-08-05 | 2025-08-14 | Andrew Wilkinson | Stephen Mason | Review | Overall Project | N/A - No specific Milestone | Health, Safety & Wellbeing | Blue | Amber | 9 reccomendations, with actions being agreed/progressed with owners. Report legally privlidged, please see Steve Mason. | N/A | N/A | N/A | Legally Privlidged - Please see Steve Mason for further infromation (or Emma Franck-Gwinnell for Legal queries) | TBC | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
43 | 12.7 - Learning & Growing | SZC-PEO-PRO-001, Assess Individual Competency SZC-PEO-PRO-003, Develop New Training SZC-PEO-PRO-004, Enrol in Training SZC-PEO-PRO-005, Evaluate Training SZC-PEO-PRO-006, Implement Training Events | 18.10.24 ACG - From PAP where procedures are Implemented and Published in IMS 11.11.24: Combined audit (NCAPI / Env / Security and Conv Safety). 1.5.24: Start date pushed to 1st May 2024 26.3.25 - VT: This won't need to be a combined audit. 3.4.25 - Check with Steve Mason on work being done with TPR's. 10.04.25 FD: Added Level 2 ID Process Owner(s) name to column AU and added Procedure Lead Name(s) to column AT 14.4.25 FD: Add Insight ref and updated start date to 27.05.25. 01/05/25 PL Amend start date to 21/05/25 plus change site activity and suppport to No. 14.5.25 FD: As part of Audit planning, it has been agreed that procedures SZC-PEO-PRO-004, Enrol in Training & SZC-PEO-PRO-001, Assess Individual Competency will be audited as part of the 2026 May audit of process 12.4 - Performance Management, as these procedures are currently under review and process architecture may need changing. 5.6.25 AB - Checked with Vanessa, we should move BRAG to Amber to align with current changes to audit plans for this one, as there is movement which makes it slightly off-plan but it's recoverable. 11.6.25 - VT: 2nd part of the audit should ocnclude by 24th of July. 11.08.2025 FD: Updated progress BRAG to blue as audit now completed. Report due to be distributed later today 12.08.2025 FD : Amended 'actual end date' to 12.08.25 as report was issued today. | C | No | No | SS&A - Quality Assurance | Line 2 - Corporate Functions | 2025-05-21 | 2025-06-30 | 2025-08-12 | Fran Gradie | Vanessa Tsanang | Audit | Human Resources | N/A - No specific Milestone | People & Skills | Blue | Amber | 1 NC Raised: The reviewed procedures contain multiple inconsistencies, such as inaccurate scopes, undocumented references, inefficient or illogical process steps, and misaligned role assignments. | LC6, LC12 & LC17 | N/A | N/A | 101576311 | N/A | 0 | 3 | 0 | 3 | 1 | 1 | 0 | 0 |  |  | 0 | 0 | No or N/A | AUD-3335 | Faun | Peter Long | N/A | Rachel Kerry Nicole Vale | Marta Carnicero | Human Resources | Internal IMS Audit | 12.0 - People | 12.7 - Learning & Growing | Assess Individual Competency Develop New Training Enrol in Training Evaluate Training Implement Training Events | SZC-PEO-PRO-001 SZC-PEO-PRO-003 SZC-PEO-PRO-004 SZC-PEO-PRO-005 SZC-PEO-PRO-006 | 7.2 | 7.2 | 7.2 |  |  | No
115 | IR-53501 | Plant Vehicle People Interface (PVPI) Inspection - (Hayley Critchley) | 20.11.24: TB - Dates changed to April to reflect when the activity needs to take place in line with ONR requirements. 04.02.25 TB: May be defferred to a later date, will advise of new date in due course. 23.04.25 JB: Start date was originally 28th April, but pushed back till May now by ONR and just 1 day now. | R | Yes | Yes | External Review - ONR | Line 4 - External | 2025-05-22 | 2025-05-22 | 2025-05-22 | Fran Gradie | Thomas Brazendale | Inspection | Delivery - Site Programme | LC & PC - Self-assessment programme assurance report | Health, Safety & Wellbeing | Blue | Green | Pending ONR's internal review and Board meeting, this should result in closure of the regulatory letter received from ONR in 2024. INA attended the meetings and consider that SZC provided good evidence covering improved arrangements and their implementation. Areas for improvement noted were around COSHH for Eye protection and the use of 2 way radios at the TCA Refuelling area (ATEX Requirements). | N/A | N/A | N/A | 101552198 | N/A | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
154 | Review of Control of Contaminated Land and Groundwater Procedure | Review and update of contaminated land and groundwater procedure | 18.06.25 EJ - new item added. 23.9.25 SB - Drafted, going thorugh review, push back to end of October. 16.10.25 BH - To go through the October IRP | C | No | No | SS&A - Environmental Services and Assurance | Line 2 - Corporate Functions | 2025-06-01 | 2025-11-15 |  | Stuart Woodings | Sam Bulmer | Review | Overall Project | N/A - No specific Milestone | Environment | Blue | Green | Document was reviewed and updated. Changes made in document | N/A | N/A | N/A | IMS reference SZC-HSE-PRO-033 | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
155 | Review of Land Quality Strategy | Review and update of SZC Land Quality Strategy | 18.06.25 EJ - new item added | C | No | No | SS&A - Environmental Services and Assurance | Line 2 - Corporate Functions | 2025-06-01 | 2025-06-30 | 2025-06-27 | Stuart Woodings | Sam Bulmer | Review | Overall Project | N/A - No specific Milestone | Environment | Blue | Green | Strategy updated for implementation | N/A | N/A | N/A | 101513814 | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
68 | Temporary Sea Defence - Hold Point Released to Commence Temporary Sea Defence (SZB/C Security Interface) | Ensure that no TDS activity undertaken by SZC could justify trigger of SZB OPA. This is focussed activity until go live date (03/04/2025 - will seek clarification on end date , we will adjust plans accordingly ). After which this will form part of our broader routine Physical Security and SZB/C interface assurance activity. This will run on a monthly basis including a site visit. 7.8.25 - RE: Update start date to Sept 2025 for now, discussing with the team and will come back to you. No risk, SZB are keeping us in the loop. 7.8.25 - RE: Apologies, please put this back as 2nd June start and Green for BRAG, as Work has started inside the MCA. we are pilling and this is about 6 weeks in. We did have a stoppage from B, while some aspects were reviewed in the cross site mods, but we are underway again. It has not gone very far. | 6.3.25 AS - Currently on-track but potential to move to the Right (design element), will update next month. 31.3.25 AS: Please move to June as looks to be moving to the Right. 31.3.25 AS: Please change from Inspection to assessment as closely matches the activity better. 12.5.25 AS: Recieved updated POAP from David Mugliston, we need to push out planned end date from Aug 25, till end of September 2026. 15.8.25 AS: Still proceeding as planned, no further updates, please check with Andrew on Secondary Risks; keep as Green. | A | Yes | Yes | SS&A - Security & Conventional Safety Assurance | Line 2 - Corporate Functions | 2025-06-02 | 2026-09-29 |  | Andrew Wilkinson | Andrew Wilkinson | Assessment | Delivery - Site Programme | Temporary Sea Defence Hold Point Release | Health, Safety & Wellbeing | Green | N/C |  | LC 2 | N/A | 2.1.6 U1 - Temporary Sea Defence |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
90 | Marine Licence Condition Procedure | Self assessment of procedure. | 27.11.24: SM - One of these was already conducted in November 2024, no major issues. We have therefore moved this secondary self-assessment back to Summer 2025. 29.5.25 ej: Will check with Stephen Roast and update. 18.06.25 EJ: Discussion with SR confirmed that self-assessment of procedure no longer possible. INA assessment of the procedure has led to overhaul which superseded SR procedure update. SR now reviewing Corporate Operations procedure update, and self-assessment will likely follow next year once process is implemented. 26.6.25 BH - Confirmed to delete, a review of the procedure will be scheduled later down the line instead. | C | No | No | SS&A - Marine Team | Line 1 - Corporate Functions | 2025-06-02 | 2025-06-30 | 2025-06-20 | Stuart Woodings | Stephen Roast | Review | SS&A - Marine Environment | N/A - No specific Milestone | Environment | N/C | N/C | Review of overhaul to Manage DCO and DML Requirement procedure. Existing procedure did not include DML conditions or handover and compliance stages, which has now been amended. | N/A | N/A | N/A | N/A (IMS Procedure) | N/A (IMS Procedure) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | Yes
84 | ISO 9001 Audit (June) | 3rd Party Audit/Inspection - Combined audit with ISO 14001 (Please see activity ID 93) | 19.3.25 PL/AB: New activity - We have added this line, it will be carried out alongside line 93 - ISO 14001. 3.4.25 fg - look to see if further prep activities need to be added please. 23.06.25- PL: Actual end date updated; Included the information related the findings ( 1 Minor nc and 3 OFI). BRAG / RAG status Updated. 24.6.25 AB - I have taken the 2 live minor nc's that were ongoing off the archived prior audit, and onto the live line here for continual monitoring. | R | Yes | Yes | External Review - LRQA | Line 4 - External | 2025-06-03 | 2025-06-20 | 2025-06-23 | Fran Gradie | Christopher Thompson | Audit | Overall Project | N/A - No specific Milestone | Quality | Blue | Amber | 1 new Minor nc raised on FCR/NCR process. The previous 2 nc from november/2024 audit (management review and efectivess of corrective actions) remains open. | LC17 | N/A | N/A |  | N/A | 0 | 0 | 3 | 0 | 1 | 3 | 0 | 0 |  |  | 0 | 0 | No or N/A | AUD-3442 | Matt Evans | External (LRQA) | N/A | [13 empty] | No
93 | ISO 14001 Audit (June) | 3rd Party Audit/Inspection - Combined audit with ISO 9001 (Please see activity ID 84) | 6.3.25 - BH: Now moved forward to June, was previously July. 18.06.25 - EJ. Audit completed, draft Audit report only at this point. Final TC and Insight references will be added when final report is received. 23.06.25- PL: Included actual end date; Included the information related the findings ( 1 Minor nc and 1 OFI). BRAG / RAG status Updated. | R | Yes | Yes | External Review - LRQA | Line 4 - External | 2025-06-03 | 2025-06-20 | 2025-06-23 | Stuart Woodings | Sam Bulmer | Audit | Overall Project | ISO 14001: Surveillance Audit Complete | Environment | Blue | Amber | 2 minor NC's closed on waste duty of care and ecological competency, as per LRQA report AR-3442. A new minor nc was raised, related environmental inspections. | LC17 | N/A | N/A |  | N/A | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 0 |  |  | 0 | 0 | No or N/A | AUD-3442 | Matt Evans | External (LRQA) | N/A | [13 empty] | No
149 | SS&A Review of the H&S Standard-Emergency Preparedness | Assurance of the Principal Contractors Emergency Preparedness & Response Standard TC: 101371756 | 30/05/25 PG: New task / initial kick off meeting with site EP and H&S on 3/6/25. 24.6.25 PG - End date was supposed to be end of June, but wish to push back to 11th July now owing to some extra time just being required to agree the report with Site Delivery Colleagues. No risk with extended time. 27.6.25 - Connor is working on finalising report. 04.07.25 PG - Draft report 101505024 and LR31655 - to be confirmed with site delivery EP team on 8 July. 08.07.2025 CJ- report finalised and actions agreed aftter meeting with site delivery EP team on this day. Learning report submitted and confirmed as a result. Awaiting action completion (set for 28th August) | B | Yes | Yes | SS&A - Emergency Preparedness | Line 2 - Corporate Functions | 2025-06-03 | 2025-07-11 | 2025-07-08 | Andrew Wilkinson | Paul Gomar | Review | Delivery - Site Programme | N/A - No specific Milestone | Health, Safety & Wellbeing | Blue | Green | Line 1 assurance plan required EP Standard should be formally issued to all relevant contractors Line 1 EP team to take ownership of the Incident Controller process Site EP team to support the delivery of the Emergency Marshal course Incident Controller details should be clearly displayed and communicated by contractors Request contractors verifiable records of emergency drills and exercises conducted to date. Ensure that the documents references are checked on the next revision. Clarify the CDM scope of this document and amend to remove any ambiguity of its application. Document ownership is incorrect and needs amending. | 11 | N/A | N/A | 101505024 | 31655 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
150 | Ecology Investigation: Patridge Nest | Investigation required relating to LR 31403 - death and damage to a patridge nest. | 05.06.25 EJ - added new investigation in progress by Ecology Specialist. 20.06.25 EJ - report completed, to be presented at SIRG. 27.6.25 - Was previously ending in June, please move to mid-July for time for finalisation of report. 18.07.25 EJ - the report is finished but cannot be uploaded to Teamcenter until it has been presented at SIRG on 6th August. 11.9.25 AB - Noting this is a P3 Investigation, going forwards we shall just be capturing P1 Investigations into significant events or HiPO's (High Potential Investigation). | B | No | Yes | SS&A - Environmental Services and Assurance | Line 2 - Corporate Functions | 2025-06-03 | 2025-08-08 | 2025-08-06 | Stuart Woodings | Sam Bulmer | Invesitgation | SS&A - Environmental Services and Assurance | N/A - No specific Milestone | Environment | Blue | Green | AFIs summarised in SIRG report slides. Deemed to be an unfortunate accident as a result of legal works activities. | N/A | N/A | N/A | 101583991 | 31403 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | Yes
55 | Review of effectiveness of Org Learning Screening meetings 2024/2025 | Review of effectiveness of Org Learning Screening meetings including review of coding accuracy. Structure of Screening meetings is under review & coding is being refreshed - check to ensure funtioning as required | 11.11.24: Add conventional safety to be included in this please with Stephen Mason. 1.5.25: HB - Changed Category to Cat C as better represents this item, and end date, pushed to November 2025, no major impact. 08.10.25: AH has added findings as per conversation with AB. | C | No | No | SS&A - Performance Improvement | Line 2 - Corporate Functions | 2025-06-09 | 2025-11-07 | 2025-10-08 | Fran Gradie | Hilary Best | Review | Overall Project | N/A - No specific Milestone | Quality | Blue | Green | • A minority of SZC Weekly Screening Meetings have been cancelled due to quoracy issues during 2025 so far, see results on page 6 of this report. • The SZC Weekly Screening Meeting committee are demonstrating the ability to effectively event categorise LRs as few event codes have been altered as outcomes of SIRG or HIRG meetings, see results on pages 10 and 13 of this report. • The review of investigation actions being returned or cancelled have been logged in the OL team’s SZC Investigations Tracker where there are currently three Level 2 investigations and fourteen Level 3 investigation actions that were either cancelled or no longer required. • It was not possible to review the frequency of regular actions being returned due to assigning incorrect action owners in the SZC Weekly Screening Meeting, as this is currently not a function within the Insight system. • The SZC Weekly Screening Meeting will require an annual assurance review, this action will be recorded in the NCAPI Assurance Tracker. • There was not enough time allocated to focus on all External Learning during the SZC Weekly Screening Meeting, and the PI Manager and OL Team are currently working on delivering this in a new meeting ‘SZC External Learning Meeting’ to enable Continuous Improvement for Learning at SZC. Once the process is completed and embedded an assurance activity covering the effectiveness of external learning will be implemented. The report summarises that the SZC Weekly Screening Meeting runs as expected, the meeting generally codes LRs correctly and requests investigations at the right level, Green rating. | LC 7 | N/A | N/A | 101615654 | 32328 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | N/A |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
143 | Industrial Health, Safety One-off Audit | SZC-HSE-PRO-021, Manage Occupational Health, Safety and Environmental Inspections (informal audit) | Check effectiveness of actions from AUD-14001 for Environment & AUD-1411 for H&S and identify any new risks Raised as a result of ISO 45001 Audit April 2025. 21.5.25 VT - Title ammended slightly, to align with the fact this is a one-off intelligence audit to support the team, rather than part of the wider L2 IMS Audit Plan. 24.6.25 AG - Ongoing, should complete as scheduled. Only a LR will be raised on this though as it's a one-off inteligence audit to support the team rather than wider L2 IMS Audit. 31.7.2025. ACG This is not a conventional audit it was more of a guideance conversation in preparation for the ISO45001 audit. There are no Findinds or Ratings just a very simple LR 31787 that will generate some actions for the H&S and Env Team | C | No | Yes | SS&A - Quality Assurance | Line 2 - Corporate Functions | 2025-06-16 | 2025-07-25 |  | Fran Gradie | Vanessa Tsanang | Audit | SS&A - Security & Conventional Safety Assurance | N/A - No specific Milestone | Quality | Green | N/C |  | LC6 LC17 | N/A | N/A |  | 31787 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A | Informal - No Insight Report | Adrian |  | N/A | Andrew Wilkinson | Steven Mason | Safety, Security and Assurance | One-off audits | 6.0 - Health, Safety, Security & Environment | 6.1 - Industrial Health & Safety | Manage Occupational Health, Safety And Environmental Inspections | SZC-HSE-PRO-021 |  | 9.1.1 | 6.1.4 9.1.1 9.2 |  |  | Yes
130 | Mobilise Contract Partner to Site (12.5) | SZC-PEO-PRO-018, Mobilise Contract Partner to Site | 11.Mar.25 ACG - New Audit - Dates to be confirmed within May/June Window. 14.Mar.25 ACG - Audit date agreed with Davina Simpson. 3.4.25 FG - Please can outcome of audit be shared with Steve Mason. 10.04.25 FD: Added Level 2 ID Process Owner(s) name to column AU and added Procedure Lead Name(s) to column AT. 24.6.25 AG - On track, should complete as planned. 4.JULY.2024 AG - All the metrics complete audit report sent etc. | C | No | Yes | SS&A - Quality Assurance | Line 2 - Corporate Functions | 2025-06-18 | 2025-07-18 | 2025-07-04 | Fran Gradie | Vanessa Tsanang | Audit | Delivery - Delivery/PDO | N/A - No specific Milestone | Health, Safety & Wellbeing | Blue | Green | Very well run procedure no significant findings. One Observation on an incorrect EDRMS Reference in a template | LC 9, LC6,LC10,LC12,LC17 | N/A | N/A | 101554877 | N/A | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A | AUD-2953 | Adrian | N/A | N/A | Matt Reed | Rachel Kerry | Human Resources | Internal IMS Audit | 12.0 - People | 12.5 - Onboarding | Manage Contract Partner to Site | SZC-PEO-PRO-018 | 8.1 | 8.1 | 8.1.1 |  |  | No
100 | Review of SME input in procurement space Q1 / Q2 | Review of SME input in procurement space Q1/Q2. Review of tracker, look at gaps where environment management SME not involved in certain tender review | 06.02.25 BH - Still awaiting data to review, so push back to end of Feb from start of Jan, end date is now brought forward a little to mid-April. 6.3.25 BH: Start date to move back (as review of end of Q1 Data) so would not make sense to start in Feb (was Feb). 2.5.25 BH: Start date needs to be pushed back to allow for ISO 14001 work for Carly as this is a priority and kicks off in early June, previously showing as 14th April - 31st July, pushed back to start at the end of June. 29.5.25 ej - Will check with Carly and come back to this one. 27.6.25 - Started and on track 15.08.25 BH Item complete | C | No | Yes | SS&A - Environmental Services and Assurance | Line 2 - Corporate Functions | 2025-06-21 | 2025-08-01 | 2025-08-12 | Stuart Woodings | Sam Bulmer | Review | Overall Project | N/A - No specific Milestone | Environment | Blue | Green | Actions to improve functions of Contracts tracker and input from EMLs during procurement. Review of CBL document portal to be undertaken. | N/A | N/A | N/A | 101752083 | 31997 | 5 | 7 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
81 | Quarterly review of environmental monitoring data, incidents and actions Q2 | Collaborative review of specialist environmental monitoring data, environmental incidents and open actions | 22/10/24 - Note: Combine with ESG team activities. 25.7.25 - Please push back to end of August, just some final elements to complete (previously July). No additional risk from deadline extension. 01/09/2025 EJ - deadline to be mid Sep based on lack of available info and resourcing. 23.9.25 BH - Push back to mid-October, just finishing this one off now. 16.10.25 BH: Updating today. | C | Yes | Yes | SS&A - Environmental Services and Assurance | Line 2 - Corporate Functions | 2025-07-01 | 2025-10-15 | 2025-10-01 | Stuart Woodings | Sam Bulmer | Review | SS&A - Environmental Services and Assurance | N/A - No specific Milestone | Environment | Blue | Green | Review of environmental monitoring data, some observations and OFI identified. detailed in the learning report | N/A | N/A | N/A | N/A | 32278 | 0 | 3 | 3 | 1 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
97 | Hold Point Preparation- Marine Beach Landing Facility | Marine Beach Landing Facility - August 2025 | 22/10/24 - Note: Combine with ESG team activities. 29.5.25 EJ - Will check with Stephen Roast today. 9.5.25 SB: Ella will check with Becky to check with the HP Manager, very likely this could slip again owing to the Holdpoint date. 18.06.25 - EJ HP Manager confirmed platform date is now 1st July. 26.06.25 - on track, but back of July not start. 31.07.25 - moved back to finalise report. 2.9.25 BH: Please move end date back from 31st August to 12th September as need time to write report and finalise. | A | No | Yes | SS&A - Environmental Services and Assurance | Line 2 - Corporate Functions | 2025-07-01 | 2025-09-12 | 2025-09-24 | Stuart Woodings | Sam Bulmer | Review | Overall Project | Marine Beach Landing Facility - Hold Point Released to Commence Marine Bulk Import Facility | Environment | Blue | Green | Review of the Environmental aspects of the MBIF Hold Point review has shown the process is robust and that environmental SQEP has oversight of the process and completion. Rather than the current arrangement of reviewing every hold point within the project programme , OFI1 has reccomended that Hold point reviews will be done on a risk based approach and the trigger will be initiated by the environmental hold point manager. | N/A | N/A | 2.1.8 U1 - Commence construction of the Marine Bulk Import Facility | 101608014 | 32232 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
109 | Environmental Documentation Review - Q2 | Quarterly review of CEMP/SWMP/RAMS Q2 |  | C | No | Yes | SS&A - Environmental Services and Assurance | Line 2 - Corporate Functions | 2025-07-01 | 2025-07-31 | 2025-07-31 | Stuart Woodings | Sam Bulmer | Review | SS&A - Environmental Services and Assurance | N/A - No specific Milestone | Environment | Blue | Amber | Two NC relating to CEMPs being signed off without permit condition/references, and SWMP at Status B for over a month. Additional concern about Teamcenter review function for document reviews, which inhibits oversight and assurance due to restricted access. Risk registers to be updated. | N/A | N/A | N/A | 101569051 | 31912 | 0 | 2 | 3 | 1 | 2 | 2 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
152 | Audit of Permitting EMS | Internal audit focusing on permitting EMS process, EMS documents, any associated guidance, and how it works in practice. | 10.06 EJ new item added 14.08.25 to be removed because recetly audited by the quality team and INA. Procedures have also recently been updated. this will be revisited in 2026. | B | No | No | SS&A - Environmental Services and Assurance | Line 2 - Corporate Functions | 2025-07-01 | 2025-08-31 |  | Stuart Woodings | Sam Bulmer | Audit | Overall Project | N/A - No specific Milestone | Environment | Green | N/C |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | Yes
159 | Self-assessment review of warning notices 2025 / LC 08 | 2LOD Annual review of site delivery Self Assessment of LC08 warning notices | 17.9.25 PG - Spoke to Leon Cashman, hoping that end of September should still be ok. 23.9.25 PG - Report could take a little longer, please can you push back to end of October. | C | Yes | Yes | SS&A - Emergency Preparedness | Line 2 - Corporate Functions | 2025-07-01 | 2025-10-30 |  | Andrew Wilkinson | Paul Gomar | Review | Delivery - Site Programme | N/A - No specific Milestone | Health, Safety & Wellbeing | Blue | Green | Satisfactory outcome, no major issues to report, Dave Barrett will provide report. | 8 | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
156 | IR-54090 | Inspection of ENSA Facilities in Spain, related to SZC Specification, control, and oversight of PZR Welding and NDT. | 24.6.25 - MA - New item added. Rocio Camin Fernandez and Daniel Otamendi supporting. | R | Yes | No | External Review - ONR | Line 4 - External | 2025-07-10 | 2025-07-10 | 2025-07-10 | Fran Gradie | Thomas Brazendale | Inspection | Delivery - Site Programme | N/A - No specific Milestone | Quality | Blue | Green | Green overall rating with the ONR happy that from what was sampled adequete LC19 arrangements are in place for welding and NDT of the PZR at SZC. Regulatory advice provided that SZC should consider how it can demonstrate that a formal review of DQI surveillence guides has been performed. • Decision Recording: SZC should ensure that key technical decisions—particularly those involving SQEP input—are formally documented (focused on decision-making and record-keeping). This may be followed up at a future intervention. | LC 19 | N/A | N/A | 101585330 | N/A | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
46 | 11.2 Supply Chain Management Quality Assurance | Joint Audit with INA (under INA Lead and process) SZC-SCM-PRO-002 - AGS - Contract Management There is one other procedure that is outside of the IMS Framework that maybe relevant. Contract Administration. 1. SME questions from PDO Quality, quality plan e.g. CFSI. 2. Assure ourselves that requirements of quality are adequetly captured within the current process. 3. To check that the PDO Quality team has got suitable and sufficient resource to delivery the requirments of the AGS procedure. Combined audit (NCAPI / Env / Security and Conv Safety) | 11.11.24: Combined audit (NCAPI / Env / Security and Conv Safety). 05.11.24: DD - The start date of this audit is likely to move to the Right a little, owing to the fact there is currently an audit being carried out by Deloitte through Peter Chambers. Don is checking with David Redpath. 12.12.24: AB - Following conversation with Don, we've temporarily moved this to Q4 2025, to be confirmed nearer the time. 10.04.25 FD: Added Level 2 ID Process Owner(s) name to column AU and added Procedure Lead Name(s) to column AT. 21.5.25 VT: This audit will sit in INA's plan too. But we will lead this part on Contract Management. 11.6.25 - VT: Joint audit with INA alongside supply Chain (was previously Oct but will now be in July 2025). | C | No | Yes | SS&A - Quality Assurance | Line 2 - Corporate Functions | 2025-07-22 | 2025-09-30 | 2025-09-12 | Fran Gradie | Vanessa Tsanang | Audit | Commercial | N/A - No specific Milestone | Quality | Blue | Green | 0 NC | LC6 LC17 | N/A | N/A |  | N/A | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A | AUD-3629 | Peter H. Bex D. | Annette S. Vanessa T. | N/A | Greg Brown | Greg Brown | Supply Chain | Internal IMS Audit | 11.0 - Supply Chain Management | 11.2 - Contract Management | AGS - Contract Management Contract Administration Supplier Relationship | SZC-SCM-PRO-002 | 8.4.3 | 8.1 | 8.1.4 |  |  | No
138 | 8.3 - Quality | Joint Audit with INA (under INA Lead and process) SZC-ACQ-PRO-018, Manage Quality Execution SZC-ACQ-PRO-027, Conduct Supply Chain Audit Scope may be extended to 2.3 Oversee Manufacturing Objective: Provide assurance that SZC has defined and implemented a robust strategy for performing oversight of its supply chain. | Joing Audit with INA 8.4.25 - New item added by Vanessa Tsanang. 10.04.25 FD: Added Level 2 ID Process Owner(s) name to column AU and added Procedure Lead Name(s) to column AT 1.5.25 - AB: Removed Fran's name from owner at her request, as she says this Audit will come under Steven Heard only. 21.5.25 VT: Audit has moved, will now be July rather than June start date, agreed with relevant parties. | C | No | Yes | SS&A - Quality Assurance | Line 2 - Corporate Functions | 2025-07-22 | 2025-09-30 | 2025-09-12 | Fran Gradie | Vanessa Tsanang | Audit | SS&A - Quality Assurance | N/A - No specific Milestone | Quality | Blue | Amber | NC 01 (Minor) – Supplier Oversight Audit Action Tracking Evidence that Audit Actions are not being tracked and controlled as per SZC procedure/process to ensure timely completion, potentially leading to loss of Quality improvements at a supplier of important nuclear safety pumps (e.g. Safety Injection, NI Component Cooling & Emergency SG Feed Water). AFI 01 – Clarity of Supply Chain Quality Line 1 and Line 2 Oversight 1OBS No 2 & 7 | LC6 LC17 | N/A | N/A |  | N/A | 1 | 2 | 0 | 0 | 1 | 1 | 0 | 0 |  |  | 0 | 0 | No or N/A | TBC | Peter H. Bex D. | Annette S. Vanessa T. | N/A | Steven Heard | Steven Heard | PDO Quality | Internal IMS Audit | 8.0 - Assurance, Compliance & Quality | 8.3 - Quality | Conduct Supply Chain Audit Manage Contractor Site Non-Conformance Manage End of Manufacturing Report Manage Quality Execution Conduct Management Review Manage External Audit Of SZC Activities Manage Non-Conformance Perform Internal AuditSite Non-Conformances, Field Change Requests and Request for Information | SZC-ACQ-PRO-027 SZC-ACQ-PRO-004 SZC-ACQ-PRO-031 SZC-ACQ-PRO-018 SZC-ACQ-PRO-006 SZC-ACQ-PRO-013 SZC-ACQ-PRO-016 SZC-ACQ-PRO-020 SZC-ACQ-PRO-032 | 8.4.1 8.7 10.2 7.5.2 8.5.1 8.5.6 8.6 8.1 4.1 9.3 10.3 8.2.1 9.2 8.2.4 | 8.1 6.1.4 10.1 10.2 10.3 7.5.2 9.3 9.2 | 8.1.4.1 6.1.4 10.1 10.2 10.3 9.3 9.2 |  |  | No
120 | ISO 45001 Stage 2 assessment 2025 | LRQA ISO 45001 Stage 2 assessment | 11.12.24 PL: Newly added following confirmation of new date for Stage 1. SPOC is Sam Parker. 12.5.25 SM: This could entail additional time/auditors tbc. 21.5.25 CT: Dates will remain the same, but the cost will be increased to 17 audit (person) days (due to increase in auditor coveredge based on certain factors such as size of organisation), this will also take into account an 'audit planning day' on the 30th May. Further details to be confirmed after planning day on the 30th May. 11.6.25 CT - Decreased by 1 now, so will be 16 audit days, 1 of which has already been used up for a planning day at the back end of May, 5 days in Head office, 10 days on site (still spread over the same 5 day period). The H&S Policy even though it has been revised, still needs to be approved by the board, and then re-issued to the IMS Team for republishing. 13.8.25 AB/PL: Although end date is showing as 5th August, the outcome will be added in post the 1st September when we are re-inspected on the Major non-conformance that was identified in this inspection to see if it can be removed, reduced to a minor, or if it still stands. 2.9.25 AB: Updated information following feedback from Chris and Peter, the major initially identified in August is now closed, pending technical review before Certification can be formally approved. 2.10.25 AB: Updated Live MNC's to 8, these also include remaining one's from AUD-2028 (Stage 1) that are still open. | R | No | Yes | External Review - LRQA | Line 4 - External | 2025-07-28 | 2025-08-05 | 2025-09-01 | Andrew Wilkinson | Stephen Mason | Audit | Overall Project | ISO 45001 Certification | Health, Safety & Wellbeing | Blue | Amber | Auditor congratulated team on, a well structured action plan with 5 why's and cleared defined root cause, engagement of all parties in this recovery exercise including INA / Legal / Site delivery etc, we now have a well structured legal register which is 'fully' populated, 'I can see this is the end of your recent journey', future audits we will need to revisit this area in detail to ensure the legal register remains current and the actions related to the root cause are progressed, Matt hoped we could appreciate the importance and reasoning behind following the details of the standard. Certification is recommended. | LC17 | N/A | N/A | N/A | N/A | 0 | 0 | 8 | 0 | 5 | 8 | 1 | 0 | 1st September 2025 | 1st September 2025 | 0 | 0 | No or N/A | AUD-3201 | Matt Evans (LRQA) | Peter Long | Steve Mason and Sam Parker | [13 empty] | No
79 | 6.4 - Environmental & Sustainability Management | IMPORTANT NOTE = THERE IS ASSOCAITED HOLD POINT (8th of Sept 2025) SZC-HSE-PRO-002 - Assess Environmental Aspects and Impacts SZC-HSE-PRO-007 - Manage the Environment Case SZC-HSE-PRO-032 - Apply for and Maintain Nuclear and Environmental Consent, Permit or Licence. SZC-HSE-PRO-033 - Control Contaminated Land and Groundwater SZC-HSE-PRO-035 -Develop and Manage Environmental Requirements SZC-HSE-PRO-042- Perform Environmental Monitoring. SZC-ACQ-PRO-029, Manage Environmental Objectives SZC-HSE-STA-001 - Environmental Optimisation Standard. SZC-HSE-STA-002 - Land Quality Management Standard SZC-HSE-STA-022 - Integrated Waste Management Standard Note three other procedures outside the IMS Framework at time of planning that have not been published. | 17.10.24 PL: Commence Construction of the Marine Beach Landing Facility. Hold Point Released to Commence Marine Bulk Import Facility - baseline 9/9/25 however None noted in current IAAP. This milestone is outside of current reporting range, however, it is close enough that it would be expected that some early assurance activies would be recorded. 11.11.24: Combined audit (NCAPI / Env / Security and Conv Safety). Start date pushed to mid-July. Also see activity 97 from Env team on Hold point - Marine Beach landing facility. 26.3.25 VT - Added Faun as observer. 2.4.25 VT - Environment will be involved as auditee's but not a combined audit now. ACG 9APR25 - End date changed 10.04.25 FD: Added Level 2 ID Process Owner(s) name to column AU and added Procedure Lead Name(s) to column AT. Removed SZC-HSE-PRO-047 Column E & Column AZ also removed SZC-HSE-PRO-048, SZC-HSE-PRO-049 & SZC-HSE-PRO-050 from Colmn AZ as no longer on the IMS. 4-JULY-2025 ACG: Dates agreed with Carly Merret and Placeholder establsihed with potential auditiees. Will now run form 29th to 31st of July. Detailed planning still to be establsihed. 16.9.25 VT: Please move SZC-ACQ-PRO-029, Manage Environmental Objectives onto this from 8.2 Assurance, as this should sit within this process. | C | No | Yes | SS&A - Quality Assurance | Line 2 - Corporate Functions | 2025-07-29 | 2025-10-27 | 2025-08-15 | Fran Gradie | Vanessa Tsanang | Audit | SS&A - Marine Environment | N/A - No specific Milestone | Environment | Blue | Green | No NC's raised. Very well run process. | LC6,LC17 | N/A | N/A | 101579183 | N/A | 0 | 8 | 2 | 2 | 0 | 0 | 0 | 0 | N/A | N/A | 0 | 0 | No or N/A | AUD-3443 | Adrian | Faun | N/A | Stuart Woodings | Stuart Woodings | Safety, Security and Assurance | Internal IMS Audit | 6.0 - Health, Safety, Security & Environment | 6.4 - Environmental & Sustainability Management | Apply for and Maintain Nuclear and Environmental Consent, Permit or Licence Assess Environmental Aspects and Impacts Control Contaminated Land and Groundwater Develop and Manage Environmental Requirements Environmental Optimisation Standard Integrated Waste Management Standard Land Quality Management Standard Manage the Environment Case Perform Environmental Monitoring | SZC-HSE-PRO-032 SZC-HSE-PRO-002 SZC-HSE-PRO-033 SZC-HSE-PRO-035 SZC-HSE-STA-001 SZC-HSE-STA-022 SZC-HSE-STA-002 SZC-HSE-PRO-007 SZC-HSE-PRO-042 | N/A | 6.1.3 8.1 6.1.1 6.1.2 6.1.4 8.1 9.1 6.2.1 9.1.1 9.2 | N/A | N/A | N/A | No
17 | Review of the PVPI Compliance - OSI Works 2025 v2 (ONR Focus) | Review of PVPI against the SZC Contractor Standard. Following on from v1 and the earlier review. | 18.10.24 AB - Added to IAAP following consultation with Stephen Mason and Emma Bentley. 2.9.25 EB - Completed on Friday just gone, added commentary, the report will be to follow shortly, maybe some minor reccomendations but the outcome was Green. | A | Yes | Yes | SS&A - Security & Conventional Safety Assurance | Line 2 - Corporate Functions | 2025-08-01 | 2025-08-29 | 2025-08-29 | Andrew Wilkinson | Stephen Mason | Assessment | Delivery - Site Programme | LC & PC - Self-assessment programme assurance report | Health, Safety & Wellbeing | Blue | Green | All PCs on the off-site infrastructure projects were reviewed for their PVPI arrangements and there we no major items of concern raised, just some reccomendations. Due to the nature of their works, they are following the hierarchy of controls and keeping plant within the Red zones with the appropriate measures in place. | N/A | N/A | N/A | 101600911 | 32170 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
96 | Hold Point Preparation Review 2 - Temporary Sea Defence | Temporary sea defence. MCA/FRA/12. | 22/10/24 - Note: Combine with ESG team activities. 06/02/25 BH - HP pushed back to June, so we are pushing out the start date to June (was Jan). 29.5.25 ej: Keep as June for now and will check with Becky. 27.6.25 BH: Was previously starting in June, please move to start of August till end of Sept and we shall revisit. 15.08.25 BH - to be removed Hold points reviews will be undertaken on a risk based approach and be triggered by the environmental hold point manager. | A | No | Yes | SS&A - Environmental Services and Assurance | Line 2 - Corporate Functions | 2025-08-01 | 2025-09-30 |  | Stuart Woodings | Sam Bulmer | Review | Overall Project | Temporary Sea Defence - Hold Point Released to Commence Temporary Sea Defence | Environment | Green | N/C |  | N/A | Flood Risk Activity Environmental Permit | 2.1.6 U1 - Temporary Sea Defence |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | Yes
113 | Environmental Input into Design Packages Self Assessment | Environmental inputs and requirements in design processes | 22/10/24 - Note: Combine with ESG team activities. Environmental input into FCRs, NCRs, Design change committees etc. 15.08.25 BH this item to be removed, the items have been superceeded by a series of meeting to update the change management process there will be no documented output.. | C | No | Yes | SS&A - Environmental Services and Assurance | Line 2 - Corporate Functions | 2025-08-01 | 2025-10-31 |  | Stuart Woodings | Sam Bulmer | Self Assessment | Overall Project | N/A - No specific Milestone | Environment | Green | N/C |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | Yes
107 | IR-53493 | Check on control arrangements for procurement, manufacture and delivery of equipment and manufacturing oversight - (Martin Davies) | 04.02.25 TB: Defferred to a later date, will advise of new date in due course. 27.02.25 JB: ONR are developing their intervention strategy, therefore all forthcoming inspections may well be cancelled or re-purposed. 3.4.25 TB - Please remove, this will no longer be proceeding as ONR are re-considering their future inspection regime. 24.6.25 MA - Maybe 5th/6th August but Angela (ONR) has challenged these dates, so further update expected. | R | Yes | Yes | External Review - ONR | Line 4 - External | 2025-08-05 | 2025-08-06 |  | Fran Gradie | Thomas Brazendale | Inspection | Delivery - Delivery/PDO | N/A - No specific Milestone | Nuclear Safety Risk | N/C | N/C |  | LC 19 | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | Yes
44 | OSI Audit - Buckleswood | Risk based review and audit of OSI site(s). | 22/10/24 - Note: Only Carly and Hannah Auditor Trained. 3.4.25 - Potentially look to review and compare with Security team to see if efforts can be combined so that the audit and questions can be captured in one hit. 28.07.25 EJ - updated to Buckleswood as audit target due to on-going complaints/contractor issues. 14.08.25 BH dates updated to reflected planned and confirmed dates - no change to timeframe so no risk. 04.09.25 EJ - draft audit report sent for review. Final report and actions to be completed on 25.09. | C | No | Yes | SS&A - Environmental Services and Assurance | Line 2 - Corporate Functions | 2025-08-18 | 2025-09-04 | 2025-09-04 | Stuart Woodings | Sam Bulmer | Audit | SS&A - Environmental Services and Assurance | N/A - No specific Milestone | Environment | Blue | Amber | Minor non-conformance - gap in Mobilisation arrangements for OSI sites / sites where SZC not PC. Retrospective Obs where RIO process not being followed for council communications. | N/A | Ordinary Watercourse Consent | N/A | 101589402 | N/A | 0 | 7 | 3 | 7 | 1 | 1 | 0 | 0 |  |  | 0 | 0 | No or N/A | 3553 | Hannah Dixon | Becky Hudson | Ella Jeffrey | Dan Kinsman | Matthew Reed/Marjorie Barnes |  | 2nd Line Quality Assurance | 6.0 - Health, Safety, Security & Environment | 8.2 - Assurance | Manage Enquiries and Complaints, Manage Interface with Regulators, Mobilisation Quality Plan |  | N/A | Yes | N/A | N/A | N/A | No
124 | IR-53495 | On and Off-site record and management systems | 27.02.25 JB: ONR are developing their intervention strategy, therefore all forthcoming inspections may well be cancelled or re-purposed. 3.4.25 TB - Please remove, this will no longer be proceeding as ONR are re-considering their future inspection regime. 24.6.25 MA - May now be w/c 18th August, still awaiting final determination from ONR. | R | Yes | Yes | External Review - ONR | Line 4 - External | 2025-08-18 | 2025-08-22 |  | Fran Gradie | Thomas Brazendale | Inspection | Overall Project | N/A - No specific Milestone | Nuclear Safety Risk | N/C | N/C |  | LC 6, 17 | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | Yes
13 | Environmental Categorisation NCC Quarterly Review Q3 | Ongoing input into environmental impact assessment of design modifications/evolutions | 11.12.24 BH Start and end dates have been pushed back, to start in March rather than Jan. this is due to the environmental categorisation arrangements not being fully established. This will have no effect or risk on other activities. 6.2.25 SW: To check to see if this needs to be in the plan (retained), or simply kept in team functional plan. 05.03.25 BH Changed to a review due to Emma's team doing all design changes. This has been changed to a quarterly metric. Additional lines will be added for Q2/Q3/Q4. dates also changed to coinside with end of Q1, so starting in April now (not March). 25.03.25 BH On track to start April. 02/05/25 BH - Emma Wells stated this will not be started for Q1 due to resources, therefore we've been asked to push back the end date. Was previously shown as starting and ending throughout April. 29.5.25 EJ: Will discuss with Emma and update. 18.06.25 EJ - discussion with EW confirmed this will commence in Q3 due to team resourcing. Q4 item to be added. 17.9.25 EW - Please push planned end date to end of October, I shall catch up with Jon on this when he's back, and adjust BRAG to Amber. 23.9.25 EW: Collaboration with Sam's team. 20/10/25 BH - All TDF, Pre-NCC's and NCC's have had env representation . All DC's at implementation gate have received Environmental Ranking | C | No | No | SS&A - Operational Permits | Line 1 - Corporate Functions | 2025-09-01 | 2025-10-30 | 2025-10-20 | Stuart Woodings | Emma Wells | Review | Overall Project | N/A - No specific Milestone | Achieving Replication | Blue | Green | Please see description Tracker of design changes and FCRs link TBC | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
19 | Assure the Emergency Preparedness & Response Roles and Responsibilities | All staff with roles in the emergency arrangements, either for response or emergency preparedness, will be SQEP, appointed to their role and the competence in their role monitored, this will be reviewed at regular intervals. | 29.11.24 PG: Assurance tool altered to Surveillence (was assessment). 6.3.25 PG: New ways of working being adopted, 5 shift managers to start this year. 3.4.25 PG - end date pushed to March 2026 (previously Dec 25). 3.4.25 - FG: Please can PG speak with Vanessa to see if there can be any support/collaboration with upcoming audit planned on emerg arrangements. 12.5.25 PG: Adverts out now for emergency shift members for us to monitor. 30.5.25 PG: We will do some cooordinated audits to reduce audit fatigue to site, but we still plan to proceed with our one. Formal start date will be beginning of September, earlier one provided (Jan 25), was simply covering some of the prep work. 2.9.25 PG: Kicked off now, works well with emerg training next week. 15.10.25 pg: On pause, whilst focus is on Business Continuity and Crisis Management, so we have pushed out the end date to June next year to align with the proposed Desalination Plant. | C | Yes | Yes | SS&A - Emergency Preparedness | Line 2 - Corporate Functions | 2025-09-01 | 2026-06-01 |  | Andrew Wilkinson | Paul Gomar | Surveillance | Overall Project | Desalination Plant readiness | Health, Safety & Wellbeing | Green | N/C |  | 8, 11 | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
29 | 15.2 - Funding & Investment Case Management | SZC-FIN-PRO-004,Manage SZC Shareholder Funds Transfer. SZC-FIN-PRO-006,Acquire Property Site. SZC-FIN-PRO-007, Establish and Maintain Investment Case. | 18.10.24 ACG - From PAP where procedures are Implemented and Published in IMS. 4.2.25 FG: Defer for now, and refer to Peter Chambers. 17.2.25 VT: On hold till we determine who will support this from a financial perspective. 19.2.25 VT: Having spoken with Finance contact, let's move this to September 2025 for now please, with the same length of time. 10.04.25 FD: Added Level 2 ID Process Owner(s) name to column AU and added Procedure Lead Name(s) to column AT. 22.07.25 CC: Due to the ongoing changes in the Finance / Treasure procedures and the restructuring of the Finance Assurance Audit Strategy, we will consider this audit to be on hold. This was defined on 20/07 together with Peter Chambers, Vanessa Tsanang and Camila Casagrande. I will contact the PO and inform them of the decision and let them know that they will be contacted in due course with further details regarding the audits. | C | No | No | SS&A - Quality Assurance | Line 2 - Corporate Functions | 2025-09-01 | 2025-11-30 |  | Fran Gradie | Vanessa Tsanang | Audit | F&ER | N/A - No specific Milestone | Reputation & Social License | N/C | N/C |  | LC6 LC17 | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  | Vanessa | Camila | Haitong Zhang | Christopher Nunn Andy Wise Andrew Grant | James Weeks | Finance & Investor Relations | Internal IMS Audit | 15.0 - Finance & Accounting | 15.2 - Funding & Investment Case Management | Establish and Maintain Investment Case Manage SZC Shareholder Funds Transfer Dispose of Property Site | SZC-FIN-PRO-007 SZC-FIN-PRO-004 SZC-FIN-PRO-006 | 8.1 8.4.1 |  |  |  |  | Yes
30 | 15.4 - Accounting & Statutory Financial Reporting | SZC-FIN-PRO-010, Prepare and Submit Financial Accruals. SZC-FIN-PRO-012, Produce Financial Performance Reports Note1 - One other procedure is not Published in IMS at time of planning 31.10.2024. Note2 - there is one other procedure that is outside the IMS Framework that may need to be considered. | 18.10.24 ACG - From PAP where procedures are Implemented and Published in IMS. 4.2.25 FG: Defer for now, and refer to Peter Chambers. 17.2.25 VT: On hold till we determine who will support this from a financial perspective. 19.2.25 VT: Having spoken with Finance contact, let's move this to September 2025 for now please, with the same length of time. 26.3.25 VT - Added Oliver Bournat as Auditee, still awaiting SME details, will speak to Peter Chambers. 10.04.25 FD: Added Level 2 ID Process Owner(s) name to column AU and added Procedure Lead Name(s) to column AT. Removed SZC-FIN-PRO-011 & SZC-FIN-PRO-001 from Column AZ as not on IMS 22.07.25 CC: Due to the ongoing changes in the Finance / Treasure procedures and the restructuring of the Finance Assurance Audit Strategy, we will consider this audit to be on hold. This was defined on 20/07 together with Peter Chambers, Vanessa Tsanang and Camila Casagrande. | C | No | No | SS&A - Quality Assurance | Line 2 - Corporate Functions | 2025-09-01 | 2025-11-30 |  | Fran Gradie | Vanessa Tsanang | Audit | Finance | N/A - No specific Milestone | Reputation & Social License | N/C | N/C |  | LC6 LC17 | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  | Vanessa | Camila | Haitong Zhang | James Weeks | James Weeks | Finance & Investor Relations | Internal IMS Audit | 15.0 - Finance & Accounting | 15.4 - Accounting & Statutory Financial Reporting | Prepare and Submit Financial Accruals Produce Financial Performance Reports | SZC-FIN-PRO-010 SZC-FIN-PRO-012 | 8.1 |  |  |  |  | Yes
37 | Permit Readiness Review - CWDA | Readiness review for incoming permits - CWDA Permit. MDS/CWDA/18. | 06.02.25 SW - Permit is going to be granted in June, but we have sought an LEP to allow for permit activities earlier than June. 1st activities under LEP, should start beginning of May now (was Jan), so push back. Discharge from dewatering of 1st part of SSSI work. No impact to other work. 26.06.25 BH - on track, documentation started. 31.07.25 EJ - confirmed with RG that deadline to be extended to end of Aug. No additional risk from deadline extension. 01/09 EJ - RG requested extension to mid-September. 23.9.25 - Move end date to end of October as just a little more time needed. 16.10.25 BH: Addressing omments and then this can be closed out. | B | No | Yes | SS&A - Environmental Services and Assurance | Line 2 - Corporate Functions | 2025-09-01 | 2025-10-30 |  | Stuart Woodings | Sam Bulmer | Review | SS&A - Environmental Services and Assurance | EA Inspection - Construction Water Discharge Activity (CWDA) Permit | Environment | Green | N/C |  | N/A | Construction Water Discharge Activity Permit | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
89 | MMO Pre-regulatory readiness review 2 | Pre-regulatory (MMO) reviews - to support known MMO audit on site in relation to a marine licence(s). Technical specialism focused | 27.11.24: SM - Start date has now moved to -, however this will be driven by the MMO Inspection programme, this date movement presents no material risk. 5.9.25: SM - Please remove this one for now, as programme is moving to the Right. | C | No | Yes | SS&A - Marine Team | Line 2 - Corporate Functions | 2025-09-01 | 2025-09-29 |  | Stuart Woodings | Stephen Roast | Review | SS&A - Environmental Services and Assurance | N/A - No specific Milestone | Environment | N/C | N/C |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | Yes
95 | Hold Point Preparation Review 1 - Cut Off Wall | Cut off wall - November 2025. MCA/GIC/7, MCA/WP0/5. | 22/10/24 - Note: Combine with ESG team activities. 14/08/25 remove hold point review. As mentioned hold point reviews will become reactive. | A | No | Yes | SS&A - Environmental Services and Assurance | Line 2 - Corporate Functions | 2025-09-01 | 2025-10-31 |  | Stuart Woodings | Sam Bulmer | Review | Overall Project | Cut-Off ("Diaphragm") Wall - Hold Point Released to Commence CoW | Environment | N/C | N/C |  | N/A | MCA/GIC/7 MCA/WP0/5 | 1.1.4 U1 - Commencement of excavation for the cut-off wall |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | Yes
99 | Risk based surveillance of FCR/NCR completion Q3/Q4 | Surveillance of previous 6 months FCRs will either be risk based on percentage check | 2.5.25 BH: Was previously scheduled to start in July, pushed back to Sept, as previous Q1/Q2 one has moved to the Right. 14/08/2025 BH remove this item. Environmenttal assurance team is categorising all FCRs. An item to be added to next years plan, once assurance team not soley undertaking categorisation | C | No | Yes | SS&A - Environmental Services and Assurance | Line 2 - Corporate Functions | 2025-09-01 | 2026-01-15 |  | Stuart Woodings | Sam Bulmer | Surveillance | SS&A - Environmental Services and Assurance | N/A - No specific Milestone | Environment | N/C | N/C |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | Yes
259 | Assuarance of L2 Investigation action close out | This is a review of all actions raised as a result of L2 investigations to ensure actions have been closed out effectively and with sufficient evidence. | 21.10.25 CE: Added new line for 2025/2026. | C | No | No | SS&A - Performance Improvement | Line 2 - Corporate Functions | 2025-09-03 | 2025-11-14 |  | Fran Gradie | Hilary Best | Review | Overall Project | N/A - No specific Milestone | Quality | Green | N/C |  | LC 7 | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
117 | IR-53500 | Inspection of the Engineered Fill Trials - (David Mugliston) | 04.02.25 TB: Defferred to a later date, will advise of new date in due course. 27.02.25 JB: ONR are developing their intervention strategy, therefore all forthcoming inspections may well be cancelled or re-purposed. 3.4.25 TB - Please remove, this will no longer be proceeding as ONR are re-considering their future inspection regime. 24.6.25 MA - May now be proceeding again in September. ONR to advise in due course. | R | Yes | Yes | External Review - ONR | Line 4 - External | 2025-09-08 | 2025-09-09 |  | Fran Gradie | Thomas Brazendale | Inspection | Delivery - Civils Programme | N/A - No specific Milestone | Nuclear Safety Risk | N/C | N/C |  | LC 14, 19 | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | Yes
126 | IR-53499 | The readiness for delivery of the Civil Works programme - (David Mugliston) | 10.02.25 JB - previously cancelled but moved to 25/26 ONR inspection plan and re-opened. 27.02.25 JB: ONR are developing their intervention strategy, therefore all forthcoming inspections may well be cancelled or re-purposed. 3.4.25 TB - Please remove, this will no longer be proceeding as ONR are re-considering their future inspection regime. 24.6.25 MA - May now be proceeding in September, ONR to confirm in due course. | R | Yes | Yes | External Review - ONR | Line 4 - External | 2025-09-15 | 2025-09-16 |  | Fran Gradie | Thomas Brazendale | Inspection | Delivery - Civils Programme | N/A - No specific Milestone | Nuclear Safety Risk | N/C | N/C |  | LC 19, (CDM 15) | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | Yes
249 | Pre-Audit for ISO 14001 Recertification - Dalkia Orwell | Audit undertaken in preperation for the recertification of ISO14001 - December | 29.09.25 BH new Item. BH Item completed on 19th September, actions in insight | B | No | Yes | SS&A - Environmental Services and Assurance | Line 2 - Corporate Functions | 2025-09-17 | 2025-09-19 | 2025-09-19 | Stuart Woodings | Sam Bulmer | Inspection | Overall Project | ISO 14001: Recertification Audit Complete | Environment | Blue | Amber | 8 actions, update waste management plan, spill response training and resources to be confirmed, actions relating to confirming documents are help | N/A | N/A | N/A | TBC | 32141 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
222 | IR-54143 | Inspection on risk of foreclosure - Risk of foreclosure Inspection | 22.7.25 tb - new item added. 02.9.25 JB - Updated. 4.9.25 JB - TD Have advised they want this pushed back to October now, still awaiting feedback on the actual date. | R | Yes | No | External Review - ONR | Line 4 - External | 2025-09-29 | 2025-09-30 | 2025-09-30 | Fran Gradie | Thomas Brazendale | Inspection | Technical | N/A - No specific Milestone | Nuclear Safety Risk | Blue | Green | Green overall rating ONR seemed happy with documentation provided and inspection, report to follow. | LC 19, 17, 6 | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
228 | EA Compliance Inspection Permit/Licence: 7/35/03/*S/0047 (Northern Abstraction) | Confirm compliance with the requirements of the permit. | 2.9.25 JB - New item added. 2.10.25 SB - Hot feedback added from Inspection (Sam bulmer), report to follow. | R | Yes | Yes | External Review - EA | Line 4 - External | 2025-09-30 | 2025-09-30 | 2025-09-30 | Fran Gradie | Thomas Brazendale | Inspection | SS&A - Environmental Services and Assurance | N/A - No specific Milestone | Environment | Blue | Green | No compliance issues identified, measures implemented following the previous inspections were praised. Full report to follow. | N/A | Water Resources Abstraction Licence - for the abstraction of water during construction | N/A | TBC |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
229 | EA Compliance Inspection Permit/Licence: 7/35/03/*S/0075 (Southern Abstraction) | Confirm compliance with the requirements of the permit. | 2.9.25 JB - New item added. 2.10.25 SB - Hot feedback added from Inspection (Sam bulmer), report to follow. | R | Yes | Yes | External Review - EA | Line 4 - External | 2025-09-30 | 2025-09-30 | 2025-09-30 | Fran Gradie | Thomas Brazendale | Inspection | SS&A - Environmental Services and Assurance | N/A - No specific Milestone | Environment | Blue | Green | No compliance issues identified, measures implemented following the previous inspections were praised. Full report to follow. | N/A | Water Resources Abstraction Licence - for the abstraction of water during construction | N/A | TBC |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
32 | Self assessment of permit handover process | Effectiveness review of the permit handover process to ensure robustness. | 29.11.24 CP: Newly added today. 2.5.25: BH - Chasing up CP. 26.06.25 - BH - CP has not started self assessment, meeting to be held 27.06.25 to discuss (CO,SW, BH, EJ). 27.6.25 BH: Was down for May to July, will now be Aug - September following consultation and meeting, no risk. 16.10.25 BH: This started a little late at start of October, should be finished by end of November but no risk. | C | Yes | No | SS&A - Construction Permitting | Line 1 - Corporate Functions | 2025-10-01 | 2025-11-30 |  | Stuart Woodings | Clare Proctor | Self Assessment | SS&A - Construction Permitting | N/A - No specific Milestone | Environment | Green | N/C |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
34 | SSSI Protection Audit - (Bridge Crossing) | Bi-annual audit for the protection of the SSSI. | 22/10/24 - Note: Only Carly and Hannah Auditor Trained. 06/02/25 SB - Still waiting to mobilise, therefore date pushed back to start of March. 6.3.25 BH - Date pushed back again as still waiting to mobilise (was March now start of April). 15.08.25 BH - 3rd party auditor to undertake udit. Likely to be mid september. 3.4.25 - Check with Andrew (Sam) to see what needs to be tied in from a security perspective. 2.5.25 - BH: Prep work has commenced. 29.5.25 SB: Date is pushed forward a little and will now finish in December (was previously September), no overall impact; have removed Q1/Q2 from title. 26.06.25 -BH/EJ to confirm start date of works, not yet started (ws previously down for 1st May, new date tbc). 23.9.25 BH: Please push back to 1st October to start. 16.10.25 BH: Started now, turn to Green. | C | No | Yes | SS&A - Environmental Services and Assurance | Line 2 - Corporate Functions | 2025-10-01 | 2025-11-30 |  | Stuart Woodings | Sam Bulmer | Audit | Delivery - Site Programme | EEW31 - Bailey Bridge Open for Use | Environment | Green | N/C |  | N/A | Flood Risk Activity Environmental Permit | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
70 | CRWA Arrangements Review | Periodic review of Coprorate Radioactive Waste Advisor Arrangements | 06.03.25 BH - changed from a SA to a review. This is a more appropriate tool for the assurance item. 16.10.25 BH: Checking with Emma, this may have already been done, will update in due course. 20.10.25 BH - Comopletd. TC number to be confirmed then can close out | C | No | No | SS&A - Operational Permits | Line 1 - Corporate Functions | 2025-10-01 | 2025-12-31 |  | Stuart Woodings | Emma Wells | Review | SS&A - Operational Permits | N/A - No specific Milestone | Environment | N/C | N/C |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
85 | Review of SZC PD arrangements for managing the project in the pre-construction phase (Review of Principal Designer Execution Strategy / ONR Focus topic) | How the SZC PD will discharge their duties under CDM. | 18.10.24 AB - Added to IAAP following consultation with Stephen Mason and Emma Bentley. 11.11.24 AB: Stephen Mason says this requires Auditor support, to discuss with Fran. 6.3.25 AB: Mike Hind is working on this. 3.4.25 sm - needs to be pushed back (was originally June / pushed to August) as part of Tilly's organisation so need to discuss with Mike. 12.5.25 SM: Still awaiting PD Execution plans, so we shall proceed with PD Execution Strategy so as we don't delay the rest of the excercise. Will be 2 parts. 27.6.25 SM: Strategy has only just been issued, there are sessions ongoing with people, and INA are doing sessions till end of July, until people are briefed we've agreed with Tilly to push this back till a date still to be confirmed (previously August). 13.10.25 FG: Please align with Stuart's team. | A | Yes | No | SS&A - Security & Conventional Safety Assurance | Line 2 - Corporate Functions | 2025-10-01 | 2025-11-30 |  | Andrew Wilkinson | Stephen Mason | Assessment | Delivery - Site Programme | N/A - No specific Milestone | Health, Safety & Wellbeing | Green | N/C |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
101 | Self-assessment review of emergency arrangements - 2025 / LC 11 | 2LOD Annual review of site delivery Self Assessment of LC11 Emergency Arrangements | 29.11.24 PG: Error on start year for this activity, has now been corrected to Oct 2025 (was 2024), one already done at start of 2024, the 2024 one only had some minor outcomes (no showstoppers), so Green. 15.07.25 PG LC08 Self Assessment removed from her as it's a Q3 action. New line added activity ID 159 | C | Yes | Yes | SS&A - Emergency Preparedness | Line 2 - Corporate Functions | 2025-10-01 | 2025-12-31 |  | Andrew Wilkinson | Paul Gomar | Review | Delivery - Site Programme | N/A - No specific Milestone | Health, Safety & Wellbeing | N/C | N/C |  | 8, 11 | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
112 | Review of Site HSE Inspection Procedure | Audit of inspection procedure SZC-HSE-PRO-021 Combined audit with ESG team activities and Andrew Wilkinson's team (Security and Conventional Safety Assurance). | 22/10/24 - Note: Combine with ESG team activities 11/11/24 - May need to work with Andrew Wilkinson on this particular activity. 27/01/25 (EJ) - delayed start due to procedure still being in review. Updates not yet implemented. 16.10.25 BH: Has been written, just awaiting IRP endorsement, will update once complete (have changed from Audit to Review). 20.10.25 BH - whole new procedure written for environmental inspections - currently to go to IRP - planned Thursday 2oth November 2025. HSE inspection procedure to be retired. This has been confirmed by Steve Mason and Sam Parker and Emma Bentley agreed thes HSE procedure to be retired. This will be formally agreed in the IRP | C | No | Yes | SS&A - Environmental Services and Assurance | Line 2 - Corporate Functions | 2025-10-01 | 2025-12-31 |  | Stuart Woodings | Sam Bulmer | Review | SS&A - Environmental Services and Assurance | N/A - No specific Milestone | Environment | Green | N/C |  | N/A | N/A | N/A | TBC | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
227 | Dip test of the Quality of the close out of actions 2025 | Check of quality of close-out of actions from learning reports. | 14.8.25 HB: New item added. | C | No | No | SS&A - Performance Improvement | Line 2 - Corporate Functions | 2025-10-01 | 2025-11-30 |  | Fran Gradie | Hilary Best | Review | Overall Project | N/A - No specific Milestone | Quality | Green | N/C |  | LC 7 | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
235 | EA Compliance Inspection: EPF Register | Inspection of arrangements for identification and procurement of equipment with an environmental protection function (EPF). Includes how learning from HPC on procurement, construction, and commissioning requirements for KEPE is captured and replicated for Sizewell C. (Inspection to be combined with EA HPC inspection of EPF) | 2.9.25 JB - New item added. 2.10.25 JH - Jon Hatton is contact, confirmed he shall advise on hot feedback shortly. | R | Yes | Yes | External Review - EA | Line 4 - External | 2025-10-01 | 2025-10-02 | 2025-10-02 | Fran Gradie | Thomas Brazendale | Inspection | SS&A - Environmental Services and Assurance | N/A - No specific Milestone | Environment | Blue | Green | EA Considers the EPF register is performing its required function and is being suitably maintained. A minor action was raised for SZC to update it's work instruction. Full report to follow. | N/A | N/A | N/A | TBC |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
248 | Review of Closed Environmental Insight Actions | An assurance review of closed environmental Insight actions to determine whether they have been closed out appropriately (evidence/SME check etc.). This relates to an existing Insight action and minor non-conformance from the June 2025 ISO 14001 audit. | 04/09 EJ - new item added, discussed with Carly Merrett. 16.10.25 BH Following assurance workshop this item is to be combined with Vanessa's team. Suggest delaying start date and making arrangements at suitable time. Will need to confirm with Carly Merritt if this needs to be done before the ISO14001 audit. 16.10.25 BH: We will consider this when it comes about next time and link in with Hilary and Vanessa's teams, however, as this has already commenced and is due to conclude in October, in this instance, we will simply keep Vanessa and Hilary informed. Line 1 environment to review own actions, Line 2 Environmental to review own actions, Quality to also review own actions - this being undertaken by Faun as well as Line 1 environment. Molly is undertaking the Line 2 requirements - these are mostly inspection actions. Hilary/ Donna Sanderson from org learning also undertaking action effectiveness on investigation actions. Donna/Faun/Molly to collaborate and Carly managing fortnightly catch ups, all collaborating on same spresadsheet. Action reference 73345 - closure date 28th November, also extented on this tracker to match insight action, this was due to the action being delegated to others. | B | No | No | SS&A - Environmental Services and Assurance | Line 2 - Corporate Functions | 2025-10-01 | 2025-11-28 |  | Stuart Woodings | Sam Bulmer | Review | SS&A - Environmental Services and Assurance | N/A - No specific Milestone | Environment | Green | N/C |  | LC 7 | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
65 | 14.5 - IT Support Management & Operations | SZC-ITS-PRO-001, Control Access to Information Systems and Assets SZC-ITS-PRO-003, Enable Capacity & Provisioning Management SZC-ITS-PRO-012,Manage IT Service Continuity SZC-ITS-PRO-013, Manage IT Service Transition SZC-ITS-PRO-018, Monitor and Evaluate IT Service Performance SZC-ITS-PRO-019, Perform Event Management SZC-ITS-PRO-020, Perform Incident Management SZC-ITS-PRO-021, Perform Problem Management SZC-ITS-PRO-022,Service Catalogue Management SZC-ITS-PRO-023, Service Request Management | 10.04.25 FD: Added Level 2 ID Process Owner(s) name to column AU and added Procedure Lead Name(s) to column AT 06.5.25 CC - email sent to Nick Harvey to align details and scope of the audit; a meeting is booked to align audit feasibility and dates. 11.6.25 VT - Due to current demands on the team, it's likely to move to Beginning of October now (Was July), still tbc. 11.6.25 CC - audit scope defined with Nick / to be performed considering 5 procedures: SZC-ITS-PRO-001, Control Access to Information Systems and Assets; SZC-ITS-PRO-012,Manage IT Service Continuity (both procedures are considered High Risk) + SZC-ITS-PRO-019, Perform Event Management; SZC-ITS-PRO-020, Perform Incident Management and SZC-ITS-PRO-021, Perform Problem Management. Audit date agreed to start on october /. Contact point defined by Nick: Wai Lam. As a audit period was agreeded with the PO, the BRAG status was changed from Red to Amber. 03.09.25 CC: Awaiting answer from Nicky Harvey and Way Lam related the audit date. 30.09.25 CC: Awaiting Wai Lam feedback/agreement related the internal audit date. 7.10.25 CC: Still chasing the auditee on confirmation of the audit, keep Amber. 09.10.25 CC: Audit date agrreded with Wai Lam (27 to 31/10/25)- Audit alignment meeting booked to 17.10. BRAG status was changed from Amber to Green. | C | No | No | SS&A - Quality Assurance | Line 2 - Corporate Functions | 2025-10-06 | 2025-12-30 |  | Fran Gradie | Vanessa Tsanang | Audit | Delivery - Delivery/PDO | N/A - No specific Milestone | Cyber security | Green | N/C |  | LC6 & LC17 | N/A | N/A |  | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  | Camila | Vanessa | N/A | Wai Lam | Wai Lam | Digital | Internal IMS Audit | 14.0 - Information Technology & Services | 14.5 - IT Support Management & Operations | Control Access to Information Systems and Assets Enable Capacity & Provisioning Management Manage IT Service Continuity Manage IT Service Transition Monitor and Evaluate IT Service Performance Perform Event Management Perform Incident Management Perform Problem Management Service Catalogue Management Service Request Management | SZC-ITS-PRO-001 SZC-ITS-PRO-003 SZC-ITS-PRO-012 SZC-ITS-PRO-013 SZC-ITS-PRO-018 SZC-ITS-PRO-019 SZC-ITS-PRO-020 SZC-ITS-PRO-021 SZC-ITS-PRO-022 SZC-ITS-PRO-023 | 7.1.3 9.1.1 8.7 10.2 |  |  |  |  | No
125 | 6.3 - Security | SZC-HSE-PRO-008,Manage Visitors SZC-HSE-PRO-009,Control Access of People To Sites SZC-HSE-PRO-026, Manage Security Event SZC-HSE-PRO-045, Manage Personal Overseas Travel Security SZC-HSE-STA-017, Cyber Security and Information Assurance Standard SZC-HSE-STA-018, Visitor Management Standard SZC-HSE-STA-019, Physical Security Standard - Construction SZC-HSE-STA-021, Personnel Security Standard Note ONE other procedure and ONE standard not Published in IMS at time of planning 31/10/2024 | 18.10.24 ACG - From PAP where procedures are Implemented and Published in IMS. 3.4.25 AW: Vanessa please can you check with me (Andrew Wilkinson), as we may need to push this audit out due to current constraints with Cyber team. And to discuss which procedures should still be sat with Andrew's team. 10.04.25 FD: Added Level 2 ID Process Owner(s) name to column AU and added Procedure Lead Name(s) to column AT. Removed SZC-HSE-PRO-016 from Column E & Column AZ also SZC-HSE-PRO-010 and SZC-HSE-STA-020 from Column AZ as not on the IMS 1.5.25 FG: This audit is still tbd, so please remove for now. 11.6.25 VT - This still needs to be rescheduled, due to LRQA audit in December on ISO27001, this may have an impact on that audit. 02.7.25 FD: BRAG updated to Amber as meeting had with Lead Auditee and agreed audit will go ahead in Aug/Sep, waiting lead auditor confirmation of availability . 09.7.25 VT: Move from 1st July to Mid August start date, conversations ongoing with James Costello. 14.07.25 FD: Moved strart date from 20/08 to agreed start date of 26/08. 11.08.25 FD: Changed BRAG to green as audit back on track and dates agreed. 13.08.25 FD: Chaged BRAG to amber as following issue of plan AW does not feel team are in position to conduct audit at end of Aug and suggest we work together to plan this for later in year. 15.08.25 FD: Following meeting with AW this audit has been postponed until October. Planned start date moved from 26/08 to 26/10 & L2 Process Owner updated from Alvin S to Andrew W following confirmation from Andrew that he will now be Process Owner. I will follow up in September to reassess and confirm whether October remains viable. 10.09.25 FD: Meeting held with JC. Auditees are identified for each procedure / standard session. To accommodate multiple participants and busy schedules, the audit will span two weeks from 13th to 24th October 2025. Email sent to all auditees to obtain preferred dates, times & locations for each session to facilitate session coordination. Deadline for responses provided of 24/09, following this I will book sessions and reissue the plan to reflect this. 22.09.25 FD: Procedure SZC-HSE-PRO-045, Manage Personal Overseas Travel Security has been removed from the scop of this audit as Brian S has confirmed it is currently under review and is likely to undergo significant changes. 29.09.25 FD: Audit plan has now been approved and issued. The audit is scheduled to begin on 13th October 2025 and conclude on 22nd October 2025, with several pre-audit sessions taking place this week. | C | Yes | Yes | SS&A - Quality Assurance | Line 2 - Corporate Functions | 2025-10-13 | 2026-04-11 |  | Fran Gradie | Vanessa Tsanang | Audit | SS&A - Security & Conventional Safety Assurance | N/A - No specific Milestone | Health, Safety & Wellbeing | Amber | N/C |  | LC6, LC12 & LC17 | N/A | N/A |  | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A | AUD-3500 | Faun | Peter Long | N/A | Tim Newton Andrew Wilkinson | Andrew Wilkinson | Safety, Security and Assurance | Internal IMS Audit | 6.0 - Health, Safety, Security & Environment | 6.3 - Physical Security | Control Access of People To Sites Control Site Vehicles Cyber Security and Information Assurance Standard Instrumentation and Control Security Standard Manage Personal Overseas Travel Security Manage Security Event Manage Visitors Personnel Security Standard Physical Security Standard - Construction Visitor Management Standard | SZC-HSE-PRO-009 SZC-HSE-STA-017 SZC-HSE-PRO-045 SZC-HSE-PRO-026 SZC-HSE-PRO-008 SZC-HSE-STA-021 SZC-HSE-STA-019 SZC-HSE-STA-018 | 7.5.3 7.2 | 8.1 | 8.1.1 |  |  | No
50 | Manage Regulatory Commitments | SZC-ACQ-PRO-017, Manage Regulatory Commitment | 18.10.24 ACG - From PAP where procedures are Implemented and Published in IMS 10.04.25 FD: Added Level 2 ID Process Owner(s) name to column AU and added Procedure Lead Name(s) to column AT. 16.9.25 VT: Please move SZC-ACQ-PRO-029, Manage Environmental Objectives to 6.4, as we have agreed following on from the 6.4 Audit that this Procedure should sit within that Process. Please also remove Pete Bryant's name from Procedure/Process owner box. 29.9.2025 ACG; Changed to just one procedure. Task (C126) and Description (D126) changed accordingly. Dates also changed to reflect just one procedure. | C | No | No | SS&A - Quality Assurance | Line 2 - Corporate Functions | 2025-10-15 | 2025-11-17 |  | Fran Gradie | Vanessa Tsanang | Audit | SS&A - Quality Assurance | N/A - No specific Milestone | Quality | N/C | N/C |  | LC6 LC17 | N/A | N/A |  | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A | AUD-3773 | Adrian | N/A | N/A | Simon Barnard Fran Gradie | Fran Gradie | Safety, Security and Assurance | Internal IMS Audit | 8.0 - Assurance, Compliance & Quality | 8.2 - Assurance | Manage Regulatory Commitments | SZC-ACQ-PRO-017 | 9.1.1 7.5.2 6.2.1 6.2.2 8.2.3 | 9.1.1 7.5.2 6.1.4 7.4.1 | 9.1.1 7.5.2 6.1.4 7.4.1 |  |  | No
223 | Audit - training audit group 1 | Audit to be conducted following the latest round of audit training for SS&A function | 08.08.25 BH New item. Freedom compound - Upper Abbey Farm, Permitting and other legal compliance arrangements (including ecology, waste management, statutory record-keeping); Training and Suitably Qualified & Experienced Personnel (SQEP) maintenance; emergency planning and arrangements 14.08.25 - audit postponed, training audit so no risk. New date to be rearranged - change to iso14001. Change to early november (was August). 23.9.25 - BH: Bring forward to start mid-October. 16.10.25 BH: Work ongoing to reestablish with support from Russel, as previous contract resource is no longer available. Remove temporarily, and we shall reactivate once we have re-aligned dates. ON-HOLD. | C | No | Yes | SS&A - Environmental Services and Assurance | Line 2 - Corporate Functions | 2025-10-15 | 2025-11-22 |  | Stuart Woodings | Sam Bulmer | Audit | SS&A - Environmental Services and Assurance | N/A - No specific Milestone | Environment | N/C | N/C |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | Yes
230 | EA Compliance Inspection Permit/Licence: EPR/GP3226SQ (IED) | Confirm compliance with the requirements of the permit. | 2.9.25 JB - New item added. | R | Yes | Yes | External Review - EA | Line 4 - External | 2025-10-16 | 2025-10-16 |  | Fran Gradie | Thomas Brazendale | Inspection | SS&A - Environmental Services and Assurance | N/A - No specific Milestone | Environment | N/C | N/C |  | N/A | Combustion Activity Permit | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
38 | 9.7 - Project Reporting & Communications | SZC-PMC-PRO-009, Manage Enquiries and Complaints SZC-PMC-PRO-016, Manage and Provide Project Reporting | 18.10.24 ACG - From PAP where procedures are Implemented and Published in IMS 10.04.25 FD: Added Level 2 ID Process Owner(s) name to column AU and added Procedure Lead Name(s) to column AT. 03.09.25 CC: As the Manage Enquiries and Complaints Procedure was covered in the audit AUD 3553 (among other procedures) conducted by the Environmental Team, this procedure will not be part of the scope of this audit. The AUD-3553 covered how the enquiries and complaints are logged on the tractivity system, and how this topics are managed (2 OFI were raised related this procedure). Improvements related to the exchange of information are also under implementation by the READ Team. Awaiting response from Tommy Clarke related the audit "Manage and Provide Project Reporting". No agreement to this moment. 29.09.25: CC: Audit period agreeded with Tommy Clarke and Team (Davina Mac and Nisu Rahman-Gregori) - audit to be performed between 20 to 24 of october. Notification letter sent and audit alignment planned to 06.10 13.10.25: CC - Following alignment within Vanessa Tsanang and auditees, we are not proceeding with the audit at this time. The procedure in question is still in draft form and undergoing significant changes. Given this, it will likely be a strong candidate for a future audit once the process has matured and stabilized. Gaps verified on the draft and current published procedures will be sent to Davina Mac, to support in the procedure review. Aditional support will be provided if requested / needed. | C | No | No | SS&A - Quality Assurance | Line 2 - Corporate Functions | 2025-10-20 | 2026-01-18 |  | Fran Gradie | Vanessa Tsanang | Audit | Delivery - Delivery/PDO | N/A - No specific Milestone | Productivity | N/C | N/C |  | LC6 & LC17 | N/A | N/A |  | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  | Camila | N/A | N/A | Tommy Clarke Marjorie Barnes | Tommy Clarke | PMO | Internal IMS Audit | 9.0 - Project Management & Controls | 9.7 - Project Reporting & Communications | Manage and Provide Project Reporting Manage Enquiries and Complaints | SZC-PMC-PRO-016 SZC-PMC-PRO-009 | 9.1.1 8.2.1 10.2 | 9.1.1 7.4.1 10.2 | 9.1.1 7.4.1 10.2 |  |  | Yes
258 | SQEP review of SME input into procurement packages for ISO14001 recertification audit | This is a review to undertake a review of completed procurement packages to assess the SME input an scoring for selected packages identified for ISO14001 recetification |  | C | No | No | SS&A - Environmental Services and Assurance | Line 2 - Corporate Functions | 2025-10-22 | 2025-11-21 |  | Stuart Woodings | Sam Bulmer | Review | Overall Project | N/A - No specific Milestone | Environment | N/C | N/C |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
236 | IR-54145 | Site incidents, reporting, recording and investigations | 02.09.25 JB - New item added. | R | Yes | Yes | External Review - ONR | Line 4 - External | 2025-10-29 | 2025-10-30 |  | Fran Gradie | Thomas Brazendale | Inspection | Delivery - Site Programme | N/A - No specific Milestone | Health, Safety & Wellbeing | N/C | N/C |  | LC 7 | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
52 | 8.4 - Continuous Improvement | SZC-ACQ-PRO-010, Enable Continuous Improvement SZC-ACQ-PRO-011, Investigate Incidents SZC-ACQ-PRO-021, Perform Self Assessment SZC-ACQ-PRO-024, Business Architecture Project Delivery SZC-ACQ-PRO-025, Manage Business Architecture Project Pipeline SZC-ACQ-PRO-026, Provide Business Architecture Project Governance Note ONE other procedure not Published in IMS at time of planning | 18.10.24 ACG - From PAP where procedures are Implemented and Published in IMS 10.04.25 FD: Added Level 2 ID Process Owner(s) name to column AU and added Procedure Lead Name(s) to column AT. 02/09.25: CC - The " Enable Continuous Improvement" and "Investigate Incidents" are under review (linked with IT projects); it was agreeded with Hilary to move the audit for both procedures to 2026 (maybe november 2026 - check due to IT projects timeline); The Perform Self Assessment Procedure is also under changes, and the gaps are identified and being adressed. This audit will focus on the 3 IT Procedures that belongs to this process. Audit date to be agreeded with Nick Harvey and Team. Note: Email sent to Nick on 03/09/25 29.09.25 CC: Ben Rowland assigned as main point of contact by Kate Brady. Audit agreeded with auditees / Planned to week 17 to 21 of november/25. Notification letter sent to the auditee. | C | No | Yes | SS&A - Quality Assurance | Line 2 - Corporate Functions | 2025-11-01 | 2026-03-01 |  | Fran Gradie | Vanessa Tsanang | Audit | SS&A - Performance Improvement | N/A - No specific Milestone | Quality | N/C | N/C |  | LC6 & LC17 | N/A | N/A |  | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  | Camila | N/A | N/A | Ben Rowland Fran Gradie | Fran Gradie | Safety, Security and Assurance | Internal IMS Audit | 8.0 - Assurance, Compliance & Quality | 8.4 - Continuous Improvement | Business Architecture Project Delivery Manage Business Architecture Project Pipeline Provide Business Architecture Project Governance Enable Continuous ImprovementInvestigate Incidents Perform Self AssessmentDeliver and Deploy Business Architecture Project | SZC-ACQ-PRO-024 SZC-ACQ-PRO-025 SZC-ACQ-PRO-026 SZC-ACQ-PRO-010 SZC-ACQ-PRO-011 SZC-ACQ-PRO-021 | 4.1 7.1.6 8.1 10.1 6.1 9.1.3 10.2 10.3 8.3.4.1 | 4.1 7.5.3 10.1 6.1.4 10.1 10.2 10.3 9.1.1 | 4.1 7.5.3 10.1 6.1.4 10.1 10.2 10.3 9.1.1 |  |  | No
224 | Dalkia ACA Audit training audit group 2) | Audit to be conducted following the latest round of audit training for SS&A function | 08.08.25 BH New item Dalkia ACA - Maintenance activities: - waste management - hazardous materials management - waste water (trade effluent) - explore drainage arrangements and waste/ haz materials storage arrangements). - F-Gas management). - Emergency planning & response - incl incdent reporting via INSIGHT. - Training & Awareness, SQEP maintenance etc. reporting into sustainability tool 23.9.25 BH - Push this back to November, further details to follow. 23.9.25 BH/SB - Still chasing site for starting this please push start date back 16.10.25 BH: Work ongoing to reestablish with support from Russel, as previous contract resource is no longer available. Remove temporarily, and we shall reactivate once we have re-aligned dates. ON-HOLD. | C | No | Yes | SS&A - Environmental Services and Assurance | Line 2 - Corporate Functions | 2025-11-01 | 2025-11-30 |  | Stuart Woodings | Sam Bulmer | Audit |  | N/A - No specific Milestone | Environment | N/C | N/C |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | Yes
225 | Audit training audit group 3 | Audit to be conducted following the latest round of audit training for SS&A function | 08.08.25 BH New item - subject and location to be confirmed. Potentially Yoxford Combine with line 45 23.9.25 - BH: Push back to November now. 16.10.25 BH: Work ongoing to reestablish with support from Russel, as previous contract resource is no longer available. Remove temporarily, and we shall reactivate once we have re-aligned dates. ON-HOLD. | C | No | Yes | SS&A - Environmental Services and Assurance | Line 2 - Corporate Functions | 2025-11-01 | 2025-11-10 |  | Stuart Woodings | Sam Bulmer | Audit |  | N/A - No specific Milestone | Environment | N/C | N/C |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | Yes
45 | OSI Audit - TBC | Risk based review and audit of OSI site(s). | 22/10/24 - Note: Only Carly and Hannah Auditor Trained. 14.08.25 BH Start date updated as other audits have shifted due to program change. Moved from september to November - no riskto program. 23.9.25 BH - One of the training groups will undertake the OSI Audit, date to be confirmed later, remove for now. | C | No | Yes | SS&A - Environmental Services and Assurance | Line 2 - Corporate Functions | 2025-11-03 | 2025-12-31 |  | Stuart Woodings | Sam Bulmer | Audit | Delivery - Site Programme | Two Village By-Pass - Advanced Works Finish (L3 Reporting Milestone) | Environment | N/C | N/C |  | N/A | AD3/TVB/FRA/59 AD3/TVB/WRA/1 AD3/TVB/WEX/26 AD3/TVB/CAP/5 AD3/TVB/MPDF/8 AD3/TVB/OWC/44 AD3/TVB/OWC/62 | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | Yes |  |  |  | N/A | [13 empty] | Yes
231 | EA Compliance Inspection Permit/Licence: TCA Borehole | Confirm compliance with the requirements of the permit. | 2.9.25 JB - New item added. | R | Yes | Yes | External Review - EA | Line 4 - External | 2025-11-06 | 2025-11-06 |  | Fran Gradie | Thomas Brazendale | Inspection | SS&A - Environmental Services and Assurance | N/A - No specific Milestone | Environment | N/C | N/C |  | N/A | Water Resources Abstraction Licence - for the abstraction of water during construction | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
20 | Marine Bulk Import Facility Milestone Review | Review in preparation for Marine Bulk Import Facility Milestone Launch Platform | 8.1.25 - Marine part delayed so pushed back from Jan 25 start date to 1st April start date now. 15.08.25 BH -Build due to start in December 2025. Date changed to reflect this . 23.9.25 BH - This activity is superseeded by Item 217 (commencement review). Please remove. | A | No | Yes | SS&A - Environmental Services and Assurance | Line 2 - Corporate Functions | 2025-11-10 | 2025-12-31 |  | Stuart Woodings | Sam Bulmer | Review | Delivery - Site Programme | EEW30 - Construct Launch Platform for Marine Bulk Import Facility | Environment | N/C | N/C |  | N/A | N/A | 2.1.8 U1 - Commence construction of the Marine Bulk Import Facility |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | Yes
255 | Quality Assurance - Action Assurance Reviews Q4 2025 | Conduct assurance checks on a sample of closed Insight actions, across various teams, to check they have been closed, with evidence and that the actions have been effective. | 08.10.25 FD: This is to facilitate closure of action 72156 rasied in the external ISO 14001 audit. | C | Yes | Yes | SS&A - Quality Assurance | Line 2 - Corporate Functions | 2025-11-10 | 2025-11-30 |  | Fran Gradie | Vanessa Tsanang | Review | Overall Project | N/A - No specific Milestone | Quality | N/C | N/C |  | LC 7 | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  | Faun | N/A | N/A | N/A | N/A | [11 empty] | No
116 | IR-53502 | Planned inspection of permitting, authorisation and setting to work Thematic inspection with a focus on control of work and authorisation. It will focus on the understanding and communication of hazards. Also the implementation of the management of interfaces between work sites, activities, contractors etc. To gain assurance that the PC and T1 contractors are fulling legal duties under CDM to plan, manage and co-ordinate work activities on site to manage risks - (Hayley Critchley) | 04.02.25 TB: Has dissapeared from Wired, will follow up and come back shortly. 27.02.25 JB: ONR are developing their intervention strategy, therefore all forthcoming inspections may well be cancelled or re-purposed. 3.4.25 TB - Please remove, this will no longer be proceeding as ONR are re-considering their future inspection regime. | R | Yes | Yes | External Review - ONR | Line 4 - External | 2025-11-17 | 2025-11-18 |  | Fran Gradie | Thomas Brazendale | Inspection | Delivery - Site Programme | N/A - No specific Milestone | Health, Safety & Wellbeing | N/C | N/C |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | Yes
232 | EA Compliance Inspection Permit/Licence: AN/035/0003/019 (AD6 Dewatering) | Confirm compliance with the requirements of the permit. | 2.9.25 JB - New item added. | R | Yes | Yes | External Review - EA | Line 4 - External | 2025-11-18 | 2025-11-18 |  | Fran Gradie | Thomas Brazendale | Inspection | SS&A - Environmental Services and Assurance | N/A - No specific Milestone | Environment | N/C | N/C |  | N/A | Water Resources Abstraction Licence - for the abstraction of water during construction | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
233 | EA Compliance Inspection Permit/Licence:AN/035/0003/018 (SSSI Dewatering) | Confirm compliance with the requirements of the permit. | 2.9.25 JB - New item added. | R | Yes | Yes | External Review - EA | Line 4 - External | 2025-11-18 | 2025-11-18 |  | Fran Gradie | Thomas Brazendale | Inspection | SS&A - Environmental Services and Assurance | N/A - No specific Milestone | Environment | N/C | N/C |  | N/A | Water Resources Abstraction Licence - for the abstraction of water during construction | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
234 | EA Compliance Inspection Permit/Licence: EPR/RP3820SH (CWDA/18) | Confirm compliance with the requirements of the permit. | 2.9.25 JB - New item added. | R | Yes | Yes | External Review - EA | Line 4 - External | 2025-11-18 | 2025-11-18 |  | Fran Gradie | Thomas Brazendale | Inspection | SS&A - Environmental Services and Assurance | EA Inspection - Construction Water Discharge Activity (CWDA) Permit | Environment | N/C | N/C |  | N/A | Construction Water Discharge Activity Permit | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
94 | ISO 14001 Audit (November - Recertification) | 3rd Party Audit/Inspection | 21.5.25 CT - Now moved to the 8th Dec start date based on schedule information referred to today and shared. 11.6.25 CT - Dates updated to 24th Nov - 5th Dec (extra time to allow for reports to be concluded), still discussing with relevant stakeholders. 29.9.25 PL - Peter confirmed current understanding is that audit will run from 24th - 28th November, with remaining time on this line set aside for time for report to be concluded. | R | Yes | Yes | External Review - LRQA | Line 4 - External | 2025-11-24 | 2025-12-31 |  | Stuart Woodings | Sam Bulmer | Audit | Overall Project | ISO 14001: Recertification Audit Complete | Environment | N/C | N/C |  | LC17 | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
139 | ISO 9001 SV2 Audit | 3rd Party Audit/Inspection - Combined audit with ISO 14001 (Please see activity ID 94) | 10.04.25 PL - new line to add 9001 audit SV2 which will be combined with activity 94. 11.6.25 CT - Dates updated to 24th Nov - 5th Dec (extra time to allow for reports to be concluded), still discussing with relevant stakeholders. 29.9.25 PL - Peter confirmed current understanding is that audit will run from 24th - 28th November, with remaining time on this line set aside for time for report to be concluded. | R | No | Yes | External Review - LRQA | Line 4 - External | 2025-11-24 | 2025-12-31 |  | Fran Gradie | Christopher Thompson | Audit | Overall Project | ISO 9001 SV | Quality | N/C | N/C |  | LC17 | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
237 | IR-54146 | CDM regulations arrangements; Client / PD / PC duties | 02.09.25 JB - New item added. | R | Yes | No | External Review - ONR | Line 4 - External | 2025-11-26 | 2025-11-27 |  | Fran Gradie | Thomas Brazendale | Inspection | SS&A - Security & Conventional Safety Assurance | ONR Construction Design Management (CDM) Inspection | Health, Safety & Wellbeing | N/C | N/C |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
83 | Quarterly review of environmental monitoring data, incidents and actions Q4 | Collaborative review of specialist environmental monitoring data, environmental incidents and open actions | 22/10/24 - Note: Combine with ESG team activities. 16.10.25 BH this has been removed due combining Q3 and Q4 . No risk | C | Yes | Yes | SS&A - Environmental Services and Assurance | Line 2 - Corporate Functions | 2025-12-01 | 2026-01-16 |  | Stuart Woodings | Sam Bulmer | Review | SS&A - Environmental Services and Assurance | N/A - No specific Milestone | Environment | N/C | N/C |  | LC17 | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | Yes
110 | Environmental Documentation Review - Q3/Q4 | Quarterly review of CEMP/SWMP/RAMS Q3 | 2.5.25 BH: Changed title from Q3 to Q4. 08.10.25 BH This has been pushed back due to resourcing issue. Will be conducted at a later date. No knock on effect | C | No | Yes | SS&A - Environmental Services and Assurance | Line 2 - Corporate Functions | 2025-12-01 | 2025-12-30 |  | Stuart Woodings | Sam Bulmer | Review | SS&A - Environmental Services and Assurance | N/A - No specific Milestone | Environment | N/C | N/C |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
111 | Environmental Documentation Review - Q4 | Quarterly review of CEMP/SWMP/RAMS Q4 | 16.10.25 bh - remove. | C | No | Yes | SS&A - Environmental Services and Assurance | Line 2 - Corporate Functions | 2025-12-01 | 2026-01-16 |  | Stuart Woodings | Sam Bulmer | Review | SS&A - Environmental Services and Assurance | N/A - No specific Milestone | Environment | N/C | N/C |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | Yes
157 | Site Emergency Arrangements 2026 | On-site emergency arrangments dip checks - includes document reviews (Incident Management Plans, RAMS), site attendnace - Emergency Arrangment Forums and onsite inspections - ongoing. | 15.9.25 PG - New item added. 15.10.25 PG - Have now altered timelines so we capture this 6 monthly instead. | C | Yes | Yes | SS&A - Emergency Preparedness | Line 2 - Corporate Functions | 2025-12-01 | 2026-05-29 |  | Andrew Wilkinson | Paul Gomar | Surveillance | Delivery - Site Programme | N/A - No specific Milestone | Health, Safety & Wellbeing | N/C | N/C |  | 11 | N/A | N/A | 101270587 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
63 | 13.1 - Stakeholder Relations | SZC-COG-PRO-001, Manage Communications SZC-COG-PRO-005, Virtual Data Room SZC-COG-PRO-011, Virtual Data Room Investor Exchange Note: Outdise of IMS Framework there are 3 procedures to consider. SZC-COG-PRO-004, Operative Information Database (OID) Obligations to Report to Government Shareholder Reporting Obligations | ACG 9APR25 - End date changed 10.04.25 FD: Added Level 2 ID Process Owner(s) name to column AU and added Procedure Lead Name(s) to column AT | C | No | No | SS&A - Quality Assurance | Line 2 - Corporate Functions | 2025-12-07 | 2026-02-05 |  | Fran Gradie | Vanessa Tsanang | Audit | F&ER | N/A - No specific Milestone | Reputation & Social License | N/C | N/C |  | LC6,LC17 | N/A | N/A |  | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  | Adrian | Vanessa (support) | N/A | Ben Geoghegan Sebastian Pampe | Lynne Kellet | Legal | Internal IMS Audit | 13.0 - Corporate Governance | 13.1 - Stakeholder Relations | Manage Communications Virtual Data Room Virtual Data Room Investor Exchange Obligations to Report to Government Operative Information Database (OID) Shareholder Reporting Obligations | SZC-COG-PRO-001 SZC-COG-PRO-005 SZC-COG-PRO-011 SZC-COG-PRO-004 | 7.4 7.5.3 | 7.4.1 7.4.2 7.4.3 | 7.4.1 7.4.2 7.4.3 |  |  | No
132 | ISO 27001 (Cybersecurity - Information Security) - Stage 1 | ISO 27001 assurance requirements Assures against: • SZC Statement of Applicability for ISO 27001:2022 ISMS • SZC Controls Framework Stage 1 December 2025 | PL: New line added: Stage 1 of the ISO 27001 separated from the activity ID 27. 21.5.25 CT - Now moved to the 8th Dec start date based on schedule information referred to today and shared. 11.6.25 CT - Dates updated to 15th-16th December with time for the report. 29.9.25 PL - Peter confirmed that still pencilled in for 15th - 18th December, with remaining time shown here, left for report to be concluded. | R | Yes | No | External Review - LRQA | Line 4 - External | 2025-12-15 | 2025-12-25 |  | Andrew Wilkinson | James Costello | Audit | Overall Project | ISO 27001 Stage 1 | Cyber security | N/C | N/C |  | LC17 | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
26 | Concrete Batching Plant | Review in preparation for Concrete Batching Plant. MDS/CAP/1. | 22/10/24 - Note: Combine with ESG team activities. Confirm timescales for this. 23.9.25 BH - Push start date to end of January 2026 and I shall review. 22.10.25 BH - To confirm with Steve Mason for involvement of H&S Team. | C | No | Yes | SS&A - Combined Line 2 Team | Line 2 - Corporate Functions | 2025-12-31 | 2026-01-31 |  | Stuart Woodings | Sam Bulmer | Review | Delivery - Site Programme | Unit 1 Concrete Batch commissioning | Environment | N/C | N/C |  | LC2 | Combustion Activity Permit | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
102 | Review of SME input in procurement space Q3/Q4 | Review of SME input in procurement space Q3/Q4 | 3.4.25 - AW: Opportunity for this activity to be brought forward, and to see if it can be expanded to security and safety, please check with Sam and report back. 23.9.25 - BH - Move start date to end of year, in line with us reviewing both quarters. | C | No | Yes | SS&A - Environmental Services and Assurance | Line 2 - Corporate Functions | 2025-12-31 | 2026-01-31 |  | Stuart Woodings | Sam Bulmer | Review | Overall Project | N/A - No specific Milestone | Environment | N/C | N/C |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
24 | Northern Drainage Culvert functional assurance | Potential Regulatory Permission Point. Awaiting clarity to see if this will be a clear HP, but expecting it should be. | 20.11.24 - TB: Updated to add milestone and link to Northern Drainage Culvert, as HP was missing from original IAAP list. 4.2.25 - Josh will be supporting Holdpoint review team. 3.4.25 - TB: Please push forward into 2026 as this has been put back now (HP). 1.5.25 TB: Likely to be removed as a holdpoint so please remove for now. | A | Yes | No | SS&A - Nuclear Licence Compliance | Line 2 - Corporate Functions | 2026-01-01 | 2026-04-01 |  | Fran Gradie | Thomas Brazendale | Audit | Civils Work Programme | Commence Northern Drainage Culvert - Hold Point | Nuclear Safety Risk | N/C | N/C | Risk 934. | N/A | N/A | 2.3.14 U1 - Northern Drainage Culvert |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | Yes
73 | Environmental Aspects and Impacts Self Assessment | Procedural self-assessment | 26.03.25 BH - Date pushed back due to July, due to time commitments of upcoming IS)14001 audit. 18/06/2025 EJ - meeting with NW, EW and CM. Proposed mid september deadline but understand this may need to be pushed back due to resourcing (potentially end of October). Monthly meetings to review progress. 29.07.25 EJ - NW confirmed this will kick off at start of September, agreed to push deadline to end of October. 15.08.25 BH - Confirm to be started in September. 23.9.25 EW - Postponed whilst it's being updated. Push back to March 2026 for now (tbc). 25.09.25 EJ - Postponed to coincide with update of Aspects and Impacts procedure. Requirement for self-assessment needs to be in the Implementation Plan for Procedure update, so more appropriate to align self-assessment to cover effectiveness and implementation of updated procedure. Proposed start January 2026, proposed deadline March 2026, to be kept under review. | C | No | No | SS&A - Operational Permits | Line 1 - Corporate Functions | 2026-01-01 | 2026-03-31 |  | Stuart Woodings | Emma Wells | Self Assessment | Overall Project | N/A - No specific Milestone | Environment | Green | N/C |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
82 | 6 Monthly review of environmental monitoring data, incidents and actions Q3/Q4 | Collaborative review of specialist environmental monitoring data, environmental incidents and open actions | 22/10/24 - Note: Combine with ESG team activities. 2.5.25 BH: Changed title from Q3 to Q4. 08/10/25 BH - This activity has been changed to 6 monthly due to resourcing issues, there will be no knock on effect. | C | Yes | Yes | SS&A - Environmental Services and Assurance | Line 2 - Corporate Functions | 2026-01-01 | 2026-01-30 |  | Stuart Woodings | Sam Bulmer | Review | SS&A - Environmental Services and Assurance | N/A - No specific Milestone | Environment | N/C | N/C |  | LC 7 | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
144 | Oversee Construction Works - One-off audit. | SZC-ACQ-PRO-032, Site Non-Conformances, Field Change Requests and Request for Information | Emerging risk identified by Environmental Assurance Lead (Becky H.) • The roles and responsibilities within the procedure are not up-to-date and are not clearly defined. FCR/NCR are regularly rejected late in the process due to lack of information; this is due to parts of the process (e.g. quality control) not being fulfilled by the relevant stakeholder, as defined in the procedure. • It is unclear what constitutes the raising of an FCR/NCR and what design changes may belong under a different governance process. • Immaturity on FCR process is subsequently having a negative impact on Environmental Surveillance (i.e. high ranks given, diluting the weighting of a high rank long-term). • An initial identification of relevant stakeholders prior to the update of the Site Non-Conformances, Field Change Requests and Requests for Information procedure was not undertaken (existing list is out-dated/not comprehensive). There are many stakeholders who are involved in the process that have not been engaged. • Currently no clarification on whether OSI sites are included in the scope of the procedure. OSI sites do not fall under Nuclear Licence conditions (is this correct?) and so how are those design changes being managed/recorded? 21.5.25 - VT - Just reflected one-off audit in title. 9.7.25 VT - Still waiting to hear from procedure owner, please push back from July to September for now. Move to Red (BRAG). 18.08.2025 FD: Meeting held with Carl H on 15.08.25 to obtain an update on where we are with this procedure update. He’s still liaising with the team to review the suggested changes. Once submitted, it will need to go through IRP, and we’d need to allow time for the procedure to be implemented into the business before auditing. Due to this pushing back from Sep to Nov. 07.10.2025 FD: This audit will now be moved to the 2026 audit schedule due to the release of a new version of the procedure SZC-CON-PRO-011 Manage Construction Change – File Change Request (FCR) and Request for Information (RFI). As this updated procedure is not likely to be published in the IMS until November, we need to allow 3–6 months for it to be implemented across the business. The audit will now focus on assessing the effectiveness of the new procedure once implemented, and will also address actions related to NC 9214 raised during our external ISO 14001 audit concerning the FCR/RFI process. | C | No | Yes | SS&A - Quality Assurance | Line 2 - Corporate Functions | 2026-01-01 | 2026-02-09 |  | Fran Gradie | Vanessa Tsanang | Audit | Delivery - Delivery/PDO | N/A - No specific Milestone | Quality | Red | N/C |  | LC6, LC12 & LC17 | N/A | N/A |  | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  | Faun | Adrian | N/A | Sebastien Bachere | Steven Heard | PDO Quality | One-off audits | 3.0 - Construct to Handover | 3.3 - Oversee Construction Works | Site Non-Conformances, Field Change Requests and Request for Information | SZC-ACQ-PRO-032 | 8.2.4 8.7 10.2 | 6.1.4 10.1 10.2 10.3 | 6.1.4 10.1 10.2 10.3 |  |  | No
160 | Material Management Review | Environmental review looking at materials handling, management and disposal if relevant | 18.07.25 - BH New Item | C | No | Yes | SS&A - Environmental Services and Assurance | Line 2 - Corporate Functions | 2026-01-01 | 2026-03-31 |  | Stuart Woodings | Sam Bulmer | Review | Overall Project | N/A - No specific Milestone | Environment | N/C | N/C |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
161 | Q1 CWA - Quarterly Review Environmental Assurance Activities | Look at assurance program, targeted/reactive inspections, significance of outcome, follow up of actions | 18.07.25 - BH New Item | C | No | No | SS&A - Environmental Services and Assurance | Line 2 - Corporate Functions | 2026-01-01 | 2026-03-31 |  | Stuart Woodings | Sam Bulmer | Review | SS&A - Environmental Services and Assurance | N/A - No specific Milestone | Environment | N/C | N/C |  | LC 7 | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
165 | Q1 - Critical Environmental Documentation Review | Quarterly review of CEMP/SWMP/RAMS | 18.07.25 - BH New Item | C | No | No | SS&A - Environmental Services and Assurance | Line 2 - Corporate Functions | 2026-01-01 | 2026-03-31 |  | Stuart Woodings | Sam Bulmer | Review | SS&A - Environmental Services and Assurance | N/A - No specific Milestone | Environment | N/C | N/C |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
169 | Q1 Review of environmental monitoring data, incidents and actions | Collaborative review of specialist environmental monitoring data, environmental incidents and open actions | 18.07.25 - BH New Item | C | No | No | SS&A - Environmental Services and Assurance | Line 2 - Corporate Functions | 2026-01-01 | 2026-03-31 |  | Stuart Woodings | Sam Bulmer | Review | SS&A - Environmental Services and Assurance | N/A - No specific Milestone | Environment | N/C | N/C |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
174 | Water abstraction | Review of permit compliance, consent understanding, review of compliance stratagy and collaboration. Follow up to current investigation. | 18.07.25 - BH New Item | B | No | Yes | SS&A - Environmental Services and Assurance | Line 2 - Corporate Functions | 2026-01-01 | 2026-03-31 |  | Stuart Woodings | Sam Bulmer | Review | SS&A - Environmental Services and Assurance | N/A - No specific Milestone | Environment | N/C | N/C |  | N/A | Water Resources Abstraction Licence - for the abstraction of water during construction | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
176 | Q1 SME Input into Procurement | Review of SME input in procurement space. Review of tracker, look at gaps where environment management SME not involved in certain tender review | 18.07.25 - BH New Item | C | No | No | SS&A - Environmental Services and Assurance | Line 2 - Corporate Functions | 2026-01-01 | 2026-03-31 |  | Stuart Woodings | Sam Bulmer | Review | SS&A - Environmental Services and Assurance | N/A - No specific Milestone | Environment | N/C | N/C |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
191 | Audit - Yoxford Roundabouts | Audit- against legal, SZC document, best environmental practice | 18.07.25 - BH New Item | B | No | Yes | SS&A - Environmental Services and Assurance | Line 2 - Corporate Functions | 2026-01-01 | 2026-03-31 |  | Stuart Woodings | Sam Bulmer | Audit | SS&A - Environmental Services and Assurance | Yoxford Roundabout - Completion of Works (L3 Reporting Milestone) | Environment | N/C | N/C |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
205 | Q1 Environmental Management Review | Quarterly Management review | 18.07.25 - BH New Item | C | No | No | SS&A - Environmental Services and Assurance | Line 2 - Corporate Functions | 2026-01-01 | 2026-03-31 |  | Stuart Woodings | Emma Wells | Review | SS&A - Environmental Services and Assurance | N/A - No specific Milestone | Environment | N/C | N/C |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
217 | Hold Point - commencement of Marine Bulk Import Facility | Review of environmental requirements for the release of this hold point. Hold point manager Alex Edge | 18.07.25 - BH New Item | A | No | No | SS&A - Environmental Services and Assurance | Line 2 - Corporate Functions | 2026-01-01 | 2026-03-31 |  | Stuart Woodings | Sam Bulmer | Review | SS&A - Environmental Services and Assurance | MBIF Hold Point Release | Environment | N/C | N/C |  | N/A | N/A | 2.1.8 U1 - Commence construction of the Marine Bulk Import Facility |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
218 | Hold point - Equipment care and maintenance | Review of environmental requirements for the release of this hold point. Hold point manager Sebastian Bachere | 18.07.25 - BH New Item | B | No | No | SS&A - Environmental Services and Assurance | Line 2 - Corporate Functions | 2026-01-01 | 2026-01-01 |  | Stuart Woodings | Sam Bulmer | Review | SS&A - Environmental Services and Assurance | Care & Maintanance Hold Point Release | Environment | N/C | N/C |  | N/A | N/A | 2.3.16 U1 - Equipment Care and Maintanance |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
23 | Temporary Sea Defence functional assurance | Potential Regulatory Permission Point | 20.11.24: TB - Update to link to relevant holdpoint. 16.1.25: TB - Some delays with MED (programme linked) aiming for Feb/March HP Panel. 24.6.25 TB: No change to dates as things stand, but could move closer to the time. | A | No | Yes | SS&A - Nuclear Licence Compliance | Line 2 - Corporate Functions | 2026-01-05 | 2026-03-30 |  | Fran Gradie | Thomas Brazendale | Audit | Civils Work Programme | Temporary Sea Defence - Hold Point Released to Commence Temporary Sea Defence | Nuclear Safety Risk | N/C | N/C |  | N/A | N/A | 2.1.6 U1 - Temporary Sea Defence |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
41 | 12.2 - Organisational Development | SZC-COG-PRO-007, Manage Board Membership - This process will move to Legal, and the best contact for arranging this and to see what process this procedure will sit in is Asha Magnus. The internal Audit should be scheduled from June 2026, as the updated procedure will be ready at FID. SZC-PEO-PRO-009, Management of Organisational Change | 18.10.24 ACG - From PAP where procedures are Implemented and Published in IMS 10.04.25 FD: Added Level 2 ID Process Owner(s) name to column AU and added Procedure Lead Name(s) to column AT 19/06/2025 FD: Updated planned start date from 1/12/2024 to 5/01/2026 as requested by MC & Agreed by VT. Feedback received from MC regarding the move of procedure SZC-COG-PRO-007, Manage Board Membership, noted added. | C | No | No | SS&A - Quality Assurance | Line 2 - Corporate Functions | 2026-01-05 | 2026-04-05 |  | Fran Gradie | Vanessa Tsanang | Audit | Human Resources | N/A - No specific Milestone | Reputation & Social License | N/C | N/C |  | LC6, LC12, LC10 & LC17 | N/A | N/A |  | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  | Faun | N/A | N/A | Asha Magnus Rachel Kerry | Marta Carnicero | Human Resources | Internal IMS Audit | 12.0 - People | 12.2 - Organisational Development | Management of Organisational Change Manage Board Membership | SZC-PEO-PRO-009 SZC-COG-PRO-007 | 5.3 | 5.3 | 5.3 |  |  | No
88 | MMO Pre-regulatory readiness review 1 | Pre-regulatory (MMO) reviews - to support known MMO audit on site in relation to a marine licence(s). Technical specialism focused. Our new 'site-based' person will be picking this up. | 27.11.24: SM - Start date has now moved to -, however this will be driven by the MMO Inspection programme, this date movement presents no material risk. 03.03.25 BH date moved back due to programme change, this means that MMO unlikely to make a site visit. 3.4.25 SR: We shall keep this one as is for now, but potential for it to move to the Right. 5.9.25: SR: Programme is moving to the Right, please move to the start of Jan 2026. No risk. | C | No | Yes | SS&A - Marine Team | Line 2 - Corporate Functions | 2026-01-05 | 2026-02-28 |  | Stuart Woodings | Stephen Roast | Review | SS&A - Environmental Services and Assurance | N/A - No specific Milestone | Environment | N/C | N/C |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
153 | Environmental Categorisation NCC Quarterly Review Q4 | Ongoing input into environmental impact assessment of design modifications/evolutions | 18.06.25 EJ - added following discussion with EW and based on previous discussions on Item 13. 20.10.25 - BH consider removing as Emma's team undertaking 100% of the related meetings and categorisations | C | No | No | SS&A - Operational Permits | Line 1 - Corporate Functions | 2026-01-05 | 2026-01-31 |  | Stuart Woodings | Emma Wells | Review | Overall Project | N/A - No specific Milestone | Environment | N/C | N/C |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
78 | 6.5 - Nuclear Safety | SZC-HSE-PRO-003 - Radiation Protection Advisor Appointment SZC-HSE-PRO-017 - Develop Decommissioning Plan SZC-HSE-PRO-022 - Address Differing Professional Opinions SZC-HSE-PRO-024 - Maintain Nuclear Site Licence Boundary SZC-HSE-PRO-029 - Provide Nuclear Site Licence Warning Notices SZC-HSE-PRO-034 - Control of Nuclear Matter SZC-HSE-PRO-043 - Review Radiation Exposure SZC-HSE-PRO-059 - Radon Management SZC-HSE-STA-003 - Radiological Safety Standards Note ONE other procedure is not Published in IMS at time of planning Hold Point Released for Confirmation of the radiological cleanliness of the SZC site (May be some value in learning the lessons of why it seems no assurance activity has taken place | 17.10.24 PL: Hold Point Released for Confirmation of the radiological cleanliness of the SZC site. Though this Milestone has passed it will still be in the next update of the IAAP and there should have been assurance activities related to it that are not recorded. Baseline date was 8/3/24 10.04.25 FD: Added Level 2 ID Process Owner(s) name to column AU and added Procedure Lead Name(s) to column AT | C | No | Yes | SS&A - Quality Assurance | Line 2 - Corporate Functions | 2026-01-13 | 2026-04-13 |  | Fran Gradie | Vanessa Tsanang | Audit | ESG & Rad Strat - Rad Pro & Nuclear Liabilities | N/A - No specific Milestone | Nuclear Safety Risk | N/C | N/C |  | LC6 LC17 | N/A | N/A |  | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  | Vanessa | Adrian | N/A | Simon Barnard Pete Bryant Tim Newton Fran Gradie | Matthew Castle | Pre-Operations | Internal IMS Audit | 6.0 - Health, Safety, Security & Environment | 6.5 - Nuclear Safety | Maintain Nuclear Site Licence Boundary Address Differing Professional Opinions Control of Nuclear MatterDevelop Decommissioning Plan Provide Nuclear Site Licence Warning Notices Radiation Protection Advisor Appointment Radiological Safety Standards Radon Management Review Radiation Exposure Undertake Station Commissioning Testing Conduct Supply Chain Surveillance | SZC-HSE-PRO-024 SZC-HSE-PRO-022 SZC-HSE-PRO-034 SZC-HSE-PRO-017 SZC-HSE-PRO-029 SZC-HSE-PRO-003 SZC-HSE-STA-003 SZC-HSE-PRO-059 SZC-HSE-PRO-043 SZC-HSE-PRO-053 |  | 8.1 9.1.2 8.2 9.1.1 | 8.1.1 9.1.2 6.1.1 7.5.1 8.1.2 6.1.2 9.1.1 6.1.4 |  |  | No
238 | IR-54148 | Learning and capable organisation for supply chain management | 02.09.25 JB - New item added. | R | Yes | No | External Review - ONR | Line 4 - External | 2026-01-20 | 2026-01-20 |  | Fran Gradie | Thomas Brazendale | Inspection | Delivery - Delivery/PDO | ONR Supply Chain Management Inspection | Operational Capability | N/C | N/C |  | LC 17, 19, 36 | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
58 | 3.7 - Care & Maintenance of Assets & Equipment | IMPORTANT NOTE = THERE IS ASSOCAITED HOLD POINT SZC-C2H-PRO-025, Manage As-Built Utilities & Construction Hazard Information. Note FOUR other procedures not yet Published in IMS at time of planning | 18.10.24 ACG - From PAP where procedures are Implemented and Published in IMS 26.3.25 VT - There are 4 procedures not yet published in IMS at this time. ACG 9APR25 - End date changed 02.5.25 CC - Manus O Donnel contacted related to the audit / definition of lead auditor. 23.5.25 CC: Manus O Donnel informed that this audit is not in his area; Mannus informed that Andy Langley and Stephen Mason can support on this topic, and both were contacted on 23.05 AND 02.06 (awaiting response). 09.06.25 CC: email sent from Vanessa to Sebastien Bachere, escalating the topic. The RAG status is changed to red. 11.6.25 VT - Changed to Yes for interest from regulator (assocaited holdpoint), we first reached out to the team on the 2nd May (lead auditee and process owner), they are saying they are not responsible for this process. Last email to Seb Bacherre on 9th June, still no response. 10.06.25 CC - Andrew Kelleher contacted by email, as suggested by Stephen Mason (awaiting response) 24.6.25 CCG - Audit has not started, keep as BRAG Red and we shall check and come back to you. 03.07.25 CC: BRAG changed from REd to Amber: this audit is linked to a Hold Point which now postponed so risks / impact for not performing an audit on this area is limited.Linked milestone added to the column S. Note: linked to the activity ID 25. To be rescheduled. 12.9.25 VT: Following discussions, we have scheduled this for Q1 2026 and revised dates. | C | Yes | Yes | SS&A - Quality Assurance | Line 2 - Corporate Functions | 2026-01-26 | 2026-03-13 |  | Fran Gradie | Vanessa Tsanang | Audit | Delivery - Site Programme | Commence Equipment Care & Maintenance Hold Point | Quality | Amber | N/C |  | LC6,LC17 | N/A | 2.3.16 U1 - Equipment Care and Maintanance |  | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  | Camila | N/A | N/A | Manus O'Donnell | Sebastien Bachere | NI Programme | Internal IMS Audit | 3.0 - Construct to Handover | 3.7 - Care & Maintenance of Assets & Equipment | Manage As-Built Utilities & Construction Hazard Information Manage Disposal of Surplus and Scrap Materials and Equipment Preservation/Cocooning Repairs During Construction Control Maintenance of Installed Plant and Equipment | SZC-C2H-PRO-025 SZC-C2H-PRO-018 SZC-C2H-PRO-019 SZC-C2H-PRO-021 SZC-C2H-PRO-001 | 7.1.6 7.5.3 | 7.5.3 |  |  |  | No
103 | IR-53497 | Implementation of learning from HPC and other relevant infrastructure projects to inform development of construction design and site operations/management. | 04.02.25 TB: Defferred to a later date, will advise of new date in due course. 27.02.25 JB: ONR are developing their intervention strategy, therefore all forthcoming inspections may well be cancelled or re-purposed. 3.4.25 TB - Please remove, this will no longer be proceeding as ONR are re-considering their future inspection regime. | R | Yes | Yes | External Review - ONR | Line 4 - External | 2026-01-26 | 2026-01-27 |  | Fran Gradie | Thomas Brazendale | Inspection | Delivery - Site Programme | N/A - No specific Milestone | Health, Safety & Wellbeing | N/C | N/C |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | Yes
257 | Quarterly Standback review of Line 1 Assurance by SS&A - Meeting 1 | To be updated, speak to Fran Gradie, Stuart Woodings, and Andrew Wilkinson. | 13.10.25 AB: Added in Assurance planning workshop at request of HoF's. | B | No | Yes | SS&A - Combined Line 2 Team | Line 2 - Corporate Functions | 2026-01-31 | 2026-02-28 |  | Fran Gradie | Vanessa Tsanang | Review | Delivery - Site Programme | N/A - No specific Milestone | Quality | N/C | N/C |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
33 | Assurance of Occupational Health Arrangements | Review of Occupational Health Arrangements against Strategy. | 4.12.25 EB: New activity added today. 05.02.25 SM: Ceri still building her team, will consult with her again shortly and come back. 12.5.25 SM: Still need time for them to become embedded, the review against the standard once we see what the standard says. 10.10.25 SM: Contract is yet to be signed so won't now start in Oct, please push into 2026 for now and Emma will come back to you after checking with Ceri. | B | No | Yes | SS&A - Security & Conventional Safety Assurance | Line 2 - Corporate Functions | 2026-02-01 | 2026-03-28 |  | Andrew Wilkinson | Stephen Mason | Assessment | Delivery - Site Programme | N/A - No specific Milestone | Health, Safety & Wellbeing | N/C | N/C |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
254 | Self- assessment PEMP | This is a self assessment of the PEMP, following implementation through the IRP | 06.10.25 BH new item | C | No | No | SS&A - Environmental Services and Assurance | Line 2 - Corporate Functions | 2026-02-01 | 2026-03-30 |  | Stuart Woodings | Sam Bulmer | Self Assessment | Overall Project | N/A - No specific Milestone | Environment | N/C | N/C |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
134 | ISO 45001 Surveillance Visit 1 (date to be confirmed after stage 2). | ISO 45001 assurance requirements 1 Surveillance Audit | PL 25.03.25: New line added related to the next step after the Gap analysis for the ISO 45001, related the surveillance audit. PL 29.9.25: Will be 2nd-5th Feb (no longer March) for SV1. | R | No | Yes | External Review - LRQA | Line 4 - External | 2026-02-02 | 2026-02-28 |  | Andrew Wilkinson | Stephen Mason | Audit | Overall Project | ISO 45001 Certification | Health, Safety & Wellbeing | N/C | N/C |  | LC17 | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
182 | Legal Register and Procedure Changes Self Assessment | Following updates and changes to the legal regiister, procedure updates and improves to the implementation. HSW Team and Steve Mason will support this self-assessment but it will still be led by Environment team, so alignment can be understood on the tool for both Enviro and H&S Legal Registers. | 18.07.25 - BH New Item 23.10.25 - AB/SM: Please can HSW Team dock-in to this self-assessment please (From Stephen Mason), so Env to lead and HSW will look to play a part where neccesary. Changed assuring function to SS&A - Combined Line 2 team. | B | No | No | SS&A - Combined Line 2 Team | Line 1 - Corporate Functions | 2026-02-02 | 2026-03-10 |  | Stuart Woodings | Sam Bulmer | Self Assessment | SS&A - Environmental Services and Assurance | N/A - No specific Milestone | Environment | N/C | N/C |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
239 | IR-54149 | Implementation of CDM Regulations | 02.09.25 JB - New item added. | R | Yes | Yes | External Review - ONR | Line 4 - External | 2026-02-26 | 2026-02-27 |  | Fran Gradie | Thomas Brazendale | Inspection | Delivery - Site Programme | ONR Construction Design Management (CDM) Inspection | Health, Safety & Wellbeing | N/C | N/C |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
67 | MOC Technical Directorate One-off Audit | Management of Change - Technical Directorate A look at the Management of Change activities suporting the standup of the Technical Directorate. | 10.04.25 FD: Added Level 2 ID Process Owner(s) name to column AU and added Procedure Lead Name(s) to column AT 21.5.25 - VT - Just reflected one-off audit in title. | C | No | No | SS&A - Quality Assurance | Line 2 - Corporate Functions | 2026-03-01 | 2026-05-30 |  | Fran Gradie | Vanessa Tsanang | Audit | Technical | N/A - No specific Milestone | People & Skills | N/C | N/C |  | LC6, LC12 & LC17 | N/A | N/A |  | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  | Camila |  | N/A | Tim Wilbraham Paul Sutherland | Tilly Spencer / Jonathan Jones | Technical | One-off audits | 1.0 - Design to Accept | 1.2 - Manage Design | Produce Design Deliverables Provide New ECS Code Manage Design Collaboration | SZC-D2A-PRO-006 SZC-D2A-PRO-005 | 8.1 8.3.2 8.3.3 8.5.2 | 8.1 | 8.1.2 |  |  | No
75 | 13.3 - Corporate Performance & Governance | SZC-COG-PRO-003, Manage Financial Authorities Framework SZC-COG-PRO-008,Manage Board Committee Terms of Reference SZC-COG-PRO-009, Manage Company Policies | 10.04.25 FD: Added Level 2 ID Process Owner(s) name to column AU and added Procedure Lead Name(s) to column AT 15.9.25 VT: Please remove from the plan following on from latest update. | C | No | No | SS&A - Quality Assurance | Line 2 - Corporate Functions | 2026-03-01 | 2026-05-30 |  | Fran Gradie | Vanessa Tsanang | Audit | F&ER | N/A - No specific Milestone | Reputation & Social License | N/C | N/C |  | LC6, LC12 & LC17 | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  | Faun | Vanessa (support) | N/A | Asha Magnus Fran Gradie James Weeks Peter Bryant | Lynne Kellet | Legal | Internal IMS Audit | 13.0 - Corporate Governance | 13.3 - Corporate Performance & Governance | Manage Financial Authorities Framework Manage Board Committee Terms of Reference Manage Company Policies | SZC-COG-PRO-003 SZC-COG-PRO-008 SZC-COG-PRO-009 | 8.1 5.5.1 5.2.1 9.1.3 | 5.2 | 5.2 9.3 |  |  | Yes
118 | Emergency Response & Business Continuity One-off audit. | Specific focus on the new offices at 25 CA. SZC-HSE-PRO-037,Establish, Maintain and Develop Emergency Preparedness SZC-HSE-PRO-028, Fire Prevention and Fire Safety Arrangements At the time of planning the following procedure is not published in IMS. SZC-HSE-PRO-058, Establish and Maintain Business Continuity Arrangements Note there is one other procedure that is ouside the IMS Framework that needs to be considered while auditing. "Plan & Administer Emergency Exercises" | 26.3.25 VT/CT - Still awaiting publishing of Business continuity plan document. 3.4.25 AW: Vanessa to discuss dates for this with Andrew. ACG 9APR25 - End date changed 10.04.25 FD: Added Level 2 ID Process Owner(s) name to column AU and added Procedure Lead Name(s) to column AT 21.5.25 - VT - Just reflected one-off audit in title. 4.6.25 ACG - Fire recently covered at two locations (ACA and SMC). TC number for the report is 101455316. Report contains Insight Audit number and Scope TC reference. Scope of procedure and thus audit may change to Main Site only. 9.7.25 VT - As the emergency response procedures are being changed, please push back to March 2026 from September 2025. | C | No | Yes | SS&A - Quality Assurance | Line 2 - Corporate Functions | 2026-03-01 | 2026-04-30 |  | Fran Gradie | Vanessa Tsanang | Audit | SS&A - Security & Conventional Safety Assurance | N/A - No specific Milestone | Productivity | N/C | N/C |  | LC6,LC17 | N/A | N/A |  | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  | Adrian | N/A | N/A | Andrew Wilkinson | Paul Gomar | Safety, Security and Assurance | One-off audits | 6.0 - Health, Safety, Security & Environment | 6.2 - Emergency Response & Business Continuity | Establish and Maintain Business Continuity Arrangements Establish, Maintain and Develop Emergency Preparedness Fire Prevention and Fire Safety Arrangements Plan & Administer Emergency Exercises | SZC-HSE-PRO-058 SZC-HSE-PRO-037 SZC-HSE-PRO-028 |  | 8.2 | 8.2 |  |  | No
219 | Hold Point - Commence South Sea Defence | Review of environmental requirements for the release of this hold point. Hold point manager Alexander Stewart | 18.07.25 - BH New Item | B | No | No | SS&A - Environmental Services and Assurance | Line 2 - Corporate Functions | 2026-03-01 | 2026-03-01 |  | Stuart Woodings | Sam Bulmer | Review | SS&A - Environmental Services and Assurance | Temporary Sea Defence Hold Point Release | Environment | N/C | N/C |  | N/A | N/A | 2.1.6 U1 - Temporary Sea Defence |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
226 | Self Assessment of Develop and Amend Environmental Requirements | Self assessment for the effectiveness and implementation of the Develop and Amend Environmental Requirements procedure, following update in 2025. | 11.08.25 EJ New item | C | No | No | SS&A - Environmental Services and Assurance | Line 2 - Corporate Functions | 2026-03-01 | 2026-03-31 |  | Stuart Woodings | Sam Bulmer | Self Assessment | SS&A - Environmental Services and Assurance | N/A - No specific Milestone | Environment | N/C | N/C |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
5 | Develop and Manage Environmental Requirements 2025 | Self assessment of procedure. | 29.11.24 BH: Due to issues regarding the Themis tool (which is a key enabler for this activity) this self assessment will now be delayed till April 2024. Originally showing as starting in Oct 24 - Nov 24, this activity did not start due to Themis no longer a viable option, so getting 3rd party to compile documents. Please speak to Becky Hudson for further questions. No current issues or impacts that this should have with the start date being deferred. 2.5.25 BH - We have moved this back to the start of June, as may not start in May (original start point). 29.5.25 SB: Still on-track for this window, Mott's supporting this work over the next month, and Hannah is updating the procedure. 27.6.25 BH - Please move start date to mid-July, to be safe as we are awaiting a report from Motts (previously aimed to start in June). 25.7.25 bh - Please update start date to Mid-August (prev July), to end in Mid-October. 15.08.25 - The procedure has been rewritten and so this activity is being postponed. Date adjusted. | C | No | Yes | SS&A - Environmental Services and Assurance | Line 1 - Corporate Functions | 2026-03-15 | 2026-05-15 |  | Stuart Woodings | Sam Bulmer | Self Assessment | SS&A - Environmental Services and Assurance | N/A - No specific Milestone | Environment | N/C | N/C |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
133 | ISO 27001 (Cybersecurity - Information Security) - Stage 2 | ISO 27001 assurance requirements Assures against: • SZC Statement of Applicability for ISO 27001:2022 ISMS • SZC Controls Framework Stage 2 March 2026 | PL: New line added: Stage 2 of the ISO 27001 29.9.25 PL - Updated start date which will now be mid-March 2026 (originally down for start of March). | R | Yes | Yes | External Review - LRQA | Line 4 - External | 2026-03-16 | 2026-03-31 |  | Andrew Wilkinson | James Costello | Audit | Overall Project | ISO 27001 Stage 2 | Cyber security | N/C | N/C |  | LC17 | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
135 | PAS2080 surveillance visit 1 - 2026 | PAS2080 assurance requirements PAS2080 Audit | PL 25.03.25: New line added related to the next step of the PAS2080. PL 9.4.25: Date has moved back to April 2026 for this next surveillence visit now. PL 29.9.25: Date has moved back from April to March for this now. Still discussing site presence with Mark Fenton. | R | Yes | Yes | External Review - LRQA | Line 4 - External | 2026-03-18 | 2026-03-27 |  | Fran Gradie | Christopher Thompson | Audit | Overall Project | N/A - No specific Milestone | Reputation & Social License | N/C | N/C |  | LC17 | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
48 | Assurance of compliance to Culture Contractor requirements | Checking of compliance to contractor requirements for culture, PM assurance of requirements adequetly evidenced/demonstrable. Ascertainment of programme, and whether stand-alone audit included within other assurance activities. | 04.2.25 KAC: Compiling list, then conversation with Vanessa to understand in current audit arrangements where these things are addressed. 04.03.25 KAC: Have spoken to Vanessa, planning on speaking to Stephen Heard and team, also looking to update CBL Documents, so we have pushed this back to start at beginning of August 2025. 1.5.25 KAC: quality assurance - CBL docs currently in final round of approval - currently undertaking a review of those existing pertaining to nuclear, and use of the nuc safety checklist in place as part of this auditing activity. some of this work will also depending on the discussion between steven heard and fran in the 'who does what' context. 24.6.25 KAC: Conversations with Steven Heard's team are ongoing on documentation, please push back from August to September for start date. 14.8.25 KAC: Still having conversations on lines of defence with relevant stakeholders, e.g. Martin Davies. Until we get further clarity on this we can't really start the work for now, let's revisit this next month or when we know more. 10.9.25 KAC: Dependent on outcome of Blueprint on Integrated Assurance. Please push forward a month for now to October. 8.10.25 KAC: Please push back to April next year, may start sooner but delay with CBL Document work, will update if starts sooner. | C | No | No | SS&A - Culture | Line 2 - Corporate Functions | 2026-04-01 | 2026-07-31 |  | Fran Gradie | Katie Anderson-Cousins | Audit | Overall Project | N/A - No specific Milestone | Nuclear Safety Risk | Green | N/C |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
158 | LC08 Warning Notices 26/27 | Ensure that suitable and sufficient notices are kept on the site and posted in positions and characters as to be conveniently read for the purposes: 1.) of informing persons of any warning signal, 2.) ensuring exits and measures to be taken in the event of a fire or emergency. | 15.9.25 PG - New item added. | C | Yes | Yes | SS&A - Emergency Preparedness | Line 2 - Corporate Functions | 2026-04-01 | 2027-03-31 |  | Andrew Wilkinson | Paul Gomar | Surveillance | Delivery - Site Programme | N/A - No specific Milestone | Health, Safety & Wellbeing | N/C | N/C |  | 8 | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
162 | Q2 CWA - Quarterly Review Environmental Assurance Activities | Look at assurance program, targeted/reactive inspections, significance of outcome, follow up of actions | 18.07.25 - BH New Item | C | No | No | SS&A - Environmental Services and Assurance | Line 2 - Corporate Functions | 2026-04-01 | 2026-06-30 |  | Stuart Woodings | Sam Bulmer | Review | SS&A - Environmental Services and Assurance | N/A - No specific Milestone | Environment | N/C | N/C |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
166 | Q2 - Critical Environmental Documentation Review | Quarterly review of CEMP/SWMP/RAMS | 18.07.25 - BH New Item | C | No | No | SS&A - Environmental Services and Assurance | Line 2 - Corporate Functions | 2026-04-01 | 2026-06-30 |  | Stuart Woodings | Sam Bulmer | Review | SS&A - Environmental Services and Assurance | N/A - No specific Milestone | Environment | N/C | N/C |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
170 | Q2 Review of environmental monitoring data, incidents and actions | Collaborative review of specialist environmental monitoring data, environmental incidents and open actions | 18.07.25 - BH New Item | C | No | No | SS&A - Environmental Services and Assurance | Line 2 - Corporate Functions | 2026-04-01 | 2026-06-30 |  | Stuart Woodings | Sam Bulmer | Review | SS&A - Environmental Services and Assurance | N/A - No specific Milestone | Environment | N/C | N/C |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
173 | FCR Procedure and Resourcing | Review of amended procedure/ resourcing – switch tool launching in September 2025. SA on switch tool | 18.07.25 - BH New Item | A | No | No | SS&A - Environmental Services and Assurance | Line 2 - Corporate Functions | 2026-04-01 | 2026-06-30 |  | Stuart Woodings | Sam Bulmer | Review | SS&A - Environmental Services and Assurance | N/A - No specific Milestone | Environment | N/C | N/C |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
175 | Noise Monitors | Compliance to permits, set up of monitoring equipment, consistency and accuracy of data | 18.07.25 - BH New Item | C | No | Yes | SS&A - Environmental Services and Assurance | Line 2 - Corporate Functions | 2026-04-01 | 2026-06-30 |  | Stuart Woodings | Sam Bulmer | Review | SS&A - Environmental Services and Assurance | N/A - No specific Milestone | Environment | N/C | N/C |  | N/A | N/A | N/A |  | 30687 (Action 66028) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
177 | Q2 SME Input into Procurement | Review of SME input in procurement space. Review of tracker, look at gaps where environment management SME not involved in certain tender review | 18.07.25 - BH New Item | C | No | No | SS&A - Environmental Services and Assurance | Line 2 - Corporate Functions | 2026-04-01 | 2026-06-30 |  | Stuart Woodings | Sam Bulmer | Review | SS&A - Environmental Services and Assurance | N/A - No specific Milestone | Environment | N/C | N/C |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
183 | Review of Environmental Emergency Exercises | Review of contractors compliance against SZC requirements, good environmental practice, ensure exercises conducted are proprotion to risk | 18.07.25 - BH New Item | C | No | Yes | SS&A - Environmental Services and Assurance | Line 2 - Corporate Functions | 2026-04-01 | 2026-06-30 |  | Stuart Woodings | Sam Bulmer | Review | SS&A - Environmental Services and Assurance | N/A - No specific Milestone | Environment | N/C | N/C |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
185 | Piling Risk Assessments Self Assessment | Self assessment into the compliance against the requirements for piling risk assessments across the project | 18.07.25 - BH New Item | C | No | Yes | SS&A - Environmental Services and Assurance | Line 2 - Corporate Functions | 2026-04-01 | 2026-06-30 |  | Stuart Woodings | Sam Bulmer | Self Assessment | SS&A - Environmental Services and Assurance | N/A - No specific Milestone | Environment | N/C | N/C |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
192 | Audit - Waste Contractor | Audit of newly appointed waste contractor. Site, legislation, document compliance | 18.07.25 - BH New Item | B | No | Yes | SS&A - Environmental Services and Assurance | Line 2 - Corporate Functions | 2026-04-01 | 2026-06-30 |  | Stuart Woodings | Sam Bulmer | Audit | SS&A - Environmental Services and Assurance | N/A - No specific Milestone | Environment | N/C | N/C |  | N/A | Waste Exemptions | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
197 | Review of Handover Process | Review of implementation against written procedure, opportunities for improvement | 18.07.25 - BH New Item | C | No | Yes | SS&A - Environmental Services and Assurance | Line 2 - Corporate Functions | 2026-04-01 | 2026-06-30 |  | Stuart Woodings | Clare Proctor | Review | SS&A - Environmental Services and Assurance | N/A - No specific Milestone | Environment | N/C | N/C |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
198 | Review of compliance with Marine Licence conditions | Review of compliance with Marine Licence conditions. Permit readiness review | 18.07.25 - BH New Item | C | No | Yes | SS&A - Environmental Services and Assurance | Line 2 - Corporate Functions | 2026-04-01 | 2026-06-30 |  | Stuart Woodings | Stephen Roast | Review | SS&A - Environmental Services and Assurance | N/A - No specific Milestone | Environment | N/C | N/C |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
203 | Environment Contract Tracker | Review of updated tracker (Oracle Unifier) by Super Users to confirm suitability for Op Perm Team contracts | 18.07.25 - BH New Item | C | No | No | SS&A - Environmental Services and Assurance | Line 2 - Corporate Functions | 2026-04-01 | 2026-06-30 |  | Stuart Woodings | Emma Wells | Review | SS&A - Environmental Services and Assurance | N/A - No specific Milestone | Environment | N/C | N/C |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
206 | Q2 Environmental Management Review | Quarterly Management review | 18.07.25 - BH New Item | C | No | No | SS&A - Environmental Services and Assurance | Line 2 - Corporate Functions | 2026-04-01 | 2026-06-30 |  | Stuart Woodings | Emma Wells | Review | SS&A - Environmental Services and Assurance | N/A - No specific Milestone | Environment | N/C | N/C |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
212 | Review and updates to BAT Arrangements following HPC updates and SA | Review of HPCs self assessment and see what determine what can be implemented at SZC | 18.07.25 - BH New Item | C | No | No | SS&A - Environmental Services and Assurance | Line 2 - Corporate Functions | 2026-04-01 | 2026-06-30 |  | Stuart Woodings | Emma Wells | Review of Self Assessment | SS&A - Environmental Services and Assurance | N/A - No specific Milestone | Environment | N/C | N/C |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
240 | IR-54150 | Learning and decision making for design maturity | 02.09.25 JB - New item added. | R | Yes | No | External Review - ONR | Line 4 - External | 2026-04-22 | 2026-04-23 |  | Fran Gradie | Thomas Brazendale | Inspection | Technical | ONR Inspection on Design Maturity | Nuclear Safety Risk | N/C | N/C |  | LC 17, 19, 20 | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
42 | 12.4 - Performance Management | SZC-PEO-PRO-002, Create Roles, Competencies and Development Actions SZC-PEO-PRO-004, Enrol in Training SZC-PEO-PRO-001, Assess Individual Competency | 18.10.24 ACG - From PAP where procedures are Implemented and Published in IMS 10.04.25 FD: Added Level 2 ID Process Owner(s) name to column AU and added Procedure Lead Name(s) to column AT | C | No | No | SS&A - Quality Assurance | Line 2 - Corporate Functions | 2026-05-01 | 2026-06-30 |  | Fran Gradie | Vanessa Tsanang | Audit | Human Resources | N/A - No specific Milestone | People & Skills | N/C | N/C |  | LC6, LC12 & LC17 | N/A | N/A |  | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  | Faun | N/A | N/A | Rachel Kerry | Rachel Kerry | Human Resources | Internal IMS Audit | 12.0 - People | 12.4 - Performance Management | Create Roles, Competencies and Development Actions | SZC-PEO-PRO-002 | 7.2 | 7.2 | 7.2 |  |  | No
180 | Review of Impacts and Aspects Register (May) | 6 monthly review of the project impact and aspects register | 18.07.25 - BH New Item | C | No | No | SS&A - Environmental Services and Assurance | Line 2 - Corporate Functions | 2026-05-01 | 2026-07-26 |  | Stuart Woodings | Emma Wells | Review | SS&A - Environmental Services and Assurance | N/A - No specific Milestone | Environment | N/C | N/C |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
188 | 6 monthly review EMS/ESG KPIs | Review of performance against targets. 6 monthly | 18.07.25 - BH New Item | C | No | No | SS&A - Environmental Services and Assurance | Line 2 - Corporate Functions | 2026-05-04 | 2026-06-01 |  | Stuart Woodings | Sam Bulmer | Review | SS&A - Environmental Services and Assurance | N/A - No specific Milestone | Environment | N/C | N/C |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
25 | Care and Maintanance Programme functional assurance | Potential Regulatory Permission Point | 20.11.24 - TB: Update to link to C&M Holdpoint. 4.2.25 - Josh will be supporting Holdpoint review team. 3.4.25 FG - Please speak to Andrew Tom, to check on the assurance lines as Andrew would be interested in supporting. 1.5.25 FG: Might be opportunity for us to speak with the Audit team with Leon's support, to see what checks are required alongside the assocaited HoldPoint. Check MED Pack and relevant lines. 27.5.25 TB: MED areas need to be checked, bulk of evidence is not progressing as expected, change BRAG to Amber. End date may slip. FG: Vanessa and team to confirm the quality of evidence and look at sampling checks. 27.5.25 VT: We shall be supporting through the planned audit we have for Care and Maintanance Programme at start of June. 24.6.25 TB: Was July-Sept 25, however moved to Jan-Mar 26, following conversations with Andrew Kelleher, as the bulk of evidence won't be available till next year, this shouldn't pose any great risk. 17.10.25 TB: C&M is now likely to be May to June so moved it from Jan 2026. | A | No | No | SS&A - Nuclear Licence Compliance | Line 2 - Corporate Functions | 2026-05-05 | 2026-06-01 |  | Fran Gradie | Thomas Brazendale | Audit | Overall Project | Commence Equipment Care & Maintenance Hold Point | Nuclear Safety Risk | Amber | N/C |  | LC 28, 12 | N/A | 2.3.16 U1 - Equipment Care and Maintanance |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
193 | ISO14001 - SV1 | Surveillance visits SV1 | 18.07.25 - BH New Item 29.9.25 - AB - Updated from Peter Long, date is now May not June. - 18-22 May, then time for report. | R | No | Yes | External Review - LRQA | Line 4 - External | 2026-05-18 | 2026-05-29 |  | Stuart Woodings | Sam Bulmer | Audit | Overall Project | ISO 14001: Surveillance Audit | Environment | N/C | N/C |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
250 | ISO9001 SV2 | Surveillance visits SV2 | 29.9.25 - AB - Update from Peter Long new item. | R | No | Yes | External Review - LRQA | Line 4 - External | 2026-05-18 | 2026-05-29 |  | Fran Gradie | Christopher Thompson | Audit | Overall Project | ISO 9001 SV | Quality | N/C | N/C |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
241 | IR-54151 | Security and safeguards for construction sources to Site | 02.09.25 JB - New item added. | R | Yes | No | External Review - ONR | Line 4 - External | 2026-05-20 | 2026-05-21 |  | Fran Gradie | Thomas Brazendale | Inspection | SS&A - Security & Conventional Safety Assurance | ONR Security and Safeguards Inspection | Nuclear Safety Risk | N/C | N/C |  | FSyP 6 - Physical Protection systems | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
28 | 15.1 - Financial Planning & Forecasting | SZC-FIN-PRO-008, Forecast Monthly Cash Call SZC-FIN-PRO-013, Undertake Budget and Forecast Financial Planning | 18.10.24 ACG - From PAP where procedures are Implemented and Published in IMS 10.04.25 FD: Added Level 2 ID Process Owner(s) name to column AU and added Procedure Lead Name(s) to column AT 15.9.25 VT: Please remove from the plan, following on from latest update. | C | No | No | SS&A - Quality Assurance | Line 2 - Corporate Functions | 2026-06-01 | 2026-08-30 |  | Fran Gradie | Vanessa Tsanang | Audit | Finance | N/A - No specific Milestone | Quality | N/C | N/C |  | LC6 & LC17 | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  | Camila | Vanessa (support) | N/A | James Weeks | James Weeks | Finance & Investor Relations | Internal IMS Audit | 15.0 - Finance & Accounting | 15.1 - Financial Planning & Forecasting | Forecast Monthly Cash Call Undertake Budget and Forecast Financial Planning | SZC-FIN-PRO-008 SZC-FIN-PRO-013 | 8.1 |  |  |  |  | Yes
163 | Q3 CWA - Quarterly Review Environmental Assurance Activities | Look at assurance program, targeted/reactive inspections, significance of outcome, follow up of actions | 18.07.25 - BH New Item | C | No | No | SS&A - Environmental Services and Assurance | Line 2 - Corporate Functions | 2026-07-01 | 2026-09-30 |  | Stuart Woodings | Sam Bulmer | Review | SS&A - Environmental Services and Assurance | N/A - No specific Milestone | Environment | N/C |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
167 | Q3 - Critical Environmental Documentation Review | Quarterly review of CEMP/SWMP/RAMS | 18.07.25 - BH New Item | C | No | No | SS&A - Environmental Services and Assurance | Line 2 - Corporate Functions | 2026-07-01 | 2026-09-30 |  | Stuart Woodings | Sam Bulmer | Review | SS&A - Environmental Services and Assurance | N/A - No specific Milestone | Environment | N/C | N/C |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
171 | Q3 Review of environmental monitoring data, incidents and actions | Collaborative review of specialist environmental monitoring data, environmental incidents and open actions | 18.07.25 - BH New Item | C | No | No | SS&A - Environmental Services and Assurance | Line 2 - Corporate Functions | 2026-07-01 | 2026-09-30 |  | Stuart Woodings | Sam Bulmer | Review | SS&A - Environmental Services and Assurance | N/A - No specific Milestone | Environment | N/C | N/C |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
178 | Q3 SME Input into Procurement | Review of SME input in procurement space. Review of tracker, look at gaps where environment management SME not involved in certain tender review | 18.07.25 - BH New Item | C | No | No | SS&A - Environmental Services and Assurance | Line 2 - Corporate Functions | 2026-07-01 | 2026-09-30 |  | Stuart Woodings | Sam Bulmer | Review | SS&A - Environmental Services and Assurance | N/A - No specific Milestone | Environment | N/C | N/C |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
184 | Effectiveness of actions raised in assurance activities, following incidents and investigations. | Self assessment of actions raised, how effective they are against the issue/ NC etc originally raised. | 18.07.25 - BH New Item | C | No | No | SS&A - Environmental Services and Assurance | Line 2 - Corporate Functions | 2026-07-01 | 2026-09-30 |  | Stuart Woodings | Sam Bulmer | Self Assessment | SS&A - Environmental Services and Assurance | N/A - No specific Milestone | Environment | N/C | N/C |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
186 | Dust Management Review | Review into dust management, compliance with legislation, SZC procedure, look at community complants and how these have been dealt with. SS&A HSW team will support the review. | 18.07.25 - BH New Item 23.10.25 - AB/SM: Please can HSW Team dock-in to this review please (From Stephen Mason), so Env to lead and HSW will look to play a part where neccesary. Changed assuring function to SS&A - Combined Line 2 team. | B | No | Yes | SS&A - Combined Line 2 Team | Line 2 - Corporate Functions | 2026-07-01 | 2026-09-30 |  | Stuart Woodings | Sam Bulmer | Review | Delivery - Site Programme | N/A - No specific Milestone | Environment | N/C | N/C |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
190 | Review - TEMP Terrestial Ecological Management Plan | Document updated review looking at implementation site wide | 18.07.25 - BH New Item | C | No | Yes | SS&A - Environmental Services and Assurance | Line 2 - Corporate Functions | 2026-07-01 | 2026-09-30 |  | Stuart Woodings | Sam Bulmer | Review | SS&A - Environmental Services and Assurance | N/A - No specific Milestone | Environment | N/C | N/C |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
195 | Audit Wickham Park and Ride | Audit- against legal, SZC document, best environmental practice. SS&A HSW Team will support this Audit. | 18.07.25 - BH New Item 23.10.25 - AB/SM: Please can HSW Team dock-in to this review please (From Stephen Mason), so Env to lead and HSW will look to play a part where neccesary. Changed assuring function to SS&A - Combined Line 2 team. | B | No | Yes | SS&A - Combined Line 2 Team | Line 2 - Corporate Functions | 2026-07-01 | 2026-09-30 |  | Stuart Woodings | Sam Bulmer | Audit | SS&A - Environmental Services and Assurance | Darsham Park & Ride (NPR) - Completion of Works (L3 Reporting Milestone) | Environment | N/C | N/C |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
199 | Review of Shipping requirements | review of legal and shipping routes requirements, in particular relation to red throated divers | 18.07.25 - BH New Item | C | No | No | SS&A - Environmental Services and Assurance | Line 2 - Corporate Functions | 2026-07-01 | 2026-09-30 |  | Stuart Woodings | Stephen Roast | Review | SS&A - Environmental Services and Assurance | N/A - No specific Milestone | Environment | N/C | N/C |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
200 | Review and update of ERC arrangements including ERC and BAT training | Environmental Rank Categoriser arrangements, resources available, training | 18.07.25 - BH New Item | C | No | No | SS&A - Environmental Services and Assurance | Line 2 - Corporate Functions | 2026-07-01 | 2026-09-30 |  | Stuart Woodings | Emma Wells | Review | SS&A - Environmental Services and Assurance | N/A - No specific Milestone | Environment | N/C | N/C |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
201 | WDA/CA Permit Compliance | Review to confirm continued suitability | 18.07.25 - BH New Item | C | No | Yes | SS&A - Environmental Services and Assurance | Line 2 - Corporate Functions | 2026-07-01 | 2026-09-30 |  | Stuart Woodings | Emma Wells | Review | SS&A - Environmental Services and Assurance | N/A - No specific Milestone | Environment | N/C | N/C |  | N/A | Waste Permit Operation | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
204 | F-gas Surveillance | Surveillance of SZ3001 and other F-Gas containing contracts to ensure alignment with Environmental initiatives (following TDF Technical Direction Forum) | 18.07.25 - BH New Item | C | No | Yes | SS&A - Environmental Services and Assurance | Line 2 - Corporate Functions | 2026-07-01 | 2026-09-30 |  | Stuart Woodings | Emma Wells | Surveillance | SS&A - Environmental Services and Assurance | N/A - No specific Milestone | Environment | N/C | N/C |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
207 | Q3 Environmental Management Review | Quarterly Management review | 18.07.25 - BH New Item | C | No | No | SS&A - Environmental Services and Assurance | Line 2 - Corporate Functions | 2026-07-01 | 2026-09-30 |  | Stuart Woodings | Emma Wells | Review | SS&A - Environmental Services and Assurance | N/A - No specific Milestone | Environment | N/C | N/C |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
209 | Update resource profile |  | 18.07.25 - BH New Item | C | No | No | SS&A - Environmental Services and Assurance | Line 2 - Corporate Functions | 2026-07-01 | 2026-09-30 |  | Stuart Woodings | Emma Wells | Review | SS&A - Environmental Services and Assurance | N/A - No specific Milestone | Environment | N/C | N/C |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
210 | Biofouling | Regulatory focused, plans, permit variation stratagy | 18.07.25 - BH New Item | C | No | No | SS&A - Environmental Services and Assurance | Line 2 - Corporate Functions | 2026-07-01 | 2026-09-30 |  | Stuart Woodings | Emma Wells | Surveillance | SS&A - Environmental Services and Assurance | N/A - No specific Milestone | Environment | N/C | N/C |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
211 | Develop BAT L3 training and upload to MLH | Establish BAT L3 training | 18.07.25 - BH New Item | C | No | No | SS&A - Environmental Services and Assurance | Line 2 - Corporate Functions | 2026-07-01 | 2026-09-30 |  | Stuart Woodings | Emma Wells | Review | SS&A - Environmental Services and Assurance | N/A - No specific Milestone | Environment | N/C | N/C |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
242 | IR-54152 | Governance and internal challenge for delivery of adequete safety documentation | 02.09.25 JB - New item added. | R | Yes | No | External Review - ONR | Line 4 - External | 2026-07-28 | 2026-07-29 |  | Fran Gradie | Thomas Brazendale | Inspection | Technical | ONR Inspection on Governance and Internal Challenge | Nuclear Safety Risk | N/C | N/C |  | LC 14, 17 | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
221 | Audit - Commence Permenant Sea Defence | Audit- against legal, SZC document, best environmental practice | 18.07.25 - BH New Item 5.9.25 - AB - Can you check with Sam/Stephen on this one, as Stephen thinks the Permanent sea defence will be the other side of 2030. | C | No | Yes | SS&A - Environmental Services and Assurance | Line 2 - Corporate Functions | 2026-08-01 | 2026-09-01 |  | Stuart Woodings | Stephen Roast/Sam Bulmer | Audit | SS&A - Environmental Services and Assurance | Commence Permanent Sea Defence | Environment | N/C | N/C |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
256 | Review of effectiveness of Org Learning Screening meetings 2025/2026 | Review of effectiveness of Org Learning Screening meetings including review of coding accuracy. Structure of Screening meetings is under review & coding is being refreshed - check to ensure funtioning as required | 8.10.25: CE: Added new line for 2025/2026. | C | No | No | SS&A - Performance Improvement | Line 2 - Corporate Functions | 2026-08-01 | 2026-09-30 |  | Fran Gradie | Hilary Best | Review | Overall Project | N/A - No specific Milestone | Quality | N/C | N/C |  | LC 7 | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
253 | ISO 45001 Surveillance Visit 2 (date to be confirmed after SV1). | ISO 45001 assurance requirements 2nd Surveillance Audit | PL 29.9.25: New line added. | R | No | Yes | External Review - LRQA | Line 4 - External | 2026-08-03 | 2026-08-06 |  | Andrew Wilkinson | Stephen Mason | Audit | Overall Project | ISO 45001 Certification | Health, Safety & Wellbeing | N/C | N/C |  | LC17 | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
243 | IR-54153 | Control of work - Single permit system at Site | 02.09.25 JB - New item added. 23.10.25 AB - SS&A HSW Team say they will look to support Site Delivery with this one where neccesary. | R | Yes | Yes | External Review - ONR | Line 4 - External | 2026-08-26 | 2026-08-27 |  | Fran Gradie | Thomas Brazendale | Inspection | Delivery - Site Programme | ONR Inspection on control of work | Health, Safety & Wellbeing | N/C | N/C |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
21 | Safety Culture Assesment | Safety Culture assessment for Sizewell C. Linked to Risk number 843: Failure to establish and maintain a project culture that aligns with SZC Values and Behaviours. SS&A HSW Team to support (Steve Mason). | 16.1.25 KAC - Should have dates firmed up in next month or so. 04.3.25 KAC - Date will possibly move forward, will report back next month on this. 3.4.25 KAC: Workshop to present tools on 23/4, we shall then decide on tool from that point onwards. 1.5.25 KAC: survey - Currently beta testing the ONR tools to support its development. tool should be ready soon - the tool is being presented to the SDF directly for a top down approach to engaging organisations. 24.6.25 KAC: Was due to start in July, pushed back to September owing to further conversations on the tool with Alan Feakins and other information. 14.8.25 KAC: Spoken with Alan, we've set-up a group to include all relevant stakeholdes and commitments to run a survey in 2026. Was due to start in Sept this year, but please push back to next year. 10.9.25 KAC: Spoke with Alan on 2nd September and our new timeline aligns with objectives on the Health and Wellbeing Strategy. 23.10.25 AB: Steve Mason and HSW team would like to support this and be kept informed, so whilst happy to support from a collaborative perspective, Culture would still lead on it. | B | Yes | No | SS&A - Combined Line 2 Team | Line 2 - Corporate Functions | 2026-09-01 | 2026-12-31 |  | Fran Gradie | Katie Anderson-Cousins | Assessment | Overall Project | N/A - No specific Milestone | Health, Safety & Wellbeing | N/C | N/C |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
59 | 8.1 - Compliance Requirements Management | SZC-ACQ-PRO-002, Maintain Legislation & Regulatory Landscape SZC-ACQ-PRO-007,Control of Licensed Site Property Transactions SZC-ACQ-PRO-008, Control Regulatory Approved Management Arrangements SZC-ACQ-PRO-012, Manage Change To Development Consent Order and Deed of Obligation SZC-ACQ-PRO-015, Manage Interfaces with Regulators SZC-ACQ-PRO-030,Manage Discharge Of Development Consent Order Requirements, Deemed Marine Licence Conditions and Deed of Obligation Requirements Note ONE other procedure not Published in IMS at time of planning, this is Define Manage and Release Tertiary Hold Points - No number at time of planning 31/10/2024 | 18.10.24 ACG - From PAP where procedures are Implemented and Published in IMS 10.04.25 FD: Added Level 2 ID Process Owner(s) name to column AU and added Procedure Lead Name(s) to column AT | C | No | No | SS&A - Quality Assurance | Line 2 - Corporate Functions | 2026-09-01 | 2026-12-30 |  | Fran Gradie | Vanessa Tsanang | Audit | Legal | N/A - No specific Milestone | Reputation & Social License | N/C | N/C |  | LC6 LC17 | N/A | N/A |  | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  | Vanessa | N/A | N/A | Christopher Nunn Richard Bull Lynne Kellett Fran Gradie | Thomas Brazendale | Safety, Security and Assurance | Internal IMS Audit | 8.0 - Assurance, Compliance & Quality | 8.1 - Compliance Requirements Management | Control of Licensed Site Property Transactions Manage Change To Development Consent Order and Deed of Obligation Manage Discharge Of Development Consent Order Requirements, Deemed Marine Licence Conditions and Deed of Obligation Requirements Maintain Legislation & Regulatory Landscape Control Regulatory Approved Management Arrangements Manage Interfaces with Regulators Define Manage and Release Tertiary Hold Points | SZC-ACQ-PRO-007 SZC-ACQ-PRO-012 SZC-ACQ-PRO-030 SZC-ACQ-PRO-002 SZC-ACQ-PRO-008 SZC-ACQ-PRO-015 SZC-PMC-PRO-002 | 8.5.1 8.2.1 8.2.2 4.1 8.1 8.2.3 | 8.1 6.1.3 6.1.1 6.1.2 6.1.3 6.1.4 7.4.1 7.4.2 7.4.3 | 8.1.1 6.1.3 8.1.3 5.4 7.4.1 8.1 |  |  | No
164 | Q4 CWA - Quarterly Review Environmental Assurance Activities | Look at assurance program, targeted/reactive inspections, significance of outcome, follow up of actions | 18.07.25 - BH New Item | C | No | No | SS&A - Environmental Services and Assurance | Line 2 - Corporate Functions | 2026-10-01 | 2026-12-31 |  | Stuart Woodings | Sam Bulmer | Review | SS&A - Environmental Services and Assurance | N/A - No specific Milestone | Environment | N/C | N/C |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
168 | Q4 - Critical Environmental Documentation Review | Quarterly review of CEMP/SWMP/RAMS | 18.07.25 - BH New Item | C | No | No | SS&A - Environmental Services and Assurance | Line 2 - Corporate Functions | 2026-10-01 | 2026-12-31 |  | Stuart Woodings | Sam Bulmer | Review | SS&A - Environmental Services and Assurance | N/A - No specific Milestone | Environment | N/C | N/C |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
172 | Q4 Review of environmental monitoring data, incidents and actions | Collaborative review of specialist environmental monitoring data, environmental incidents and open actions | 18.07.25 - BH New Item | C | No | No | SS&A - Environmental Services and Assurance | Line 2 - Corporate Functions | 2026-10-01 | 2026-12-31 |  | Stuart Woodings | Sam Bulmer | Review | SS&A - Environmental Services and Assurance | N/A - No specific Milestone | Environment | N/C | N/C |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
179 | Q4 SME Input into Procurement | Review of SME input in procurement space. Review of tracker, look at gaps where environment management SME not involved in certain tender review | 18.07.25 - BH New Item | C | No | No | SS&A - Environmental Services and Assurance | Line 2 - Corporate Functions | 2026-10-01 | 2026-12-31 |  | Stuart Woodings | Sam Bulmer | Review | SS&A - Environmental Services and Assurance | N/A - No specific Milestone | Environment | N/C | N/C |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
187 | Non-road Mobile Machinery NRMM | Review against targets set | 18.07.25 - BH New Item | C | No | Yes | SS&A - Environmental Services and Assurance | Line 2 - Corporate Functions | 2026-10-01 | 2026-12-31 |  | Stuart Woodings | Sam Bulmer | Review | SS&A - Environmental Services and Assurance | N/A - No specific Milestone | Environment | N/C | N/C |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
196 | Compliance with site water permits and DCO requirements | Review of compliance against water permits and DCO requirements | 18.07.25 - BH New Item | C | No | Yes | SS&A - Environmental Services and Assurance | Line 2 - Corporate Functions | 2026-10-01 | 2026-12-31 |  | Stuart Woodings | Clare Proctor | Review | SS&A - Environmental Services and Assurance | N/A - No specific Milestone | Environment | N/C | N/C |  | N/A | Water Resources Abstraction Licence - for the abstraction of water during construction | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
202 | Operational Permit Procedure Review | Review of the Operations Permit Procedure , opportunities for improvement | 18.07.25 - BH New Item | C | No | No | SS&A - Environmental Services and Assurance | Line 2 - Corporate Functions | 2026-10-01 | 2026-12-31 |  | Stuart Woodings | Emma Wells | Review | SS&A - Environmental Services and Assurance | N/A - No specific Milestone | Environment | N/C | N/C |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
208 | Q4 Environmental Management Review | Quarterly Management review | 18.07.25 - BH New Item | C | No | No | SS&A - Environmental Services and Assurance | Line 2 - Corporate Functions | 2026-10-01 | 2026-12-31 |  | Stuart Woodings | Emma Wells | Review | SS&A - Environmental Services and Assurance | N/A - No specific Milestone | Environment | N/C | N/C |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
213 | Placeholder - COMAH | review of COMAH requirements. HPC review and lessons learnt | 18.07.25 - BH New Item | C | No | No | SS&A - Environmental Services and Assurance | Line 2 - Corporate Functions | 2026-10-01 | 2026-12-31 |  | Stuart Woodings | Emma Wells | Review | SS&A - Environmental Services and Assurance | N/A - No specific Milestone | Environment | N/C | N/C |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
216 | Review of contractors risk management in a programmes | Review of contractors risk management in a programmes | 18.07.25 - BH New Item | C | No | No | SS&A - Environmental Services and Assurance | Line 2 - Corporate Functions | 2026-10-01 | 2026-12-31 |  | Stuart Woodings | Emma Wells | Review | SS&A - Environmental Services and Assurance | N/A - No specific Milestone | Environment | N/C | N/C |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
252 | ISO 27001 (Cybersecurity - Information Security) - SV1 | ISO 27001 assurance requirements Assures against: • SZC Statement of Applicability for ISO 27001:2022 ISMS • SZC Controls Framework SV1 | 29.9.25 PL - New line added. | R | Yes | Yes | External Review - LRQA | Line 4 - External | 2026-10-26 | 2026-10-30 |  | Andrew Wilkinson | James Costello | Audit | Overall Project | ISO 27001 SV1 | Cyber security | N/C | N/C |  | LC17 | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
244 | IR-54155 | Internal challenge and decision making for adequete safety, security and safeguards compliance at governance meetings up to and including the Board | 02.09.25 JB - New item added. | R | Yes | No | External Review - ONR | Line 4 - External | 2026-10-27 | 2026-10-28 |  | Fran Gradie | Thomas Brazendale | Inspection | Legal | ONR Inspection on Internal Challenge and Decision making | Nuclear Safety Risk | N/C | N/C |  | LC 17 | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
181 | Review of Impacts and Aspects Register (Nov) | 6 monthly review of the project impact and aspects register | 18.07.25 - BH New Item | C | No | No | SS&A - Environmental Services and Assurance | Line 2 - Corporate Functions | 2026-11-02 | 2026-12-18 |  | Stuart Woodings | Emma Wells | Review | SS&A - Environmental Services and Assurance | N/A - No specific Milestone | Environment | N/C | N/C |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
189 | 6 monthly review EMS/ESG KPIs | Review of performance against targets. 6 monthly | 18.07.25 - BH New Item | C | No | No | SS&A - Environmental Services and Assurance | Line 2 - Corporate Functions | 2026-11-02 | 2026-12-07 |  | Stuart Woodings | Sam Bulmer | Review | SS&A - Environmental Services and Assurance | N/A - No specific Milestone | Environment | N/C | N/C |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
245 | IR-54156 | Readiness inspection ahead of handover of rail line construction regulation to HSE | 02.09.25 JB - New item added. | R | Yes | Yes | External Review - ONR | Line 4 - External | 2026-11-24 | 2026-11-25 |  | Fran Gradie | Thomas Brazendale | Inspection | Delivery - Site Programme | ONR Inspection on handover of Rail line | Health, Safety & Wellbeing | N/C | N/C |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
194 | ISO14001 - SV2 | SV2 | 18.07.25 - BH New Item 29.9.25 - AB - Update from Peter Long, date is now end of Nov, rather than mid-Nov - actual audit scheduled for 18th Nov - 4th Dec, with time left for report. | R | No | Yes | External Review - LRQA | Line 4 - External | 2026-11-30 | 2026-12-04 |  | Stuart Woodings | Sam Bulmer | Audit | Overall Project | ISO 14001 SV | Environment | N/C | N/C |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
251 | ISO9001 SV3 | Surveillance visits SV3 | 29.9.25 - AB - Update from Peter Long new item. | R | No | Yes | External Review - LRQA | Line 4 - External | 2026-11-30 | 2026-12-04 |  | Fran Gradie | Christopher Thompson | Audit | Overall Project | ISO 9001 SV | Quality | N/C | N/C |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
220 | Hold Point - Concrete Pour Capability Demonstration | Review of environmental requirements for the release of this hold point. Hold point manager Jeremy Davis | 18.07.25 - BH New Item | B | No | No | SS&A - Environmental Services and Assurance | Line 2 - Corporate Functions | 2026-12-01 | 2026-12-01 |  | Stuart Woodings | Sam Bulmer | Review | SS&A - Environmental Services and Assurance | Unit 1 Concrete Batch commissioning | Environment | N/C | N/C |  | N/A | N/A | 2.0.2 U1 - Concrete pour capability demonstration |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
49 | 9.3 - Planning & Schedule Management | SZC-PMC-PRO-006, Manage Project Schedule | 18.10.24 ACG - From PAP where procedures are Implemented and Published in IMS 10.04.25 FD: Added Level 2 ID Process Owner(s) name to column AU and added Procedure Lead Name(s) to column AT | C | No | No | SS&A - Quality Assurance | Line 2 - Corporate Functions | 2027-01-14 | 2027-03-15 |  | Fran Gradie | Vanessa Tsanang | Audit | Delivery - Delivery/PDO | N/A - No specific Milestone | Productivity | N/C | N/C |  | LC6 LC17 | N/A | N/A |  | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  | Adrian | N/A | N/A | Tommy Clarke | Tommy Clarke | PMO | Internal IMS Audit | 9.0 - Project Management & Controls | 9.3 - Planning & Schedule Management | Manage Project Schedule | SZC-PMC-PRO-006 | 8.1 |  |  |  |  | No
246 | IR-54157 | Supply chain management for Asset care | 02.09.25 JB - New item added. | R | Yes | No | External Review - ONR | Line 4 - External | 2027-01-19 | 2027-01-20 |  | Fran Gradie | Thomas Brazendale | Inspection | Delivery - NI Programme | ONR Supply Chain Management Inspection | Nuclear Safety Risk | N/C | N/C |  | LC 28, 17 | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
247 | IR-54158 | Construction fire safety and emergency arrangements | 02.09.25 JB - New item added. | R | Yes | Yes | External Review - ONR | Line 4 - External | 2027-02-23 | 2027-02-24 |  | Fran Gradie | Thomas Brazendale | Inspection | Delivery - Site Programme | ONR Construction Fire Safety & Emergency Arrangements | Health, Safety & Wellbeing | N/C | N/C |  | LC 11 | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
260 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
261 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
262 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
263 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
264 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
265 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
266 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
267 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
268 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
269 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
270 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
271 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
272 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
273 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
274 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
275 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
276 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
277 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
278 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
279 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
280 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
281 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
282 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
283 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
284 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
285 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
286 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
287 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
288 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
289 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
290 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
291 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
292 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
293 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
294 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
295 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
296 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
297 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
298 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
299 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
300 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
301 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
302 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
303 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
304 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
305 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
306 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
307 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
308 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
309 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
310 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
311 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
312 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
313 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
314 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
315 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
316 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
317 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
318 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
319 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
320 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
321 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
322 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
323 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
324 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
325 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
326 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
327 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
328 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
329 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
330 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
331 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
332 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
333 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
334 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
335 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
336 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
337 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
338 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
339 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
340 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
341 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
342 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
343 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
344 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
345 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
346 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
347 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
348 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
349 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
350 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
351 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
352 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
353 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
354 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
355 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
356 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
357 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
358 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
359 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
360 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
361 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
362 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
363 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
364 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
365 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
366 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
367 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
368 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
369 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
370 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
371 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
372 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
373 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
374 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
375 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
376 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
377 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
378 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
379 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
380 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
381 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
382 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
383 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
384 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
385 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
386 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
387 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
388 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
389 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
390 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
391 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
392 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
393 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
394 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
395 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
396 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
397 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
398 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
399 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
400 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
401 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
402 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
403 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
404 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
405 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
406 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
407 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
408 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
409 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
410 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
411 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
412 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
413 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
414 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
415 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
416 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
417 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
418 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
419 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
420 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
421 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
422 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
423 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
424 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
425 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
426 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
427 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
428 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
429 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
430 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
431 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
432 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
433 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
434 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
435 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
436 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
437 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
438 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
439 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
440 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
441 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
442 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
443 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
444 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
445 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
446 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
447 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
448 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
449 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
450 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
451 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
452 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
453 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
454 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
455 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
456 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
457 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
458 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
459 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
460 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
461 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
462 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
463 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
464 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
465 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
466 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
467 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
468 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
469 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
470 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
471 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
472 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
473 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
474 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
475 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
476 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
477 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
478 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
479 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
480 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
481 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
482 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
483 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
484 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
485 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
486 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
487 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
488 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
489 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
490 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
491 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
492 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
493 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
494 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
495 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
496 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
497 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
498 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
499 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
500 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
501 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
502 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
503 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
504 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
505 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
506 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
507 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
508 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
509 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
510 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
511 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
512 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
513 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
514 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
515 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
516 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
517 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
518 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
519 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
520 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
521 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
522 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
523 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
524 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
525 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
526 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
527 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
528 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
529 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
530 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
531 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
532 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
533 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
534 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
535 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
536 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
537 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
538 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
539 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
540 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
541 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
542 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
543 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
544 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
545 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
546 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
547 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
548 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
549 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
550 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
551 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
552 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
553 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
554 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
555 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
556 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
557 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
558 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
559 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
560 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
561 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
562 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
563 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
564 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
565 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
566 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
567 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
568 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
569 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
570 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
571 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
572 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
573 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
574 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
575 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
576 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
577 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
578 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
579 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
580 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
581 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
582 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
583 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
584 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
585 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
586 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
587 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
588 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
589 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
590 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
591 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
592 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
593 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
594 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
595 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
596 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
597 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
598 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
599 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
600 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
601 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
602 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
603 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
604 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
605 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
606 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
607 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
608 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
609 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
610 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
611 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
612 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
613 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
614 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
615 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
616 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
617 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
618 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
619 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
620 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
621 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
622 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
623 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
624 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
625 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
626 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
627 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
628 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
629 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
630 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
631 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
632 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
633 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
634 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
635 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
636 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
637 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
638 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
639 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
640 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
641 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
642 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
643 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
644 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
645 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
646 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
647 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
648 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
649 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
650 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
651 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
652 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
653 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
654 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
655 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
656 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
657 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
658 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
659 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
660 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
661 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
662 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
663 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
664 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
665 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
666 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
667 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
668 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
669 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
670 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
671 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
672 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
673 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
674 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
675 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
676 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
677 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
678 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
679 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
680 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
681 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
682 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
683 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
684 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
685 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
686 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
687 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
688 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
689 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
690 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
691 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
692 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
693 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
694 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
695 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
696 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
697 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
698 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
699 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
700 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
701 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
702 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
703 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
704 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
705 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
706 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
707 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
708 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
709 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
710 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
711 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
712 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
713 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
714 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
715 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
716 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
717 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
718 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
719 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
720 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
721 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
722 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
723 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
724 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
725 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
726 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
727 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
728 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
729 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
730 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
731 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
732 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
733 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
734 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
735 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
736 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
737 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
738 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
739 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
740 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
741 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
742 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
743 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
744 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
745 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
746 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
747 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
748 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
749 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
750 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
751 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
752 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
753 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
754 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
755 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
756 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
757 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
758 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
759 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
760 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
761 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
762 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
763 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
764 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
765 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
766 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
767 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
768 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
769 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
770 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
771 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
772 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
773 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
774 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
775 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
776 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
777 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
778 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
779 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
780 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
781 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
782 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
783 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
784 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
785 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
786 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
787 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
788 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
789 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
790 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
791 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
792 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
793 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
794 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
795 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
796 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
797 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
798 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
799 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
800 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
801 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
802 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
803 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
804 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
805 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
806 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
807 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
808 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
809 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
810 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
811 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
812 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
813 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
814 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
815 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
816 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
817 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
818 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
819 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
820 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
821 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
822 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
823 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
824 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
825 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
826 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
827 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
828 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
829 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
830 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
831 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
832 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
833 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
834 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
835 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
836 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
837 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
838 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
839 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
840 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
841 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
842 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
843 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
844 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
845 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
846 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
847 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
848 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
849 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
850 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
851 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
852 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
853 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
854 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
855 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
856 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
857 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
858 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
859 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
860 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
861 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
862 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
863 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
864 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
865 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
866 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
867 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
868 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
869 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
870 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
871 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
872 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
873 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
874 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
875 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
876 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
877 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
878 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
879 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
880 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
881 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
882 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
883 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
884 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
885 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
886 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
887 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
888 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
889 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
890 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
891 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
892 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
893 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
894 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
895 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
896 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
897 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
898 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
899 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
900 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
901 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
902 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
903 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
904 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
905 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
906 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
907 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
908 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
909 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
910 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
911 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
912 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
913 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
914 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
915 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
916 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
917 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
918 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
919 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
920 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
921 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
922 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
923 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
924 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
925 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
926 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
927 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
928 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
929 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
930 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
931 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
932 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
933 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
934 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
935 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
936 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
937 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
938 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
939 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
940 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
941 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
942 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
943 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
944 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
945 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
946 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
947 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
948 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
949 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
950 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
951 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
952 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
953 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
954 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
955 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
956 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
957 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
958 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
959 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
960 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
961 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
962 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
963 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
964 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
965 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
966 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
967 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
968 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
969 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
970 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
971 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
972 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
973 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
974 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
975 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
976 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
977 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
978 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
979 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
980 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
981 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
982 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
983 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
984 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
985 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
986 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
987 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
988 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
989 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
990 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
991 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
992 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
993 |  |  |  |  | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | No or N/A |  |  |  | N/A | [13 empty] | No
[5 empty] | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A
[5 empty] | No | [10 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A
[16 empty] | N/A - No specific Milestone |  |  |  |  | N/A | N/A | N/A
Formulas:
Planned End Date / Report published = Table7[[#This Row],[Planned Start Date ]]+60
Actual End Date = Table7[[#This Row],[Planned Start Date ]]+60
Note on F21: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Alex Boyce we have draft findings but not finalised so they are subject to change? Camila is thus reluctant to add the numbers?
Note on P25: Sam Bulmer: Support: Russell Grinham
Note on C32: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: New line / audit added
Note on G32: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Checked with VT, we have altered to a Cat C.
Note on C33: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: Requiring Auditor support Reply: @Fran Gradie
Note on P34: Sam Bulmer: Support - Rebecca Hudson
Note on P39: Sam Bulmer: Support - Rebecca Hudson
Note on P41: Sam Bulmer: Support - Rebecca Hudson
Note on E43: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Manage Design Open Point AUD-1260 Aug 2023. Reply: Manage Design Change are a favourite of LRQA during ISO9001 audits.
Note on F43: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Alex Boyce see new comment
Note on E45: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: Hi @Thomas Brazendale do we know what the 7 areas were? Reply: @Thomas Brazendale should we be doing some ‘pre-assurance’ before this date so there's no surprises? Reply: Marta and Jonathan Jones supporting the inspection.
Note on M46: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: PL: this planning refers to the 5 audit person days (field work) plus the time for the report to be released.
Note on S46: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: PL: Query: Why there is not an milestone to achieve the stage 2? Reply: @Camila Casagrande Zanaga one for Stage 2 has not been set to date from my knowledge, something that PL could discuss with Chris / ESG perhaps.
Note on M49: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Paul Gomar have now adjusted the dates, this would mean it concludes, this month, please can you check the end date to see if this matches your expectations as you said to put both this and the one further below down for 6 months rather than full year?
Note on E51: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: PL: Stage 1 and Stage 2 of the ISO 27001 separated in the ID 132 and 133.
Note on M51: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: PL: This due date refers to the field work completed plus the time for release the audit report
Note on P53: Sam Bulmer: Support: Hannah Dixon (lead aduitor) and Rebecca Hudson
Note on E54: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Procedures in Red currently authored by Peter Long thus must be audited, approved and reviewed by others. Reply: Conduct Supply Chain Audit done in November 2023 (AUD-1461) Reply: Site nonconformances check move from CCIS to Switch. FCR check utilisation of field view and roll out of mobile devices
Note on M55: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: PL: this planning refers to 3 audit person days (field work) plus the release of the report.
Note on P55: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Also speak to Sam Parker.
Note on O57: Sam Bulmer: Support: Carly Merrett
Note on P57: Sam Bulmer: Support: Carly Merrett
Note on F59: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Alex Boyce date in principle agreed
Note on I66: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Not expected to be at site but we haven't received the report yet.
Note on F67: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Ella Jeffrey please can you check the RAG with Carly for the outcome for this one, thanks Alex.
Note on O67: Sam Bulmer: Support: Carly Merrett
Note on P67: Sam Bulmer: Support: Carly Merrett
Note on E70: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: AUD-1273 Aug 2023
Note on M76: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Peter Long: Field works ends on 05/06, and the report is expected in 2 weeks maximum.
Note on M77: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Peter Long: Field works ends on 05/06, and the report is expected in 2 weeks maximum.
Note on O77: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Support: Carly Merrett
Note on P77: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Support: Carly Merrett
Note on AW81: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Alex Boyce, this has been changed to an “informal audit” No report etc etc. Just as prep for ISO45001 external audit.
Note on F82: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Alex Boyce, date confirmed Reply: @Alex Boyce all updated Reply: Thanks @Adrian Green , I noticed actual end date was blank so put down today’s date, but please edit if that’s not right (so long as it’s a date in July).
Note on AX82: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Alex Boyce & @Vanessa Tsanang This was changed recently to 3.0 should I change in this tracker? Reply: @Adrian Green yes please
Note on P83: Sam Bulmer: Support: Carly Merrett
Note on O84: Sam Bulmer: Support - Rebecca Hudson
Note on P84: Sam Bulmer: Support - Rebecca Hudson
Note on O85: Sam Bulmer: Support: Russell Grinham & Stephen Roast
Note on P85: Sam Bulmer: Support: Russell Grinham & Stephen Roast
Note on O86: Sam Bulmer: Support - Rebecca Hudson
Note on P86: Sam Bulmer: Support - Rebecca Hudson
Note on M90: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Adrian Green we have made this a 90 day activity as we wish to increase the scope, Camila will be supported by Don and others.
Note on E91: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Procedures in Red currently authored by Peter Long thus must be audited, approved and reviewed by others. Reply: Conduct Supply Chain Audit done in November 2023 (AUD-1461) Reply: Site nonconformances check move from CCIS to Switch. FCR check utilisation of field view and roll out of mobile devices
Note on M92: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: PL: this planning refers to 7 audit person days (field work) plus the release of the report. Reply: Will now be 17 person days, taking into account additional auditors owing to the increase in our organisational headcount and a few other factors.
Note on P92: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Also, speak to Sam Parker.
Note on C93: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: To be moved (start date) to 1st July, @Fran Gradie to pick up with @Stuart Woodings see activity 97 - Hold point prep: Marine Beach Landing facility under Sam Bulmer. Reply: I have updated Adrian Green.
Note on E93: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: SZC-ACQ-PRO-029, Manage Environmental Objectives was previously 8.2 (Assurance), now sits within 6.4 - Environmental & Sustainability.
Note on F93: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Alex Boyce updated dates see notes Reply: @Alex Boyce report will be published today, tracker updated. Findings into Insight maybe after I return from annual leave. Reply: @Alex Boyce also added team centre number with approved report in pdf and word formats.
Note on Y93: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Alex Boyce this will cover many permits, how do I select multiple options? Reply: If we are talking Environmental Permits, Is the activity directly linked to an Environmental permit, as my instruction from Stuart when adding this column was that it should be the key one shown here. Reply: @Adrian Green can you check with Sam Bulmer please?
Note on P95: Sam Bulmer: Support: Russell Grinham & Stephen Roast
Note on O96: Sam Bulmer: Support - Rebecca Hudson
Note on P96: Sam Bulmer: Support - Rebecca Hudson
Note on O98: Sam Bulmer: Support: Carly Merrett
Note on P98: Sam Bulmer: Support: Carly Merrett
Note on L102: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Do with SZC-FIN-PRO-010, Prepare and Submit Financial Accruals
Note on AT102: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: to be defined in the audit planning
Note on L103: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Do with SZC-FIN-PRO-007, Establish and Maintain Investment Case
Note on AT103: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: to be defined in the audit planning
Note on P104: Sam Bulmer: Support: Russell Grinham
Note on O106: Sam Bulmer: Support: Russell Grinham
Note on P106: Sam Bulmer: Support: Russell Grinham
Note on O107: Sam Bulmer: Support - Rebecca Hudson
Note on P107: Sam Bulmer: Support - Rebecca Hudson
Note on F111: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: Hi @Becky Hudson please can you add in dates for this and just confirm it’s a Cat B? Reply: @Becky Hudson I’ve put a temp date in here, but please can you check and update ASAP, thanks. Reply: completed
Note on L112: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Dates still yet tbc.
Note on L116: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: change to nov
Note on P116: Sam Bulmer: Support: Hannah Dixon (lead aduitor) and Rebecca Hudson
Note on C118: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: Requiring auditor support. @Fran Gradie
Note on O120: Sam Bulmer: Support - Hannah Dixon
Note on P120: Sam Bulmer: Support - Hannah Dixon
Note on E125: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: See AUD-2165 for Control Access of People To Sites. Linus also touched on two others but these were not formalised. Reply: This should be later in 2025 to allow for moving to 25CA and subsequent time to establish process at new address.
Note on E126: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Much of this has been covered in 2023. Two procedures we know have changed as part of IMS improvements might be worth looking at in mid to late 2025
Note on F126: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Alex Boyce see changes as described
Note on L127: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: confirmation of new date needed
Note on E129: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: AUD-1278 - Aug 2023 - Manage Enquiries and Complaints, no NCR’s found. This has been covered in LRQA audits and is a topic for re-certification audit in Nov 2024. Thus not seen a pressing topic. Thus no justification for looking at this in the mid to short term, thus exclude from scope. Reply: Manage and Provide Project Reporting, allow Power BI reporting to settle in and then evaluate. Little point doing earlier as it will just be all “when Power BI gets here” style answers
Note on E132: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: AUD-2027 cover Investigate Incidents Reply: Enable Continuous Improvement covered in LRQA audit 9001
Note on F133: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Are they reporting waste from site or waste from the offices. Is this reported seperately - question or Nidi
Note on O135: Sam Bulmer: Support: Carly Merrett
Note on P135: Sam Bulmer: Support: Carly Merrett
Note on O137: Sam Bulmer: Support: Russell Grinham & Stephen Roast
Note on P137: Sam Bulmer: Support: Russell Grinham & Stephen Roast
Note on O143: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Support Carly Merrett
Note on P143: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Support Carly Merrett
Note on O146: Sam Bulmer: Support - Rebecca Hudson
Note on P146: Sam Bulmer: Support - Rebecca Hudson
Note on O147: Sam Bulmer: Support - Rebecca Hudson
Note on P147: Sam Bulmer: Support - Rebecca Hudson
Note on O148: Sam Bulmer: Support - Rebecca Hudson
Note on P148: Sam Bulmer: Support - Rebecca Hudson
Note on D151: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: PL: New line added: Stage 1 of the ISO 27001 separated from the activity ID 27
Note on M151: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: PL: This due date refers to the field work completed (4 days) plus the time for release the audit report; This planned date need to be confirmed with LRQA
Note on O152: Sam Bulmer: Support: Russell Grinham
Note on P152: Sam Bulmer: Support: Russell Grinham
Note on O153: Sam Bulmer: Support: Carly Merrett
Note on P153: Sam Bulmer: Support: Carly Merrett
Note on O156: Sam Bulmer: Support - Rebecca Hudson
Note on P156: Sam Bulmer: Support - Rebecca Hudson
Note on E169: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Management of Organisational Change, regularly looked at by LRQA Reply: Manage Board Membership, to previously conducted audits in July 2023 along similar lines. Appears this procedure replaced them, Reply: No urgency on this topic.
Note on L172: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Moved back significantly based on comments related to passed HOLD POINT.
Note on E174: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Thomas Brazendale please can you discuss with Chris, please see email.
Note on L174: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: External audit is June so keep month light
Note on D179: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: PL: New line added related to the next step after the Gap analysis for the ISO 45001, related the surveillance audit.
Note on L179: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: PL: this planning will be confirmed after the phase 2
Note on D183: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Faun Dunford , just to note, Vanessa has asked me to remove this line from the plan as will come under Internal Audit, which I have now done.
Note on F184: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Alex Boyce FYI
Note on D188: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: PL: New line added: Stage 2 of the ISO 27001 separated from the activity ID 27
Note on M188: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: PL: This due date refers to the field work completed (8 days) plus the time for release the audit report; This planned date need to be confirmed with LRQA
Note on D189: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: PL: New line added related to the next step of the PAS2080
Note on M189: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: PL: this planning refers to the 4 audit person days (field work) plus the time for the report to be released. This date will be confirmed near the audit date.
Note on O189: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: PL: Query: is this not part of Julia Pyke organization? Reply: @Camila Casagrande Zanaga it does relate to ESG team yes, however, as it wraps up into areas covered by Peter and team, we probably need to have it under Chris and Fran, as this is the SS&A Tracker, there may be a conversation when we see future plans, on if this should also be replicated or separated out into ESG.
Note on P189: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: PL: Query: is this not part of Julia Pyke organization? Reply: @Camila Casagrande Zanaga it does relate to ESG team yes, however, as it wraps up into areas covered by Peter and team, we probably need to have it under Chris and Fran, as this is the SS&A Tracker, there may be a conversation when we see future plans, on if this should also be replicated or separated out into ESG.
Note on G195: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: FCR on risk register so cat A?
Note on E207: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Expect this to be raised at next ISO9001 in Nov 2024 probably a priority? Reply: AUD-1309, Sept 2023
Note on C214: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Camila Casagrande Zanaga Just to note, Vanessa has asked me to take this line out of the audit plan.
Note on E214: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: AUD-1359, Actions in progress
Note on AT214: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: to be defined in the audit planning
Note on D229: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Combine with WDA/CA permit compliance line 201
Note on D232: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: Check with Stephen first key milestone for Marine construction Reply: @Becky Hudson any update from Stephen on this one?
Note on E237: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Maintain Legislation & Regulatory Landscape (AUD-1488) November 2023 Reply: Control Regulatory Approved Management Arrangements has been recently covered by LRQA and has been internally audited (AUD-1543, December 2023)
Note on M248: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: PL: This due date refers to the field work completed (8 days) plus the time for release the audit report; This planned date need to be confirmed with LRQA
Note on E256: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: AUD-1974 (May 2024) covers this subject and it has also been looked at in ISO9001 and ISO14001 External Audits. It is therefore not required until 2027

## Category Types
Risk Category Types
Category | Description
Category A | 1. An Assurance activity linked to a key project milestone or key risk. 2. Includes critical project reviews / Hold points / Readiness. 3. Should link to a milestone identified on IWS, the introduction of a hold point release, a key risk in ARM, or a risk in the Internal Audit Function's Risk Assessment.
Category B | 1. An Assurance activity that assesses compliance with key legislation such as Nuclear Site Licence (NSL) / Environmental Permits / Environmental, Social, and Governance (ESG) requirements / Developmental Consents Order (DCO), etc. 2. An Assurance engagement not linked to a key project milestone or key risk undertaken by the Internal Audit Function.
Category C | 1. Routine day to day activity used to inform Assurance functions and other process audits / routine self-assessment (using one of the IAAP standard Assurance tools only).
Category R | 1. An Assurance activity undertaken by an external regulatory body e.g. ONR, EA, and OFGEM.

## Hold Point Linkage
SZC Hold Point List Linkage
1.1.1 U1 - DCO Application
1.1.2a U1 - Design Replication Confirmation
1.1.4 U1 - Commencement of excavation for the cut-off wall | Released
2.1.14 U1 - Assembly of High Integrity Primary Circuit Components
1.2.4 U1 - Commencement of Offshore Works - Installation of Permanent Structures
1.2.1 U1 - First Nuclear Concrete
1.2.3 U1 - Start of long lead items manufacture under SZC Standalone Contract
1.3.1 U1 - Start of Commissioning
1.4.1 U1 - First Fuel Load into Reactor
1.4.2 U1 - Initial criticality and low power tests
1.5.1 U1 - Start of commercial operations
1.3.10 U1 - Fuel reciept onto the site
2.0.1a U1 - Confirmation of the radiological cleanliness of the SZC site
2.0.2 U1 - Concrete pour capability demonstration
2.0.7 U1 - Commencement of the authorised development DCO Works
2.1.6 U1 - Temporary Sea Defence
2.1.8 U1 - Commence construction of the Marine Bulk Import Facility
2.1.11 U1 - Commencement of backfill
2.2.5 U1 - Turbine pedestal pouring
2.2.8 U1 - Reactor building dome lifting
2.2.9 U1 - Commencement of pre-stressing activities
2.2.10 U1 - Reciept of first major NSSS Shipment to Site
2.2.11 U1 - Installation of the reactor pressure vessel (rpv)
2.2.12 U1 - Pre-stressing gallery
2.2.14 U1 - Launch of the tunnel boring machine (TBM)
2.2.15 U1 - Start of Bulk Radiography
2.2.16 U1 - First Primary Circuit Weld
2.2.17 U1 - Release of delivery of TXS Cabinets to Site
2.2.18 U1 - Start of Radiography (early "first-off")
2.2.19 U1 - First mechanical electrical and HVAC (MEH) Installation of walled-in equipment
2.2.20 U1 - Start of first bulk mechanical electrical and HVAC (MEH) activity in the Nuclear Island
2.2.21 U1 - First mechanical electrical and HVAC (MEH) system hand-over activity to commissioning
2.2.24 U1 - Tunnel/Shaft Connection
2.2.25 U1 - First Secondary Stream System Pipework Weld - Prefabrication
2.2.26 U1 - First Secondary Steam System Pipework Weld
2.3.2 U1 - Water in Forebay
2.3.7 U1 - Start of Hot functional tests
2.3.9 U1 - Segregation of Unit 1 Site
2.3.13 U1 - Start of Cold functional tests
2.3.14 U1 - Northern Drainage Culvert
2.3.15 U1 - Permanent Sea Defence
2.3.16 U1 - Equipment Care and Maintanance
Multiple (to be detailed in Description)
N/A

## Environmental Permit or Consent
Environmental Permit or Consent
Flood Risk Activity Environmental Permit
Fish Pass Approval
Combustion Activity Permit
Land Drainage Consent
Construction Water Discharge Activity Permit
Water Resources Abstraction Licence (Transfer Licence)
Water Resources Abstraction Licence - for the abstraction of water during construction
Water Resources Impoundment Licence
Waste Permit Operation
Ordinary Watercourse Consent
Waste Exemptions
N/A
All Permits

## BRAG
Blue | Complete
Red | Off plan & requires rescheduling
Amber | Off plan but recoverable
Green | Going as planned
N/C | Not commenced

## Assurance Tools
Assurance Tools
Tool name | Tool Description | Where Applicable
Assessment | An assessment is an activity designed to judge or decide on the amount, value, quality, or importance of something, or the judgment or decision that is made. It is therefore more subjective and open to personal professional opinion than, say, an inspection. An assessment is the measurement of technical or functional aspects and the outcomes of the areas being assessed. Within the SZC assurance framework assessments are used to inform decisions rather than assess compliance. | Typically used by Line 3, but may be applied by other lines, where appropriate. SZC Reference: Perform Independent Technical Assessment SZC–ACQ–PRO–022 Perform Independent Assessment SZC-ACQ-PRO-019
Audit | Audits involve examination of compliance with issued processes, procedures and standards. Within the SZC assurance framework audits are: - A “check” function undertaken by a party organisationally separate to that being audited. - To assess overall compliance with one or more regulations, procedures, or other compliance drivers. - A process of evaluating that compliance obligations have been met, including that the required inspections have been completed. - An assurance activity that can be conducted by a third-party to SZC. The process of auditing relies on 3 types of evidence being analysed: 1. Documentary – reviewing appropriate procedures/documents. 2. Testimony – carrying out interviews on a cross-section of personnel. 3. Visual – from a workplace inspection. | Typically used by Line 2 or 3 Functions in oversight of Line 1, or Line 1 in oversight of Line 0. Frequently used by third party agencies as part of the “External” assurance carried out on SZC. SZC Reference: Perform Internal (Management System) Audit (Against IMS) SZC-ACQ-PRO-020 Conduct Supply Chain Audit SZC-ACQ-PRO-027 Manage External Audit SZC-ACQ-PRO-013
Inspection | Inspections are like audits in that they involve discussions with delivery/operational personnel and visits to the workplace to confirm that required standards are being achieved, and that processes, procedures and standards are adequate and being followed. They are though more specific than audits in terms of scope and will focus on a particular set of activities rather than overall compliance with one or more regulations, procedures, or other compliance drivers. Inspections are: - A “do” function. - Typically, something that a site is required to do by a compliance obligation. - Targeted verification activities to see if specific equipment or processes are in place and operating in a safe and environmentally friendly / sustainable way. - More frequent than audits | Used by Line 2 and 3 within the SZC assurance framework to inspect specific activities undertaken by Line 1, and by Line 1 in oversight of Line 0. SZC Reference: Manage Occupational Health and Safety Inspections SZC-HSE-PRO-021
Investigations | Investigations are usually undertaken following a significant abnormal event at the request of senior management and are therefore reactive rather than planned. These are undertaken by others within the organisation with no direct involvement with the event to ensure that the investigation is demonstrably independent. Typically involve examination of issued processes, procedures and standards together with discussions and workplace visits to identify the cause of the abnormal event. Findings can be used to inform the revision of management system documentation and may be indicative of the organisation’s leadership, capability, culture and risk controls. | Can be applied by any Line within the SZC framework depending on the nature and/or severity of the associated abnormal event. Key though is the independence of the investigation team and this will typically lead to the investigation being undertaken by the next Line up within the SZC framework e.g. Line 3 on Line 2, or Line 2 on Line 1.
Reviews | Reviews involve the examination of information, data and documentation but without a visit to the workplace. Similar to audit in terms of gathering evidence in terms of: 1. Documentary – reviewing appropriate procedures/documents. 2. Testimony – carrying out interviews on a cross-section of personnel. 3. Visual – from a workplace inspection. While audits primarily focus on assessing overall compliance reviews are primarily used to assess the quality and comprehensiveness of the application of management systems procedures and methodologies. They are therefore more holistic and subjective in terms of findings with the focus being on identifying areas for improvement as well as good practice to she shared across the organisation. | Typically used by Line 2 or 3 Functions in oversight of Line 1.
Self Assessment | Self-assessment (SA) under the SZC assurance framework is a “self-check” which can be employed by all functions / delivery teams for internal assessment purposes and can be scaled appropriately to support assessment of: - Compliance with Licence conditions, Legislation, Regulatory requirements, or permits. - Effectiveness of specific policies. - Effectiveness and efficiency of performance of procedures or activities. - Cohesive team performance and capability. - Ongoing application of relevant good practice. - Continuous improvement and learning. To underpin effective risk management and support proportionate assurance, Self-Assessments of performance in the following areas, must be captured and visible on the IAAP: - Assessment of compliance against all relevant Legislation or Regulatory Requirements, including assessment of performance against: - NSL, Environmental Permits, CDM, Legal, Financial compliance, Ethics and Corporate Governance, security, and data protection - Any procedure claimed as ‘arrangements’ underpinning legislation or regulatory requirements (most likely captured as audits in Audit Plan). - Assessment of compliance with the DCO. - Assessment of compliance against requirements identified by key external stakeholders and specified as a SZC Project Commitments/Requirements. An SA can also be incorporated within the IAAP, at the discretion of the Responsible Manager, if they determine visibility of the SA on the IAAP supports the principles of proportionate assurance. Other SAs should be captured in Functional assurance plans. | Applicable to all lines. Each SZC function / delivery team will maintain its own schedule of self-assessments and records from these. These will be available to the Line 2 & 3 assurance functions to help them identify the most appropriate areas and times to apply other assurance activities SZC Reference: Perform Self-Assessment SZC-ACQ-PRO-021 includes guidance on how to; - Update, approve and communicate the self-assessment schedule. - Scope, plan, prepare for and conduct a self-assessment. - Capture the learning, writing the self- assessment report and approval of the report and associated actions. - Publish the report and track the actions to completion.
Surveillance | Surveillance is used as part of routine inspection activities to check workplace conditions and enable behavioural observations to be made. Findings can be indicative of the effectiveness of risk controls and the organisation’s capability and culture Surveillance involves attending meetings and workplaces to form judgements on whether the required standards and behaviours are being achieved. Includes oversight of business activities such as observations of setting to work, conduct of work or tasks or meetings involving operational and functional management and includes oversight of formal governance meetings. Observations from surveillance activities provide “intelligence” to inform specific inspections as well as the overall assurance oversight plan through providing insight on process compliance. | Used by Line 2 in the SZC assurance framework to support specific inspections on Line 1, and by Line 1 in supporting oversight inspections of Line 0.
Concurrence | Apply Concurrence procedure: SZC-ACQ-PRO-005 To provide enhanced scrutiny of the implementation, continuation, permissioning or resumption of an activity or process judged to present sufficient risk to the organisation that independent assessment and assurance from the internal regulator is deemed prudent. | Used by Line 3 in oversight of specific activities across the Project.
Review of Self Assessment | Reviews of self assessments are to check on assocaiated findings and actions from self assessments that have already been conducted to ensure they are effective. | Used predominantly by auditors to 'review' self-assessments.
Note on E5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: These are Line 3 (INA) Procedures. Do you need to distinguish between Assessment of the Line 0 (e.g. RD surveillance) and the role of INA / Independent Assessments? Reply: @Adam Duddridge , yes Fran and I spotted this, we took across the definition from the IAAP definitions list, could you check with Peter Chambers on this, as happy for us to look at this again once this has been agreed upon, but rather we align with the IAAP definitions list as that’s what this will need to line up with. Reply: @Adam Duddridge altered as discussed, if you can share with Simon to update with Deloitte when he speaks to them next that would be great. Reply: @Simon Barnard

## RAG
Outcome RAG Status
N/C | Not yet completed
Red | Completed with major issues identified & requiring escalation
Amber | Completed with major issues but being addressed
Green | Completed with no major issues

## Risks
Strategic Risk | Description | Owner
Achieving Replication | SZC is unable to replicate the HPC design and supporting supply chain. | Tilly Spencer
Cyber security | The Confidentiality, Integrity or Availability of SZC information is compromised. | Mina Golshan
Environment | SZC requires a significant number of permits (~160) to enable the project through construction, commissioning and operation. To enable the project to protect the environment and SZC's reputation these permits must be: 1) suitably designed and negotiated to ensure compliance is achievable based on the agreed terms, 2) secured within required timescales to enable efficient scheduling of works. | Mina Golshan
Funding Requirements | The project's ability to secure and maintain financing (or maintain access to financing) is critical to its delivery and operation; failure to meet debt covenants or financing conditions, alongside global market volatility affecting construction material costs and availability beyond the RAB limits, poses a significant risk to financial viability and project execution. (Combined Risk of Access to funding requirements and Global Commodities Markets) | Katherine Horrell
Grid Connection | Reforms to the electricity connection process have resulted in a need for SZC to reapply to rejoin the queue for grid connection. Without the connection, SZC will not be able to commission the station and export power, which would have a detrimental impact on income generation. This also applies to the planned demand connection related to the Construction Electrical Supplies. | Julia Pyke
Health, Safety & Wellbeing | The scale and complexity of the SZC project carries inherent health and safety risk to the workforce and local community which needs to be managed as an imperative. | Mina Golshan
Nuclear Safety Risk | SZC needs to demonstrate that it has a safe and compliant design, built to quality specification and operated by suitably qualified and experienced workforce within a safety conscious culture. Failure to demonstrably achieve these will risk timely delivery, cost increases and operational safety and regulatory action. The risk being managed is the potential inability to commission the plant due to regulatory compliance reasons, or core damage and significant release of radioactivity because of an inability to maintain the integrity of the fission product barriers designed to protect the health and safety of the plant staff and the public. Nuclear risks require ownership and management by a ‘Capable Nuclear’ Organisation and the required management controls, which are broadly encompassed in SZC’s arrangements to deliver the ONR’s 36 Nuclear Site Licence Conditions. | Mina Golshan
Operational Capability | To achieve high safety, availability and deliver value for money, the aim of operational preparedness is to enable progressive organisational transition to achieve a capable organisation at the Commercial Operation Date (COD), independent from EDF group, able to operate the plant safely and reliably - with nuclear, environmental, and industrial safety, and security at the forefront of operational behaviours. | Nigel Cann
Organisational Capability | The SZC project may face challenges in meeting new and evolving corporate and regulatory standards, risking non-compliance or insufficient evidence of compliance. Inadequate risk assessment and business continuity planning could further impact operational resilience during disruptions. New standards and requirements related to financing documents, the economic licence, shareholder agreements and government classification must be complied with. Additionally, the industry, scope, scale, cost and importance of SZC reflects the needs to for the project to have robust and clear understanding of how large and uncertain risks could derail the continuity of the project throughout construction. (Combined Risk of Business Continuity and Corporate Maturity combined) | Xanthe Kueppers
People & Skills | The project is unable to attract, develop and retain the necessary people or provide the right skills at the right time to enable effective delivery of the project, inclusive of accommodation, transport, welfare and wellbeing. | Sarah Hancock
Productivity | Achieving target productivity and production is key to maintaining the schedule and could lead to significant cost escalation if not achieved. Maximising productivity and production outputs across Civil Works and MEH scopes, and delivering the associated sequence of works, key milestones and the corresponding cost profile for SZC, is predominantly dependent on learning from the HPC delivery. This involves clearly identifying and then embedding a broad and complex suite of inter-related enablers of maximum productivity and production and monitoring and assuring the successful implementation of these enablers during works delivery. There is a risk that the work undertaken by the project to understand these enablers, and the subsequent work undertaken to successfully embed these enablers into delivery, does not have the anticipated impact. At this time, this risk focuses on delivery of Civil Works and will progress to MEH Works when HPC delivery reaches a greater level of maturity. (Combined risk of Productivity and HPC Delay) | Bertrand Michoud
Quality | There is a risk that the quality management plan is not effective, which could result in the quality of work delivered across the project falling short of expectations or requirements for commissioning to be achieved (e.g, the welding issues encountered on Flamanville 3). | Bertrand Michoud
Reputation & Social License | Whilst SZC has now gained funding certainty with FID, the project’s reputation and continued success are heavily dependent on sustained political support, positive media coverage, and strong relationships with local communities and stakeholders. Shifts in national or local political landscapes, coupled with adverse press, may undermine investor, supplier, and recruitment confidence. Although the project currently holds a Social Licence to operate, this trust is contingent on responsible conduct and proactive engagement. Poor site performance, inadequate communication with stakeholders, or failure to uphold community expectations could erode public support, damage the project's reputation, and jeopardize its social legitimacy. | Julia Pyke

## List of functions
Commercial
ESG & Rad Strat - ESG Teams
External Review - Arcadis VDD
External Review - DESNZ
External Review G4S
External Review - IPA - MPRG
External Review - KPMG - External Financial Auditor
External Review - Deloitte - External Financial Auditor
External Review - LRQA
External Review - ONR
External Review - EA
F&ER
Finance
Human Resources
Independent Nuclear Assurance
Internal Audit
Legal
Risk
SS&A - Marine Environment
SS&A - Nuclear Licence Compliance
SS&A - Operational Permits
SS&A - Performance Improvement
SS&A - Quality Assurance
SS&A - Security & Conventional Safety Assurance
Technical
Transition
ESG & Rad Strat - Rad Pro & Nuclear Liabilities
SS&A - Emergency Preparedness
Delivery - CI&BOP
Delivery - NI Programme
Delivery - Civils Programme
Delivery - Site Programme
Delivery - Delivery/PDO
Overall Project
SS&A - Environmental Services and Assurance
SS&A - Culture
SS&A - Construction Permitting
SS&A - Combined Line 2 Team
SS&A and ESG Combined

## Milestone
Milestone | Due date | Level | HP Ref
CNEPE OBD M&T Design Report Issued | 2024-05-20 | L2
M&T Optismised Basic Design RD Specification Completed | 2024-06-28 | L2
M&T Class 4 Estimate and Schedule Development Completed | 2024-05-27 | L2
Draft Productivity Plan Issued | 2024-07-26 | L2
Main Batching Plant design & procurement completed (to meet COW start dates) | 2024-10-25 | L2
SZ1220 Lot 2 Contract Award | 2025-02-28 | L2
Pre-Stressing Gallery - Phase 1 Design GRB Complete | 2025-06-09 | L2
Common Raft - Phase 1 Design GRB Complete | 2025-02-12 | L2
SD11 Park & Ride Archaeology Commencement | 2024-06-13 | L2
SD25 North Park & Ride Commencement | 2025-04-09 | L2
SD05 Commence Off Site Infrastructure Site Accesses | 2024-05-30 | L2
SD18 Bridleway 19 Diversion Commencement | 2024-09-23 | L2
SD22 Lover’s Lane Realignment Commencement | 2025-05-02 | L2
SD26 Major Roads Commencement | 2025-04-25 | L2
SD21 Rail Stage 1 Enabling commenced – systems and non-systems | 2024-08-30 | L2
SD24 Rail - GRIP 5 Design Approved | 2025-02-20 | L2
Darsham Park & Ride (NPR) - Design Available for Construction (L3 Reporting Milestone) | 2024-09-19 | L2
Darsham Park & Ride (NPR) - Contract Awarded (L3 Reporting Milestone) | 2025-03-07 | L2
Darsham Park & Ride (NPR) - Site Access Complete (L3 Reporting Milestone) | 2024-07-16 | L2
Darsham Park & Ride (NPR) - Advanced Works Start (L3 Reporting Milestone) | 2024-08-28 | L2
Darsham Park & Ride (NPR) - Advanced Works Finish (L3 Reporting Milestone) | 2024-10-02 | L2
Darsham Park & Ride (NPR) - Start on Site (L3 Reporting Milestone) | 2025-04-09 | L2
Darsham Park & Ride (NPR) - Completion of Works (L3 Reporting Milestone) | 2026-04-24 | L2
Wickham Park & Ride (SPR) - Design Available for Construction (L3 Reporting Milestone) | 2024-09-27 | L2
Wickham Park & Ride (SPR) - Contract Awarded (L3 Reporting Milestone) | 2025-03-07 | L2
Wickham Park & Ride (SPR) - Site Access Complete | 2025-10-23 | L2
Wickham Park & Ride (SPR) - Advanced Works Start (L3 Reporting Milestone) | 2024-06-27 | L2
Wickham Park & Ride (SPR) - Advanced Works Finish (L3 Reporting Milestone) | 2025-08-27 | L2
Wickham Park & Ride (SPR) - Start on Site (L3 Reporting Milestone) | 2025-08-28 | L2
Wickham Park & Ride (SPR) - Completion of Works (L3 Reporting Milestone) | 2026-11-20 | L2
Freight Management Facility, including Water Storage Facility- Design Available for Construction (L3 Reporting Milestone) | 2024-07-08 | L2
Freight Management Facility, including Water Storage Facility - Contract Awarded (L3 Reporting Milestone) | 2025-03-20 | L2
Freight Management Facility, including Water Storage Facility - Site Access Complete (L3 Reporting Milestone) | 2025-07-22 | L2
Freight Management Facility, including Water Storage Facility - Advanced Works Start (L3 Reporting Milestone) | 2024-05-08 | L2
Freight Management Facility, including Water Storage Facility - Advanced Works Finish (L3 Reporting Milestone) | 2024-07-24 | L2
Freight Management Facility, including Water Storage Facility - Start on Site (L3 Reporting Milestone) | 2025-05-28 | L2
Freight Management Facility, including Water Storage Facility - Completion of Works (L3 Reporting Milestone) | 2026-07-20 | L2
Minor Roads - Design Available for Construction (L3 Reporting Milestone) | 2024-11-11 | L2
Minor Roads - ITT Issued (L3 Reporting Milestone) | 2024-05-16 | L2
Minor Roads - Contract Awarded (L3 Reporting Milestone) | 2024-11-25 | L2
Minor Roads - Completion of Works (L3 Reporting Milestone) | 2026-07-20 | L2
Sizewell Link Road - Design Available for Construction (L3 Reporting Milestone) | 2024-08-15 | L2
Sizewell Link Road - ITT Issued (L3 Reporting Milestone) | 2024-05-21 | L2
Sizewell Link Road - Contract Awarded (L3 Reporting Milestone) | 2024-11-28 | L2
Sizewell Link Road - Consents & Permits Approved (L3 Reporting Milestone) | 2024-12-20 | L2
Sizewell Link Road - Land Access Available (L3 Reporting Milestone) | 2024-05-23 | L2
Sizewell Link Road - Site Access Complete (L3 Reporting Milestone) | 2024-06-26 | L2
Sizewell Link Road - Advanced Works Start (L3 Reporting Milestone) | 2024-07-17 | L2
Sizewell Link Road - Advanced Works Finish (L3 Reporting Milestone) | 2026-09-08 | L2
Sizewell Link Road - Start on Site (L3 Reporting Milestone) | 2025-03-31 | L2
Sizewell Link Road - Completion of Works (L3 Reporting Milestone) | 2027-04-06 | L2
Two Village By-Pass - Design Available for Construction (L3 Reporting Milestone) | 2024-06-28 | L2
Two Village By-Pass - ITT Issued (L3 Reporting Milestone) | 2024-05-21 | L2
Two Village By-Pass - Contract Awarded (L3 Reporting Milestone) | 2024-11-28 | L2
Two Village By-Pass - Consents & Permits Approved (L3 Reporting Milestone) | 2025-04-04 | L2
Two Village By-Pass - Land Access Available (L3 Reporting Milestone) | 2024-05-23 | L2
Two Village By-Pass - Site Access Complete (L3 Reporting Milestone) | 2024-06-26 | L2
Two Village By-Pass - Advanced Works Start (L3 Reporting Milestone) | 2024-07-24 | L2
Two Village By-Pass - Advanced Works Finish (L3 Reporting Milestone) | 2025-12-04 | L2
Two Village By-Pass - Start on Site (L3 Reporting Milestone) | 2025-04-25 | L2
Two Village By-Pass - Completion of Works (L3 Reporting Milestone) | 2027-04-14 | L2
Yoxford Roundabout - ITT Issued (L3 Reporting Milestone) | 2024-05-10 | L2
Yoxford Roundabout - Contract Awarded (L3 Reporting Milestone) | 2025-03-24 | L2
Yoxford Roundabout - Consents & Permits Approved (L3 Reporting Milestone) | 2025-02-14 | L2
Yoxford Roundabout - Site Access Complete (L3 Reporting Milestone) | 2024-06-26 | L2
Yoxford Roundabout - Advanced Works Start (L3 Reporting Milestone) | 2024-10-28 | L2
Yoxford Roundabout - Advanced Works Finish (L3 Reporting Milestone) | 2025-01-13 | L2
Yoxford Roundabout - Start on Site (L3 Reporting Milestone) | 2025-04-25 | L2
Yoxford Roundabout - Completion of Works (L3 Reporting Milestone) | 2026-03-02 | L2
Rail Projects - Design Available for Tender (L3 Reporting Milestone) | 2025-02-20 | L2
Rail Projects - Design Available for Construction (L3 Reporting Milestone) | 2025-02-20 | L2
Rail Projects - Contract Awarded (L3 Reporting Milestone) | 2024-07-16 | L2
Rail Projects - Consents & Permits Approved (L3 Reporting Milestone) | 2024-12-27 | L2
Rail Projects - Land Access Available (L3 Reporting Milestone) | 2024-10-02 | L2
Rail Projects - Site Access Complete (L3 Reporting Milestone) | 2024-08-07 | L2
Rail Projects - Advanced Works Finish (L3 Reporting Milestone) | 2025-08-27 | L2
Rail Projects - Start on Site (L3 Reporting Milestone) | 2024-08-30 | L2
Rail Projects - Completion of Works (L3 Reporting Milestone) | 2027-01-19 | L2
Accommodation Campus - Design Available for Construction (L3 Reporting Milestone) | 2025-07-11 | L2
Accommodation Campus - ITT Issued (L3 Reporting Milestone) | 2024-05-20 | L2
Accommodation Campus - Contract Awarded (L3 Reporting Milestone) | 2025-03-04 | L2
Accommodation Campus - Consents & Permits Approved (L3 Reporting Milestone) | 2025-11-12 | L2
Accommodation Campus - Site Access Complete (L3 Reporting Milestone) | 2024-06-10 | L2
Accommodation Campus - Advanced Works Finish (L3 Reporting Milestone) | 2025-02-20 | L2
Accommodation Campus - Start on Site (L3 Reporting Milestone) | 2025-12-15 | L2
Accommodation Campus - Completion of Works (L3 Reporting Milestone) | 2027-08-24 | L2
MDS Roads - Design Available for Construction (L3 Reporting Milestone) | 2024-07-17 | L2
MDS Roads - ITT Issued (L3 Reporting Milestone) | 2024-05-09 | L2
MDS Roads - Contract Awarded (L3 Reporting Milestone) | 2025-02-04 | L2
MDS Roads - Consents & Permits Approved (L3 Reporting Milestone) | 2025-03-28 | L2
MDS Roads - Land Access Available (L3 Reporting Milestone) | 2024-08-07 | L2
MDS Roads - Site Access Complete (L3 Reporting Milestone) | 2024-09-19 | L2
MDS Roads - Advanced Works Finish (L3 Reporting Milestone) | 2024-11-19 | L2
MDS Roads - Start on Site (L3 Reporting Milestone) | 2025-05-02 | L2
MDS Roads - Completion of Works (L3 Reporting Milestone) | 2027-01-06 | L2
BW19 - Contract Awarded (L3 Reporting Milestone) | 2024-09-20 | L2
BW19 - Consents & Permits Approved (L3 Reporting Milestone) | 2024-10-18 | L2
BW19 - Land Access Available (L3 Reporting Milestone) | 2024-10-18 | L2
BW19 - Site Access Complete (L3 Reporting Milestone) | 2024-10-18 | L2
BW19 - Advanced Works Finish (L3 Reporting Milestone) | 2024-11-19 | L2
BW19 - Start on Site (L3 Reporting Milestone) | 2024-10-18 | L2
BW19 - Completion of Works (L3 Reporting Milestone) | 2026-06-25 | L2
ACA Archeology - Mitigations Complete | 2024-07-30 | L2
Fen Meadow Compensation Sites - Benhall - Turve Contractor Mobilisation - Turve Translocation | 2024-10-25 | L2
Fen Meadows - Benhall Site Construction Complete | 2024-10-23 | L2
Outage Laydown Area - A Station Land Purchased | 2024-08-02 | L2
Demolition (Redundant Facilities) - Demolition of Old Outage Store Complete | 2025-04-04 | L2
Low Voltage Power Available from SZB | 2024-06-20 | L2
Associated Developments 4 - Complete Grip 4 Design | 2024-08-21 | L2
Associated Developments 6 - Out to Tender for Delivery | 2024-06-03 | L2
CWA - Full Project Alliance Agreement (PAA) ready for CWA participant signatures | 2024-05-31 | L2
CWA - Implementation Phase complete | 2024-05-31 | L2
MCA Lake - WJ Surface Water Management Completion | 2024-06-03 | L2
MCA HSW Ground Water Treatment Plant Available | 2024-06-25 | L2
MCA Temp Building Pack 1 Available | 2024-07-03 | L2
MCA HBL-1 BLF Operating Building Available | 2025-06-25 | L2
MCA South SZB Fence Available | 2025-05-12 | L2
Foreshore Diversion - FRAP obtained | 2024-10-31 | L2
Permanent Fence install​ation - Public Right of Way Diversion complete | 2024-08-23 | L2
SSSI Area - Clearance Works Complete | 2024-11-14 | L2
Batcher area - cleared to allow Earthworks to commence | 2024-05-31 | L2
Desalination plant area - cleared to allow Earthworks to commence | 2024-06-25 | L2
Red Route - Completed | 2024-08-09 | L2
Main Welfare Building - Commence Superstructure | 2025-08-22 | L2
Foreshore Diversion - FRAP obtained | 2024-10-31 | L2
Permanent Fence Install​ation - Public Right of Way Diversion Complete | 2024-08-23 | L2
SSSI Area - Clearance Works Complete | 2024-11-14 | L2
Red Route Open | 2024-08-09 | L2
ACA Railhead (Zone 7) - Land Clear of Advanced Works | 2024-11-22 | L2
Two Village By-pass - All Land Clear of Advanced Works | 2025-08-27 | L2
HGE - Start of MEH detailed design | 2024-07-01 | L2
CI BOP & Heat Sink Programme - Project Definition Documents updated | 2024-05-31 | L2
CI BOP - 3 x Contracts Ready to be Signed: Fayat, GE Pumps, Trillium | 2024-08-20 | L2
GE Turbine - Contract Ready for Signature | 2024-06-19 | L2
CI BOP - 7 x contracts signed: Fayat, GE pumps, Trillium, Sommer, Ovivo, Bertin, Flowserve | 2024-09-04 | L2
Large Travelling Cranes (SZ3681 Fayat) - Contract Award | 2024-06-19 | L2
KRS (SZ3301 Bertin) - Contract Award | 2024-05-31 | L2
Turbine (SZ3011 GE) - Contract Award | 2024-06-28 | L2
Sommer Barrier Wall - Concept Design delivered | 2024-06-28 | L2
Chlorination Plant (SZ3422) - Contract Award | 2024-06-28 | L2
Thermal Driven Pumps (SZ3253 Flowserve) - Contract Award | 2024-06-28 | L2
CRF Motor Driven Pumps (SZ3251 GE Alstom) - Contract Award | 2024-08-20 | L2
Power Transmission (SZ3001 Linxon) - Contract Award | 2024-07-31 | L2
Frames and Security Doors (SZ3441 Sommer) - Contract Award | 2024-07-31 | L2
Galleries - Start MEHA design | 2024-07-31 | L2
Filtration Equipment (SZ3511 Ovivo) - Contract Award | 2024-07-31 | L2
OP: Water Quality & Quantity | 2024-09-30 | L2
HP H15 - Handover of design to MEH Alliance for HVAC aeraulic studies | 2024-10-31 | L2
Demineralisation Plant (SZ3421 Veolia/Bilfinger) - ECI Complete | 2024-12-31 | L2
HCA H16 - Handover of design to MEH Alliance for Seismic Calculations | 2024-12-31 | L2
End to End L2 Schedule Update | 2024-12-31 | L2
Demineralisation Plant (SZ3421 Veolia) - Contract Award - | 2025-02-28 | L2
Co-generation - Pre-FEED Study Delivered | 2024-12-20 | L2
400kV Substation - Reference Design Delivered by National Grid | 2024-12-20 | L2
ED16 - EEW0425 Ground Anchors design Ph2 | 2024-11-25 | L2
EEW09 - Commence Sheet Piling Trials | 2024-05-31 | L2
EEW14 - Start of Bulk Deliveries | 2024-06-28 | L2
EEW17 - Start SSSI Crossing North | 2024-09-02 | L2
EEW21 - Ditch Diversion Works Complete (Northern Section) | 2024-11-29 | L2
EEW30 - Construct Launch Platform for Marine Bulk Import Facility | 2025-04-28 | L2
EEW31 - Bailey Bridge Open for Use | 2025-05-30 | L2
Cut Off Wall - East Wall Phase 2 Design Submission for Client Approval | 2024-07-11 | L2
Cut Off Wall - East Wall Phase 3 Design Approved Ready for Construction | 2025-02-25 | L2
Cut Off Wall - West Wall Phase 2 Design Submission for Client Approval | 2024-06-07 | L2
Cut Off Wall - West Wall Phase 3 Design Approved Ready for Construction | 2025-01-15 | L2
Cut Off Wall - North Wall Phase 2 Design Submission for Client Approval | 2024-06-07 | L2
Cut Off Wall - North Wall Phase 3 Design Approved Ready for Construction | 2025-01-15 | L2
Deed of Obligation - Anniversary Payment | 2025-02-18 | L2
East Suffolk Trust (EAST) - Submission of Application for establishment | 2024-05-28 | L2
UXO Marine License - Approval | 2024-12-31 | L2
Fisheries Liaison and Coexistence Plan (FLCP) - Approval by MMO | 2025-03-07 | L2
Aids to Navigation Management Plan (ANMP) - Approval by MMO | 2025-05-01 | L2
New Offices - Secured for London and Manchester | 2025-05-01 | L2
LC & PC - Self-assessment programme assurance report | 2025-01-31 | L2
PAS 2080 - gap analysis complete | 2024-06-28 | L2
NSL - Environmental Permits for Variation 1 application complete | 2025-02-28 | L2
ISO 9001: Re-Certification Audit | 2024-12-31 | L2
ISO 14001: Surveillance Audit | 2024-12-31 | L2
Orwell Park Offsite Warehouse - Client Health & Safety Assurance for occupation | 2024-09-30 | L2
Re-licensing Phase 1 - Submission of variation application to Regulators | 2024-09-20 | L2
Hold Point List Revision 5.0 - Board informed, Approved by MD Delivery - To link to Care & Maintenance HP | 2024-08-30 | L2 / HP
SZC Project Security Strategy - Developed and approved | 2024-05-31 | L2
Nuclear Site Security Plan Ver 2.0 - Reviewed and reissued revised plan | 2024-12-31 | L2
Economic Licence (RAB/GSP (Government Support Package)) - Agreement | 2024-06-28 | L2
Economic Licence (RAB/GSP (Government Support Package)) - Grant Licence (including Weighted Average Cost of Capital) | 2024-06-28 | L2
Revenue Contract (with Revenue Collection Counterparty - RCC) - Signature of Contract | 2024-06-28 | L2
Equity (Private) Raise - Completed | 2024-06-28 | L2
Equity (Public) Raise - Completed | 2024-06-28 | L2
Debt (SZC view) Raise - Completed | 2024-06-28 | L2
Post-Financial Close e-SHA (Shareholder Agreement) - Signed | 2024-05-03 | L2
SZC Assumption Book and Financial Model for Financial Close - Final complete | 2024-06-28 | L2
SZC IR Agreements and Governance - Interim in place | 2024-10-30 | L2
SZC Jobs Service - Launch of refreshed version | 2024-09-30 | L2
Employment model requirements (at FC) - Delivered | 2024-06-28 | L2
Vetting and People System - Integrated into SZC | 2024-06-27 | L2
Surveillance Strategies for off-site Manufacture and on-site Construction - Approved updates | 2024-10-01 | L2
SWITCH 3DX (Quality NCRs) - Complete implementation | 2024-12-31 | L2
Pre-Construction Safety Report (PCSR) Specification - Updated | 2024-09-30 | L2
Contingent Workforce Management - Go-Live | 2024-06-27 | L2
Supplier Management Systems - Go-Live | 2024-06-28 | L2
Contract Management System - Go-Live | 2024-06-28 | L2
PDO Delivery Partner contracts - Service Phase 1 endorsed and ready for signature FC - 1 month (Jacobs & Gleeds) | 2024-06-21 | L2
NI14 - Close/Mitigate 24 Open Points | 2024-09-30 | L2
NI10 - MEH Bulk Procurement Strategies Endorsed (HVAC & Piping) | 2024-09-30 | L2
NI08 - Engineering collaboration phase fully defined and in flight | 2024-07-31 | L2
Commence Equipment Care & Maintenance Hold Point | 2025-09-11 | HP | 2.3.16 U1
NI16 - Update of the E2E Level 2 Schedule incorporating Pre-fabrication | 2024-10-31 | L2
NI04 - Update of the E2E Level 2 Schedule, aligned with Estimate 5.0 update | 2024-05-31 | L2
NI Equipment - 24 packages fully executed | 2024-05-15 | L2
NI06 - 35 Nuclear Island Equipment Contracts - Signature of Contract (SOC) | 2024-06-28 | L2
NI12 - 90 Nuclear Island Equipment Contracts at Gate B | 2024-09-30 | L2
NI19 - 60 Nuclear Island Equipment Contracts - Signature of Contract (SOC) | 2024-12-20 | L2
NI21 - 65 Nuclear Island Equipment Contracts - Signature of Contract (SOC) | 2025-03-31 | L2
NI11 - Issuance of the Notice to Proceed to Framatome for SZ4101 Contract (N4S) | 2024-09-30 | L2
NI18 - Largest RPV Forging Complete at Japan Steel Works | 2024-11-26 | L2
NI13 - Offsite pipework and valve strategy - endorsement of the forward schedule | 2024-09-30 | L2
NI07 - SZ2721-001- Axima - SOC - Gate D1 | 2024-07-26 | L2
NI09 - SZ5311 - IED - Launch ITT | 2024-08-30 | L2
NI20 - SZ4101 - Start of Manufacturing of UNICORN Modules | 2025-01-30 | L2
NI15 - End of Siemens Manufacturing of Back-to-Back Cabinets for Unit 1 | 2024-09-30 | L2
NI22 - End of SIEMENS I&C early manufacturing to mitigate obsolescence | 2025-03-28 | L2
Critical IT platforms (IMS, EDRMA, Tenancy) - Available | 2024-06-28 | L2
MEHA Bulk Procurement Strategy - Approved by ALT | 2024-07-26 | L2
Axima SoC MEH | 2024-07-26 | L2
MEHA – Contract Signed | 2024-07-29 | L2
Bulks procurement – HPC BoM | 2024-08-28 | L2
IED (QUAD) - Launch ITT | 2024-08-30 | L2
Technical strategy for opportunities (Open top, Modularisation) - Complete | 2024-09-10 | L2
Exyte - Contract Signature | 2024-10-03 | L2
Bulk Equipment tendering - Commencement of KO | 2024-10-30 | L2
Piping PjDD - Complete | 2024-11-26 | L2
MEHA Annual Resourcing Plan - ALT Approval | 2024-12-20 | L2
IEG (Omexom) - SoC | 2025-01-15 | L2
Piping - Procurement strategy & draft PO produced | 2025-01-29 | L2
MEHA Annual Performance Review - Start | 2025-03-03 | L2
Annual Baselining for FY 24-25 - Completed | 2025-03-31 | L2
Cut-Off ("Diaphragm") Wall - Hold Point Released to Commence CoW | 2025-08-11 | HP | 1.1.4 U1
First Nuclear Safety Concrete - Hold Point released | 2027-10-28 | HP | 1.2.1 U1
Nuclear Island Concrete U1 - Hold Point Released to Commence NI Concrete Pour | 2028-05-23 | HP | 1.2.2 U2
Offshore Works - Hold Point Released to Commence Offshore Works | 2028-03-08 | HP | 1.2.4 U1
Radiological Cleanliness of SZC Site - Hold Point Released for Confirmation of the radiological cleanliness | 2024-03-08 | HP | 2.0.1a U1
Concrete Pour Capability - Hold Point Released for Concrete Pour Capability Demonstration | 2026-10-28 | HP | 2.0.2 U1
Temporary Sea Defence - Hold Point Released to Commence Temporary Sea Defence | 2025-03-31 | HP | 2.1.6 U1
Marine Beach Landing Facility - Hold Point Released to Commence Marine Bulk Import Facility | 2025-09-18 | HP | 2.1.8 U1
Backfill - Hold Point Released to Commence Back Fill | 2027-06-30 | HP | 2.1.11 U1
Reactor Building Dome - Hold Point Released to Commence Unit 1 Dome Lift | 2032-03-05 | HP | 2.2.8 U1
NSSS Shipment to Site - Hold Point Released for Receipt of First Major NSSS Shipment to Site (Unit 1) | 2028-06-23 | HP | 2.2.10 U1
Pre-stressing Gallery - Hold Point Released for Pre-Stressing Gallery Concrete Pour | 2027-10-28 | HP | 2.2.12
Bulk Radiography - Hold Point Released for Start of Bulk Radiography (Unit 1) | 2026-04-03 | HP | 2.2.15 U1
TXS Cabinets - Hold Point Released for Release of Delivery of TXS Cabinets to Site | 2029-03-29 | HP | 2.2.17
Radiography - Hold Point Released for Start of Radiography. (early "first-off") (Unit 1) | 2026-03-19 | HP | 2.2.18 U1
Mechanical Electrical and HVAC (MEH) installation - Hold Point Released for First MEH installation of walled-in equipment | 2027-10-19 | HP | 2.2.19 U1
Mechanical Electrical and HVAC (MEH) activity [in the Nuclear Island] - Hold Point Released for Start of First bulk MEH activity [in NI Unit 1] | 2030-03-01 | HP | 2.2.20 U1
Unit 1 Site - Hold Point Released for Segregation of Unit 1 Site | 2027-11-23 | HP | 2.3.9 U1
Nuclear Island Concrete U2 - Hold Point Released to Commence Nuclear Island Concrete Pour | 2029-05-22 | HP | 2.2.1 U2
NSA Contract - Signature of Contract | 2024-04-30 | L2
NI02 - SZ4101 Framatome Contracts Signature (SOC); N4S, Fuel Assembly Fabrication, LTSA | 2024-04-26 | L2
Book build complete (L0) | 2024-12-27 | L0
Financial Close (L0) | 2024-12-27 | L0
Target Subsidary Control Approval (L0) | 2024-10-26 | L0
SZC FDP - Funded Decommissioning Plan (DWMP and FAP - Funding Arrangements Plan) - Secretary of State Approval (L0) | 2024-10-25 | L0
N/A - No specific Milestone | - | -
Relicensing / variation of licence | 2025-10-31 | L2
Digital transformation of IMS functions | 2025-12-31 | L2
ISO 45001 Certification | 2025-09-01 | L2
ISO 14001: Surveillance Audit Complete | 2025-07-31 | L2
RSR IC1 and IC2 report delivered to regulator | 2025-03-31 | L2
ISO 14001: Recertification Audit Complete | 2025-12-31 | L2
Transformation of the SZC Organisational learning process and tool | 2025-12-31 | L2
National Institute of Standards and Technology Cyber Security Framework Maturity Score of 3 | 2025-12-31 | L2
Commence Northern Drainage Culvert - Hold Point | 2025-09-08 | HP | 2.3.14 U1
Commence Permanent Sea Defence | 2026-08-03 | HP | 2.3.15 U1
Launch of the Tunnel Boring Machine (TBM) | 2030-09-13 | HP | 2.2.14
First Secondary Steam System Pipe Weld - Prefabrication (Unit 1) | 2030-08-02 | HP | 2.2.25 U1
Loading/Installation of First Major NSSS (Nuclear Steam Supply System) Component (Unit 1) | 2030-03-30 | HP | 2.2.11 U1
Start of Welding of the Main Components of the Primary Circuit on Site (Unit 1) | 2030-07-04 | HP | 2.2.16 U1
First Secondary Steam System Pipe Weld (Unit 1) | 2031-01-01 | HP | 2.2.26 U1
First Mechanical Electrical and HVAC (MEH) system hand-over activity to commissioning (Unit 1) | 2031-12-16 | HP | 2.2.21 U1
Commence Turbine Pedestal Concrete Pouring | 2032-04-05 | HP | 2.2.5 U1
Commencement of Pre-Stressing Activities | 2032-09-04 | HP | 2.2.9 U1
Tunnel/Shaft Connection | 2032-10-28 | HP | 2.2.24
Loading / Installation of First Major NSSS Component (Unit 2) | 2033-03-29 | HP | 2.2.6 U2
U2 Dome Lift (Start) | 2033-06-28 | HP | TBC
UNIT 2 - TA Energisation & Start of Commissioning | 2033-10-30 | HP | TBC
U1 Start Cold Functional Tests (CFT) | 2034-07-15 | HP | TBC
UNIT 2 - Release of Water into the Forebay to Start Commissioning of Pump House | 2034-10-30 | HP | TBC
U1 Start of Fuel Delivery | 2034-11-24 | HP | TBC
U1 Start Hot Functional Tests (HFT) | 2034-11-07 | HP | TBC
U1 Start of Fuel Loading | 2035-04-27 | HP | TBC
Start of Cold Functional Tests (U2) | 2035-07-14 | HP | 2.3.13 U2
Start of Hot Functional Tests | 2036-12-29 | HP | 2.3.7 U2
Start of Fuel Loading (U2) [logic to be defined] | 2037-06-18 | HP | 2.4.1 U2
MBIF Hold Point Release | 2026-01-01 | New SSA Milestones
ONR Supply Chain Management Inspection | 2026-01-01 | New SSA Milestones
EA Inspection - Intermediate Level Waste (ILW) Store | 2026-01-01 | New SSA Milestones
EA Inspection - Construction Water Discharge Activity (CWDA) Permit | 2026-01-01 | New SSA Milestones
ONR Construction Design Management (CDM) Inspection | 2026-02-01 | New SSA Milestones
ISO 45001 SV 1 | 2026-03-01 | New SSA Milestones
ISO 27001 Stage 2 | 2026-03-01 | New SSA Milestones
PAS 2080 SV 1 | 2026-03-01 | New SSA Milestones
Temporary Sea Defence Hold Point Release | 2026-04-01 | New SSA Milestones
ONR Inspection on Design Maturity | 2026-04-01 | New SSA Milestones
Summer Readiness | 2026-04-01 | New SSA Milestones
ONR Security and Safeguards Inspection | 2026-05-01 | New SSA Milestones
ISO 27001 Stage 1 | 2026-01-01 | New SSA Milestones
Unit 1 Concrete Batch commissioning | 2026-05-01 | New SSA Milestones
Desalination Plant readiness | 2026-06-01 | New SSA Milestones
Post implementation of Organisational Learning Procedure changes | 2026-06-01 | New SSA Milestones
Combined Discharge Outfall (CDO) Use commencement | 2026-06-01 | New SSA Milestones
Care & Maintanance Hold Point Release | 2026-07-01 | New SSA Milestones
ONR Inspection on Governance and Internal Challenge | 2026-07-01 | New SSA Milestones
Drive shaft commence | 2026-08-01 | New SSA Milestones
ONR Inspection on control of work | 2026-08-01 | New SSA Milestones
ISO 45001 SV2 | 2026-08-01 | New SSA Milestones
Readiness for Winter 2026 | 2026-09-01 | New SSA Milestones
SSSI Assurance | 2026-09-01 | New SSA Milestones
Commencement of main excavation on the MCA | 2026-10-01 | New SSA Milestones
ONR Inspection on Internal Challenge and Decision making | 2026-10-01 | New SSA Milestones
ISO 27001 SV1 | 2026-10-01 | New SSA Milestones
Dewatering Hold Point | 2026-10-01 | New SSA Milestones
ISO 9001 SV | 2026-11-01 | New SSA Milestones
ONR Inspection on handover of Rail line | 2026-11-01 | New SSA Milestones
Winter Shutdown Assurance 2026 | 2026-12-01 | New SSA Milestones
ISO 14001 SV | 2026-10-01 | New SSA Milestones
ONR Construction Fire Safety & Emergency Arrangements | 2027-02-01 | New SSA Milestones
NIST CSF 2 Version 2 - Score of 3 (top end of Zone 3) | 2026-03-30 | New SSA Milestones
Cyber Security - Respond and Recover Capability | 2026-12-31 | New SSA Milestones
Annual IT Health Check - All actions closed | 2026-06-30 | New SSA Milestones
Assurance of EDF SOC (Decision on EDF/TCS SOC) | 2026-09-30 | New SSA Milestones

## Lines of Defence
Line 0 - Supply Chain
Line 1 - Delivery
Line 1 - Corporate Functions
Line 2 - Corporate Functions
Line 3 - Independent
Line 4 - External

## Level IDS
Level 1 ID (not particularly relevant) | Level 2 Process ID (Audit Title)
1.0 - Design to Accept | 1.1 - Specify Requirements
10.0 - Configuration & Replication Management | 1.2 - Manage Design
11.0 - Supply Chain Management | 1.3 - Accept & Handover Design
12.0 - People | 10.1 - Manage Requirements and Replication
13.0 - Corporate Governance | 10.2 - Manage Interfaces
14.0 - Information Technology & Services | 10.3 - Manage Information
15.0 - Finance & Accounting | 10.4 - Manage Baseline Reference Configuration
2.0 - Manufacture to Deliver | 10.5 - Manage Configuration Change
3.0 - Construct to Handover | 11.1 - Procurement
4.0 - Commission to COD | 11.2 - Contract Management
5.0 - Operate to Decommission | 11.3 - Supplier Relationship Management
6.0 - Health, Safety, Security & Environment | 11.4 - Supply Chain Performance Management
7.0 - Manage Safety Case | 12.1 - Recruitment
8.0 - Assurance, Compliance & Quality | 12.2 - Organisational Development
9.0 - Project Management & Controls | 12.3 - HR Services
12.4 - Performance Management
12.5 - Onboarding
12.6 - Saying Goodbye
12.7 - Learning & Growing
13.1 - Stakeholder Relations
13.2 - Legal Services & Administration
13.3 - Corporate Performance & Governance
14.1 - Manage Solution Applications
14.2 - Manage IT Infrastructure
14.3 - Data Management
14.4 - Manage Information Security
14.5 - IT Support Management & Operations
15.1 - Financial Planning & Forecasting
15.2 - Funding & Investment Case Management
15.3 - Financial Risk Management
15.4 - Accounting & Statutory Financial Reporting
15.5 - Treasury
2.1 - Manage Manufacturing Readiness
2.2 - Oversee Manufacturing
2.3 - Release Equipment
2.4 - Coordinate & Receive Shipment
2.5 - Preservation
2.6 - Handover to Construction
3.1 - Preparation for Construction
3.2 - Planning & Sequencing
3.3 - Oversee Construction Works
3.4 - Handover
3.5 - CDM Management
3.6 - Site Operations & Construction Management
3.7 - Care & Maintenance of Assets & Equipment
4.1 - Prepare
4.2 - Execute Commissioning Work Pack
4.3 - Verify
4.4 - Transfer of Responsibility
6.1 - Industrial Health & Safety
6.2 - Emergency Response & Business Continuity
6.3 - Physical Security
6.4 - Environmental & Sustainability Management
6.5 - Nuclear Safety
6.6 - Facilities Management
7.1 - Manage Safety Case
8.1 - Compliance Requirements Management
8.2 - Assurance
8.3 - Quality
8.4 - Continuous Improvement
9.1 - Scope Management
9.2 - Estimating
9.3 - Planning & Schedule Management
9.4 - Cost Management
9.5 - Change Management
9.6 - Risk Management
9.7 - Project Reporting & Communications

## SSA Quality Column Definitions
Column Title | Definition | Type | Priority | Why?
Planned End Date | Defined as end of fieldwork. i.e. Report accepted and stored, Actions in Insight and agreed with Auditee. This is not complete closure of the audit in Insight as this is dependent on Actions being closed which may have lengthy timescales and are outside of the control of the SSA Quality Team (Agreed with Alex Boyce 17/10/2024). | Hold Point | 1 | If the hold point audit is required to aid in signing off the hold point then it must take priority as it will potentially delay schedules if not completed in a timely manner
Number of Level 2 Procedures | This is to help with planning and is the number of level 2 procedures that sit under the top level process in IMS. | Internal IMS Audit | 2 | These procedures have been assessed as Implemented and Published on IMS. Priority is based on opinions of QA Team at this point in time.
Source | Where we have sourced information from to build the audit plan (mainly a filter) | 2nd Line Quality Assurance | 3 | 2nd Line quality focused SME Assurance Activities. These procedures are from the QMS.
Risk Ranking | From Extract Sheet sent by C.Thompson on portfolio risk (SNAPSHOT) | One-off audits | 4 | Intelligence led audits where there is specific interest to a key stakeholder.
Risk ID | Legacy Risk ID form Portfolio Risk document provided
Risk Theme | Risk Theme form Portfolio Risk document provided
Risk Description | Risk Description form Portfolio Risk document provided
|  | Audit Duration to close | Number of procedures | Reasoning
|  | 1 Months (20 Days) | 1 | One procedure only involves one auditee team so realtively straightforward.
|  | 1.5-2 Months (40 days) | 2 to 4 | Slight increase in complexity hence allowing another month to agree actions and resolve issues
|  | 2-2.5 Months (60 days) | 5 to 8 | Further increase in complexity likely to have multple auditees and their teams, will take consideably longer to conduct the audit and agree any actions/ resolve issues.
|  | 2.5-3 Months (75 days) | 9 | Complex cases
|  | 2 Months (60 days) | SA | Self Assesment Only - this is because we have date for Self Assement to begin and then we will allow approximately 6 months for that to be completed as an indicative guide. 2 month audit window for QA Team Audit.
|  | No | Audit Activity | Timeline ~ 15/20 working days 1 Procedure | Notification
|  | 1 | Notification Letter | 1 day | 1 month before Audit Opening (at the latest)
|  | 2 | Audit Preparation 1/2 | 2 day
|  | 3 | Audit Plan | 1 day | 2 weeks before Audit Opening (at the latest)
|  | 4 | Audit Preparation 2/2 | 3 days
|  | 5 | Audit Opening - Closure (Fieldwork duration) | 1-2 days
|  | 6 | Audit Report - Less narative | 2 days | 2 weeks after Audit closing meting (at the latest)
|  | 7 | Audit report - Final version | 1 day
|  | 8 | Agreement of Corrective actions | 1 day
|  | 9 | Corrective actions into Insight | 1day
|  | 10 | Chasing actions | 1 day
SSA Internal Quality Audit Team - Further details on BRAG and RAG (Audit specific)
BRAG Completion (Blue/Red/Amber/Green)
|  | Status | Meaning | Example criteria
|  | Blue | Audit fieldwork is complete and report distributed | • Defined as end of fieldwork. i.e. Report accepted and stored, Actions in Insight and agreed with Auditee.
|  | Green | Audit progressing as planned. | • Audit not started but on-track • Audit started on time • All scheduled activities are on track • No major issues or delays reported
|  | Amber | Some deviations from the plan, but recovery possible. | • Audit started late but ongoing • Resource or scheduling issues identified but manageable • Minor delays in data collection, interviews or access
|  | Red | Audit is significantly off track and requires interventions. | • Audit not started as planned • Major scheduling conflicts or lack of resources • Critical access issues or non-cooperation
RAG Outcome (Outcome following end of audit)
|  | Status | Meaning | Example criteria
|  | Green | Effective: The assessed governance arrangements, risk management practices, and internal controls were adequately established and functioning effectively. The issues identified during the audit are considered minor and unlikely to impact the achievement of the objectives of the audited area, provided that only Observations (OBS) AND/OR Opportunities for Improvement (OFI) were raised. | • No NC – Minor observations / OFI that do not impact compliance
|  | Amber | Improvement Needed: The assessed governance arrangements, risk management practices, and internal controls were partially established and operational but require significant improvement. Issues identified during the audit have the potential to impact the achievement of the objectives of the audited area, particularly if any Minor Non-Conformities (NC) were raised. Some non-conformities or gaps exist, but they can be addressed without major operational impact. | • Minor NCs – corrective actions required within a reasonable timeframe
|  | Red | Not Effective: The assessed governance arrangements, risk management practices, and internal controls were neither adequately established nor functioning. Issues identified during the audit pose a significant risk of severely compromising the achievement of the objectives of the audited area, particularly if any Major Non-Conformities (NC) were raised. Major issues found that require urgent corrective action. | • Major NC or systemic failures – regulatory non-compliance – immediate corrective actions required

## Directorate (Audit team)
List of Directorates
Safety, Security and Assurance
Technical
Land
Human Resources
ESG
Legal
Pre-Operations
Finance & Investor Relations
IT
CIBOP Programme
Civil Works Programme
Delivery Integration
MEHA Programme
NI Programme
Site Delivery
Corporate Operations
N/A
PMO
PDO Quality
Supply Chain
Digital

## Procedures
Audit Unique Reference | Level 1 ID (not particularly relevant) | Level 2 Process ID (Audit Title) | Related Procedures (these control the process) | Related Procedure Number | Auditee Role | Auditee Name | Directorate | Proposed Date (Based on Priority by DD = 11.1 - 3, 2.1 - 5, 3.1 - 3, 12.1 - 5, 13.1 and it may be worth looking at 2.1)
1 | 1.0 - Design to Accept | 1.1 - Specify Requirements | Capture Requirements for Design Manage Responsible Designer Project Work Request | SZC-D2A-PRO-002 SZC-D2A-PRO-003 | Replication and Configuration Manager | Paul Sutherland | Engineering & Delivery
2 | 1.0 - Design to Accept | 1.2 - Manage Design | Produce Design Deliverables Provide New ECS Code Manage Design Collaboration | SZC-D2A-PRO-006 SZC-D2A-PRO-005 | Replication and Configuration Manager | Paul Sutherland | Engineering & Delivery
3 | 1.0 - Design to Accept | 1.3 - Accept & Handover Design | Assemble and Issue Design Packages | SZC-D2A-PRO-001 |  |  | Engineering & Delivery
4 | 10.0 - Configuration & Replication Management | 10.1 - Manage Requirements and Replication | Design Requirement (FOAK Non Safety Case) Management SZC Replication Procedure Ongoing Management of Requirements | SZC-CON-PRO-015 SZC-CON-PRO-017 | Requirements Management Lead Replication and Configuration Manager | Philip Holland Paul Sutherland Ovidiu Bolea | Engineering & Delivery
5 | 10.0 - Configuration & Replication Management | 10.2 - Manage Interfaces | Manage Construction Interface Data Manage Delivery Interfaces Manage Design Interfaces | SZC-CON-PRO-016 SZC-CON-PRO-018 SZC-CON-PRO-005 | Pre-Construction Planning Lead Delivery Integration Director Engineering Design and Delivery Manager | Nick Stockwell David Redpath Patrick Griffith | Engineering & Delivery
6 | 10.0 - Configuration & Replication Management | 10.3 - Manage Information | Control Construction Documents Federating Models | SZC-CON-PRO-012 | Replication and Configuration Manager | Paul Sutherland Ovidiu Bolea | Engineering & Delivery
7 | 10.0 - Configuration & Replication Management | 10.4 - Manage Baseline Reference Configuration | Manage Non-permanent Works Site Configuration Prepare Reference Configuration | SZC-CON-PRO-010 | Configuration Manager (NPW) | Adam Vernon Ovidiu Bolea | Engineering & Delivery
8 | 10.0 - Configuration & Replication Management | 10.5 - Manage Configuration Change | Issue (DEN) Design Evolution Notice Manage Construction Change - Field Change Request (FCR) Manage Contract Transfer Sheet Manage Design Change Manage Design Open Point Manage Evolutions in the Project List of Applicable Documents Manage Exemption in the Lists of Applicable Documents Manage Non-Permanent Baseline Change Manage Post-Handover Open Point Manage NNB Engineering Design Development Manage Referential Change | SZC-CON-PRO-001 SZC-CON-PRO-011 SZC-CON-PRO-003 SZC-CON-PRO-004 SZC-CON-PRO-006 SZC-CON-PRO-007 SZC-CON-PRO-008 SZC-CON-PRO-009 SZC-CON-PRO-013 | Replication and Configuration Manager (NPW)Requirements Management Lead | Paul Sutherland Adam Vernon Philip Holland Ovidiu Bolea Sarah Williamson Ovidiu Bolea | Engineering & Delivery
9 | 11.0 - Supply Chain Management | 11.1 - Procurement | AGS - Procurement Management of Revisions, Additions or Deletions to the Contract Baseline Library | SZC-SCM-PRO-001 SZC-SCM-PRO-004 | Head of Commercial Governance and Perf | Greg Brown | Commercial
10 | 11.0 - Supply Chain Management | 11.2 - Contract Management | AGS - Contract Management Contract Administration | SZC-SCM-PRO-002 | Head of Commercial Governance and Perf | Greg BrownGreg Brown | Commercial
11 | 11.0 - Supply Chain Management | 11.3 - Supplier Relationship Management | AGS - Supplier Relationship Management Supplier Mapping | SZC-SCM-PRO-003 | Head of Commercial Governance and Perf | Greg BrownGreg Brown | Commercial
12 | 11.0 - Supply Chain Management | 11.4 - Supply Chain Performance Management | Governance
13 | 12.0 - People | 12.1 - Recruitment | Recruit Employee Recruit or Onboard Contractor Rehire Managed Service Worker | SZC-PEO-PRO-011 SZC-PEO-PRO-010 | Head of HR Business Partnering Head of People - Civils | Katie Figg Beverley Pickeringshaw Rachel Kerry Marta Carnicero | HR
14 | 12.0 - People | 12.2 - Organisational Development | Management of Organisational Change Manage Board Membership | SZC-PEO-PRO-009 SZC-COG-PRO-007 | Head of SZC HR Operations Company Secretary | Rachel Kerry Asha Magnus | HR Legal Affairs
15 | 12.0 - People | 12.3 - HR Services | Transfer, Extend And Update Employment Details | SZC-PEO-PRO-012 |  |  | HR
16 | 12.0 - People | 12.4 - Performance Management | Create Roles, Competencies and Development Actions | SZC-PEO-PRO-002 |  |  | HR
17 | 12.0 - People | 12.5 - Onboarding | Mobilise Contract Partner To Site Provide Limited Access for Managed Service Workers Rehire and Terminate Access to Sizewell C Provide Managed Service Worker, Re-hire and Terminate Access to Sizewell C Provide Temporary Managed Service Worker Access To Sizewell C Undertake Alcohol & Drug Test Obtain National Security Vetting Clearance | SZC-C2H-PRO-011 SZC-C2H-PRO-008 | Site Construction Lead Head of EAU Occupational Health Manager Head of Security and Safety Assurance | Matt Reed Chris Young Ceri Bryant Andrew Wilkinson | Engineering & Delivery HR Safety Security & Assurance
18 | 12.0 - People | 12.6 - Saying Goodbye | Manage Leavers Remove Sizewell C Managed Service Worker Access | SZC-PEO-PRO-008 | Head of HR Business Partnering | Katie Figg Rachel Kerry Marta Carnicero | HR
19 | 12.0 - People | 12.7 - Learning & Growing | Assess Individual Competency Develop New Training Enrol in Training Evaluate Training Implement Training Events | SZC-PEO-PRO-001 SZC-PEO-PRO-003 SZC-PEO-PRO-004 SZC-PEO-PRO-005 SZC-PEO-PRO-006 | Head of SZC HR Operations | Rachel Kerry | HR
20 | 13.0 - Corporate Governance | 13.1 - Stakeholder Relations | Manage Communications Virtual Data Room Virtual Data Room Investor Exchange Obligations to Report to Government Operative Information Database (OID) Shareholder Reporting Obligations | SZC-COG-PRO-001 SZC-COG-PRO-005 SZC-COG-PRO-011 SZC-COG-PRO-004 | Head of SZC Communications Financing & Economic Regulation | Ben Geoghegan Sebastian Pampe Lynne Kellett | Communications Legal Affairs
21 | 13.0 - Corporate Governance | 13.2 - Legal Services & Administration | Administer and Operate Boards and Board Committees Manage Freedom of Information Requests Access Legal Advice | SZC-COG-PRO-006 SZC-COG-PRO-010 SZC-COG-PRO-002 | Company Secretary Head of Legal SZC | Asha Magnus Lynne Kellett | Legal Affairs
22 | 13.0 - Corporate Governance | 13.3 - Corporate Performance & Governance | Manage Financial Authorities Framework Manage Board Committee Terms of Reference Manage Company Policies | SZC-COG-PRO-003 SZC-COG-PRO-008 SZC-COG-PRO-009 | Finance Director Company Secretary Head of Nuclear Compliance, Audit and Pl | James WeeksAsha MagnusFran Gradie | Chief Financial Officer Legal Affairs Safety Security & Assurance
23 | 14.0 - Information Technology & Services | 14.1 - Manage Solution Applications | Deliver Software Application Solution Maintain Application Solution Manage Application Testing and QA Manage Change to Live Production IT Environment Manage Retirement of Obsolete Application | SZC-ITS-PRO-002 SZC-ITS-PRO-004 SZC-ITS-PRO-005 SZC-ITS-PRO-006 SZC-ITS-PRO-015 | Head of Digital & IT (SZC) | Nick Harvey | Chief Financial Officer
24 | 14.0 - Information Technology & Services | 14.2 - Manage IT Infrastructure | Manage Cloud Infrastructures Manage IT Network & Telecom Services Manage Servers | SZC-ITS-PRO-007 SZC-ITS-PRO-009 SZC-ITS-PRO-016 | Head of Digital & IT (SZC) | Nick Harvey | Chief Financial Officer
25 | 14.0 - Information Technology & Services | 14.3 - Data Management | Manage Database Operations Manage Master and Reference Data Manage Storage and Data Backup | SZC-ITS-PRO-008 SZC-ITS-PRO-014 SZC-ITS-PRO-017 | Head of Digital & IT (SZC) | Nick Harvey | Chief Financial Officer
26 | 14.0 - Information Technology & Services | 14.4 - Manage Information Security | Manage IT Security Incidents Manage IT Security Threats | SZC-ITS-PRO-010 SZC-ITS-PRO-011 | Head of Digital & IT (SZC) | Nick Harvey | Chief Financial Officer
27 | 14.0 - Information Technology & Services | 14.5 - IT Support Management & Operations | Control Access to Information Systems and Assets Enable Capacity & Provisioning Management Manage IT Service Continuity Manage IT Service Transition Monitor and Evaluate IT Service Performance Perform Event Management Perform Incident Management Perform Problem Management Service Catalogue Management Service Request Management | SZC-ITS-PRO-001 SZC-ITS-PRO-003 SZC-ITS-PRO-012 SZC-ITS-PRO-013 SZC-ITS-PRO-018 SZC-ITS-PRO-019 SZC-ITS-PRO-020 SZC-ITS-PRO-021 SZC-ITS-PRO-022 SZC-ITS-PRO-023 | Head of Digital & IT (SZC) | Nick Harvey | Chief Financial Officer
28 | 15.0 - Finance & Accounting | 15.1 - Financial Planning & Forecasting | Forecast Monthly Cash Call Undertake Budget and Forecast Financial Planning | SZC-FIN-PRO-008 SZC-FIN-PRO-013 | Finance Director | James Weeks | Chief Financial Officer
29 | 15.0 - Finance & Accounting | 15.2 - Funding & Investment Case Management | Establish and Maintain Investment Case Manage SZC Shareholder Funds Transfer Dispose of Property Site | SZC-FIN-PRO-007 SZC-FIN-PRO-004 | Head of Investment and Investors Head of Treasury | Andy Wise Andrew Grant James Week Min Li | Chief Financial Officer
30 | 15.0 - Finance & Accounting | 15.3 - Financial Risk Management | Evaluate Supplier Credit Risk Manage Construction Insurance Manage Pre And Post Insolvency Risk Manage Foreign Exchange Risk | SZC-FIN-PRO-005 SZC-FIN-PRO-003 SZC-FIN-PRO-009 | Head of Treasury Head of Insurance and Risk | Andrew Grant Thomas Darnell James Week Min Li | Chief Financial Officer
31 | 15.0 - Finance & Accounting | 15.4 - Accounting & Statutory Financial Reporting | Perform Tax Governance Activities Prepare and Submit Financial Accruals Produce Financial Performance Reports Process Inter and Intra Company Transactions | SZC-FIN-PRO-001 SZC-FIN-PRO-010 SZC-FIN-PRO-012 SZC-FIN-PRO-011 | Tax Manager Finance Director Finance Director | Janice Britton James Weeks | Chief Financial Officer
| 15.0 - Finance & Accounting | 15.4 - Accounting & Statutory Financial Reporting
32 | 15.0 - Finance & Accounting | 15.5 - Treasury | SZC Treasury Short-Term Liquidity Management Manage Payments and Retentions | SZC-FIN-PRO-002 | Head of Treasury | Andrew Grant James Week Min Li | Chief Financial Officer
33 | 2.0 - Manufacture to Deliver | 2.2 - Oversee Manufacturing | Conduct Manufacturing Surveillance Conduct Pressure Systems Safety Regulations and Safety Case Policy Surveillance Expedite Contract Partner Manage Equipment Qualification Programme Manage Manufacturing Non-Conformance Manage FUDs Modulate Manufacturing Surveillance and Suspend and Restart Manufacturing | SZC-M2D-PRO-004 SZC-M2D-PRO-016 SZC-M2D-PRO-007 SZC-M2D-PRO-005 SZC-M2D-PRO-006 | PDO Quality Programme Director NI Eng & Delivery Programme Director | Steven Heard Sebastien Bachere | Engineering & Delivery
34 | 2.0 - Manufacture to Deliver | 2.3 - Release Equipment | Manage Shipment Authorisation Request (SAR) Provide Quality Release Certificate | SZC-M2D-PRO-011 SZC-M2D-PRO-003 | PDO Quality Programme Director | Steven Heard | Engineering & Delivery
35 | 2.0 - Manufacture to Deliver | 2.4 - Coordinate & Receive Shipment | Manage Transportation Arrangements Managing Road Freight into SZC | SZC-M2D-PRO-002 SZC-M2D-PRO-017 | PDO Quality Programme Director Site Delivery Lead | Steven Heard Si Middleton - Burrows | Engineering & Delivery
36 | 2.0 - Manufacture to Deliver | 2.5 - Preservation | Care and Maintenance Activities Conduct Warehouse Management Manage Spare PartsPerform Construction Asset Reviews Repairs During Manufacturing | SZC-M2D-PRO-001 SZC-M2D-PRO-010 SZC-M2D-PRO-012 SZC-M2D-PRO-014 | NI Eng & Delivery Programme Director Site Operations Director NI Eng & Delivery Programme Director | Sebastien Bachere David Peacop Sebastien Bachere | Engineering & Delivery
37 | 2.0 - Manufacture to Deliver | 2.6 - Handover to Construction | Conduct Final Mile Delivery Coordinate Equipment and Material Call Off | SZC-M2D-PRO-009 SZC-M2D-PRO-008 | Site Operations Director | David Peacop | Engineering & Delivery
38 | 3.0 - Construct to Handover | 3.1 - Preparation for Construction | Execute Work Package Prepare, Review and Accept Risk Assessment and Method Statements Standard Provide Delivery Work Package Checklists | SZC-C2H-PRO-015 SZC-C2H-STA-004 SZC-C2H-PRO-020 | NI Eng & Delivery Programme Director Head of Site Health, Safety & Wellbeing NI Eng & Delivery Programme Director | Sebastien Bachere Keith Prince | Engineering & Delivery
39 | 3.0 - Construct to Handover | 3.2 - Planning & Sequencing | Create Construction Sequence Plan | SZC-C2H-PRO-011 |  |  | Engineering & Delivery
40 | 3.0 - Construct to Handover | 3.3 - Oversee Construction Works | Manage Site Surveillance Management of Excavations & Services Standard Management of Lifting Operations Standard Management of Occupational Health, Hygiene and Wellbeing Standard Management of Scaffolds Standard Safe Operations for Marine Construction Standard SZC Review and Approve End of Erection Status Report Management of Confined Spaces Standard Management of Lone Working Standard Occupational Health And Safety Inspections and Audits Standard | SZC-C2H-PRO-008 | PDO Quality Programme Director Site Construction Lead Site Delivery Lead Head of Site Health, Safety & Wellbeing Head of Security and Safety Assurance | Steven Heard Matt Reed Rick Watler Keith Prince Si Middleton - Burrows Andrew Wilkinson | Engineering & Delivery
41 | 3.0 - Construct to Handover | 3.4 - Handover | Handover of Buildings Handover to Commission Manage Site Works Handover Review and Approve End of Construction Status Report | SZC-C2H-PRO-016 SZC-C2H-PRO-017 SZC-C2H-PRO-022 SZC-C2H-PRO-013 | NI Eng & Delivery Programme Director PDO Quality Programme Director | Sebastien Bachere Steven Heard | Engineering & Delivery
42 | 3.0 - Construct to Handover | 3.5 - CDM Management | Control Unplanned Work Activities Manage Provision and Use of Work Equipment Manage Temporary Works Provide Risk Assessments and Method Statements | SZC-C2H-PRO-003 SZC-C2H-PRO-009 SZC-C2H-PRO-004 SZC-C2H-PRO-010 | Site Establishment & Ops Director CWP Eng & Technical Lead Head of Site Health, Safety & Wellbeing | John Brooks Bruno Gondouin Keith Prince | Engineering & Delivery
43 | 3.0 - Construct to Handover | 3.6 - Site Operations & Construction Management | Communicate with Adjacent Facilities | SZC-C2H-PRO-008 |  |  | Engineering & Delivery
44 | 3.0 - Construct to Handover | 3.7 - Care & Maintenance of Assets & Equipment | Manage As-Built Utilities & Construction Hazard Information Manage Disposal of Surplus and Scrap Materials and Equipment Preservation/Cocooning Repairs During Construction Control Maintenance of Installed Plant and Equipment | SZC-C2H-PRO-025 SZC-C2H-PRO-018 SZC-C2H-PRO-019 SZC-C2H-PRO-021 SZC-C2H-PRO-001 | SZC Technical Programme Director Site Operations Director NI Eng & Delivery Programme Director | Manus O'Donnell David Peacop Sebastien Bachere | Engineering & Delivery Operations
45 | 4.0 - Commission to COD | 4.1 - Prepare | Assign Commissioning Grade Define Commissioning Test Configuration Design Commissioning TestDevelop Commissioning Instruction Develop Commissioning Test Package Identify Required Equipment for Commissioning Manage Commissioning Control Points | SZC-C2C-PRO-001 SZC-C2C-PRO-003 SZC-C2C-PRO-004 SZC-C2C-PRO-005 SZC-C2C-PRO-006 SZC-C2C-PRO-009 SZC-C2C-PRO-010 | NI Eng & Delivery Programme Director | Sebastien Bachere | Engineering & Delivery
46 | 4.0 - Commission to COD | 4.2 - Execute Commissioning Work Pack | Execute Commissioning Instruction Manage Commissioning Observations Manage Commissioning Open Points Manage Commissioning Surveillance Of Contractor Led Activities Manage Commissioning Surveillance Of NNB Led Activities Manage Maintenance During Commissioning Manage Spares and Consumables During Commissioning Manage System Commissioning File Manage Testing Anomalies Update Decommissioning Plan | SZC-C2C-PRO-007 SZC-C2C-PRO-012 SZC-C2C-PRO-013 SZC-C2C-PRO-014 SZC-C2C-PRO-015 SZC-C2C-PRO-016 SZC-C2C-PRO-017 SZC-C2C-PRO-018 SZC-C2C-PRO-019 SZC-C2C-PRO-024 | NI Eng & Delivery Programme Director | Sebastien Bachere | Engineering & Delivery
47 | 4.0 - Commission to COD | 4.3 - Verify | Reconfigure Plant for Test Verify Commissioning Instruction Verify Commissioning Test Results | SZC-C2C-PRO-020 SZC-C2C-PRO-025 SZC-C2C-PRO-026 | NI Eng & Delivery Programme Director | Sebastien Bachere | Engineering & Delivery
48 | 4.0 - Commission to COD | 4.4 - Transfer of Responsibility | Complete Final Takeover Hand Plant Back to Construction Manage Commissioning Functional Takeover Turnover for Blocking/Isolation Turnover for Maintenance Turnover for Temporary Operation | SZC-C2C-PRO-002 SZC-C2C-PRO-008 SZC-C2C-PRO-011 SZC-C2C-PRO-021 SZC-C2C-PRO-022 SZC-C2C-PRO-023 | NI Eng & Delivery Programme Director | Sebastien Bachere | Engineering & Delivery
49 | 6.0 - Health, Safety, Security & Environment | 6.1 - Industrial Health & Safety | Control of Substances Hazardous to Health Standard Ensure Safe Control of Work Activities Main Site Fire Safety Plan Standard Management of Site Vehicles and Drivers Procedure Management of Tunnelling Operations Standard Traffic Management and Protection of Pedestrians Standard Work at Height Standard Avoidance of Overhead Services Safety Display Screen Equipment Ensure First Aid At Work Arrangements Ensure Safe Control of Manual Handling Manage Industrial Safety Contractor Evaluation Manage Occupational Health, Safety And Environmental Inspections Manage Personal Protection Equipment Work Equipment Standard Ensure Safe Control of Work at Height Manage Exposure to NoiseManage Hazardous Substances Management of HSE Investigations Standard | SZC-HSE-STA-014 SZC-HSE-PRO-046 SZC-HSE-STA-004 SZC-HSE-PRO-027 SZC-HSE-STA-012 SZC-HSE-STA-015 SZC-HSE-STA-013 SZC-HSE-PRO-018 SZC-HSE-PRO-060 SZC-HSE-PRO-014 SZC-HSE-PRO-023 SZC-HSE-PRO-019 SZC-HSE-PRO-021 SZC-HSE-PRO-031 SZC-HSE-STA-016 SZC-HSE-PRO-040 SZC-HSE-PRO-025 SZC-HSE-PRO-012 SZC-HSE-STA-006 | H&S Manager Head of Site Health, Safety & Wellbeing Passenger Transport Service Manager Programme Manager (M&T) Site Operations - Site Lead Site Construction Lead Head of Security and Safety Assurance Interface Oversight Face Manager | Glenn Whitten Keith Prince David Stuart Steve Lousley Spencer Bowdler Rick Watler Andrew Wilkinson Eoin O Brien Chris Hall | Engineering & Delivery
50 | 6.0 - Health, Safety, Security & Environment | 6.2 - Emergency Response & Business Continuity | Establish and Maintain Business Continuity Arrangements Establish, Maintain and Develop Emergency Preparedness Fire Prevention and Fire Safety Arrangements Plan & Administer Emergency Exercises | SZC-HSE-PRO-058 SZC-HSE-PRO-037 SZC-HSE-PRO-028 | Head of Security and Safety Assurance Head of Env Consenting and Compliance | Andrew Wilkinson Stuart Woodings Mina Golshan | Operations Safety Security & Assurance
51 | 6.0 - Health, Safety, Security & Environment | 6.3 - Physical Security | Assess Security Threats Assure Delivery Of Security Standards Specify Security Standards Control Access of People To Sites Control Site Vehicles Manage Export Control Licensing Cyber Security and Information Assurance Standard Instrumentation and Control Security Standard Manage Personal Overseas Travel Security Manage Security Event Manage Visitors Personnel Security Standard Physical Security Standard - Construction Visitor Management Standard | SZC-HSE-PRO-009 SZC-HSE-PRO-010 SZC-HSE-PRO-016 SZC-HSE-STA-017 SZC-HSE-STA-020 SZC-HSE-PRO-045 SZC-HSE-PRO-026 SZC-HSE-PRO-008 SZC-HSE-STA-021 SZC-HSE-STA-019 SZC-HSE-STA-018 | Site Security Manager Passenger Transport Service Manager Head of Legal SZC Head of Security and Safety Assurance | Mina Golshan Tim Newton David Stuart Lynne Kellett Andrew Wilkinson | Engineering & Delivery Legal Affairs Safety Security & Assurance
52 | 6.0 - Health, Safety, Security & Environment | 6.4 - Environmental & Sustainability Management | Manage Physical Samples Apply for and Maintain Nuclear and Environmental Consent, Permit or Licence Assess Environmental Aspects and Impacts Control Contaminated Land and Groundwater Develop and Manage Environmental Requirements Environmental Optimisation Standard Integrated Waste Management Standard Land Quality Management Standard Manage the Environment Case Perform Environmental Monitoring Dispose of Physical Samples View Physical Sample Withdraw or Change Physical Sample | SZC-HSE-PRO-047 SZC-HSE-PRO-032 SZC-HSE-PRO-002 SZC-HSE-PRO-033 SZC-HSE-PRO-035 SZC-HSE-STA-001 SZC-HSE-STA-022 SZC-HSE-STA-002 SZC-HSE-PRO-007 SZC-HSE-PRO-042 SZC-HSE-PRO-048 SZC-HSE-PRO-049 SZC-HSE-PRO-050 | PDO Quality Programme Director Head of Env Consenting and Assurance Head of Env Consenting and Compliance | Steven Heard Stuart Woodings Steven Heard | Engineering & Delivery
54 | 6.0 - Health, Safety, Security & Environment | 6.5 - Nuclear Safety | Maintain Nuclear Site Licence Boundary Address Differing Professional Opinions Control of Nuclear MatterDevelop Decommissioning Plan Provide Nuclear Site Licence Warning Notices Radiation Protection Advisor Appointment Radiological Safety Standards Radon Management Review Radiation Exposure Undertake Station Commissioning Testing Conduct Supply Chain Surveillance | SZC-HSE-PRO-024 SZC-HSE-PRO-022 SZC-HSE-PRO-034 SZC-HSE-PRO-017 SZC-HSE-PRO-029 SZC-HSE-PRO-003 SZC-HSE-STA-003 SZC-HSE-PRO-059 SZC-HSE-PRO-043 SZC-HSE-PRO-053 | Site Security Manager Head of INA Head of ESG & Radiation Strategy Head of Nuclear Compliance, Audit and Pl | Tim Newton Simon Barnard Pete Bryant Fran Gradie Sebastien Bachere | Engineering & Delivery Safety Security & Assurance
55 | 6.0 - Health, Safety, Security & Environment | 6.6 - Facilities Management | Establish Management of Property Sites Manage Facilities | SZC-HSE-PRO-011 |  | Mike Lavelle Chris Hall
56 | 7.0 - Manage Safety Case | 7.1 - Manage Safety Case | Control Modifications During Construction & Commissioning Manage Generic Design Assessment Findings Manage Safety Reports | SZC-MSC-PRO-001 SZC-MSC-PRO-002 SZC-MSC-PRO-003 | Head of Design Authority | Paul Marks Jonathan Jones | Engineering & Delivery
57 | 8.0 - Assurance, Compliance & Quality | 8.1 - Compliance Requirements Management | Control of Licensed Site Property Transactions Manage Change To Development Consent Order and Deed of Obligation Manage Discharge Of Development Consent Order Requirements, Deemed Marine Licence Conditions and Deed of Obligation Requirements Maintain Legislation & Regulatory Landscape Control Regulatory Approved Management Arrangements Manage Interfaces with Regulators Define Manage and Release Tertiary Hold Points |  | Head of Land Advanced Works & DCO Leads Head of Legal SZC Head of Nuclear Compliance, Audit and Pl | Christopher Nunn Richard Bull Lynne Kellett Fran Gradie John Brooks | Commercial Engineering & Delivery Legal Affairs Engineering & Delivery
58 | 8.0 - Assurance, Compliance & Quality | 8.2 - Assurance | Apply Concurrence Develop or Amend Company Procedure or Standard Implement Bulk Change to IMS Implement Company Procedure or Standard Manage Environmental Objectives Manage Independent Assessment Programme Manage Regulatory Commitments Perform Independent Assessment Perform Independent Technical Assessment Provide Formal Advice from Assurance Develop/Amend Contractors Handbook Procedure | SZC-ACQ-PRO-005 SZC-ACQ-PRO-009 SZC-ACQ-PRO-003 SZC-ACQ-PRO-028 SZC-ACQ-PRO-029 SZC-ACQ-PRO-014 SZC-ACQ-PRO-017 SZC-ACQ-PRO-019 SZC-ACQ-PRO-022 SZC-ACQ-PRO-023 | Head of INA Head of Nuclear Compliance, Audit and Pl Head of ESG & Radiation Strategy | Simon Barnard Fran Gradie Pete Bryant Mike Lavelle | Safety Security & Assurance
59 | 8.0 - Assurance, Compliance & Quality | 8.3 - Quality | Conduct Supply Chain Audit Manage Contractor Site Non-Conformance Manage End of Manufacturing Report Manage Quality Execution Conduct Management Review Manage External Audit Of SZC Activities Manage Non-Conformance Perform Internal AuditSite Non-Conformances, Field Change Requests and Request for Information | SZC-ACQ-PRO-027 SZC-ACQ-PRO-004 SZC-ACQ-PRO-031 SZC-ACQ-PRO-018 SZC-ACQ-PRO-006 SZC-ACQ-PRO-013 SZC-ACQ-PRO-016 SZC-ACQ-PRO-020 SZC-ACQ-PRO-032 | PDO Quality Programme Director Head of Nuclear Compliance, Audit and Pl | Steven Heard Fran Gradie | Engineering & Delivery Safety Security & Assurance
60 | 8.0 - Assurance, Compliance & Quality | 8.4 - Continuous Improvement | Business Architecture Project Delivery Manage Business Architecture Project Pipeline Provide Business Architecture Project Governance Enable Continuous ImprovementInvestigate Incidents Perform Self AssessmentDeliver and Deploy Business Architecture Project | SZC-ACQ-PRO-024 SZC-ACQ-PRO-025 SZC-ACQ-PRO-026 SZC-ACQ-PRO-010 SZC-ACQ-PRO-011 SZC-ACQ-PRO-021 | Head of Digital & IT (SZC) Head of Digital & IT (SZC) Head of Nuclear Compliance, Audit and Pl | Nick Harvey Fran Gradie Matthew Preston | Chief Financial Officer Safety Security & Assurance
61 | 9.0 - Project Management & Controls | 9.1 - Scope Management | Conduct Project Gateway Readiness Review Conduct Project Initiation Manage Documents Manage Performance Measurement Baseline Scope Request for Information Review and Accept Project Deliverables Define, Manage and Release Key Hold Points Management of Generic Organisational Requirements Raise Technical Services Task Order | SZC-PMC-PRO-005 SZC-PMC-PRO-015 SZC-PMC-PRO-008 SZC-PMC-PRO-010 SZC-PMC-PRO-003 SZC-PMC-PRO-004 SZC-PMC-PRO-002 | Head of Programme Controls PDO Quality Programme Director Replication and Configuration Manager Technical Programme Director Head of Nuclear Compliance, Audit and Pl | Tommy Clarke Paul Sutherland Manus O'Donnell Fran Gradie Pawan Rathore | Engineering & Delivery Safety Security & Assurance
62 | 9.0 - Project Management & Controls | 9.2 - Estimating | Manage Cost Estimates | SZC-PMC-PRO-007 |  |  | Engineering & Delivery
63 | 9.0 - Project Management & Controls | 9.3 - Planning & Schedule Management | Manage Project Schedule | SZC-PMC-PRO-006 |  |  | Engineering & Delivery
64 | 9.0 - Project Management & Controls | 9.4 - Cost Management | Manage Project Cost | SZC-PMC-PRO-011 |  |  | Engineering & Delivery
65 | 9.0 - Project Management & Controls | 9.5 - Change Management | Manage Project Trend And Change Manage Early Warnings | SZC-PMC-PRO-014 | Head of Programme Controls | Tommy Clarke Pawan Rathore | Engineering & Delivery
66 | 9.0 - Project Management & Controls | 9.6 - Risk Management | Manage Project Risks and Opportunities | SZC-PMC-PRO-013 |  |  | Engineering & Delivery
67 | 9.0 - Project Management & Controls | 9.7 - Project Reporting & Communications | Manage and Provide Project Reporting Manage Enquiries and Complaints | SZC-PMC-PRO-016 SZC-PMC-PRO-009 | Head of Programme Controls Head of READ | Tommy Clarke Marjorie Barnes | Engineering & Delivery
68 | 11.0 - Supply Chain Management | Uncategorised at Level xx.x | Assurance Continuous Improvement Dispute Resolution Manage Contract Change Manage Contract Closure Market Engagement Sourcing Strategy Tendering Administer Construction All Risks Insurance Claim Administer Subcontracts (FIDIC Contracts) Assess Payment Application and Pay Contract Partner Avoid Contract DisputeAward Contract - NNB/RD (2,000-6,000 Contracts) Create procurement strategy Determine procurement route Determine purchasing need Evaluate Tender - NNB/RD (2,000-6,000 Contracts) Issue Invitation to Tender - NNB/RD (2,000-6,000 Contracts) Manage Changes to Baseline Contract Documentation Pre-Qualify Suppliers NNB/RD (2,000-6,000 Contracts) Procure low risk contract Produce market intelligence report Source Suppliers and Prepare for Pre-Qualification Questionnaire - NNB/RD (2,000-6,000) Source suppliers and prepare pre-qualification questionaire Acquire Goods and Services Manage Site Configuration Modification Management of Supply Chain Conflict of Interest | SZC-SCM-PRO-005 | Head of Commercial Governance and Perf | Greg Brown Lynne Kellett Lisa Reit Min Lin Marc Cohen
69 | 12.0 - People | Uncategorised at Level xx.x | Manage Contractor Exit | SZC-PEO-PRO-017 |  |  | Engineering & Delivery
70 | 2.0 - Manufacture to Deliver | Uncategorised at Level xx.x | Inspect And Handover Equipment And Materials
71 | 4.0 - Commission to COD | Uncategorised at Level xx.x | Develop Commissioning Test Develop Commissioning Test Configuration Identify Required Tools for Commissioning |  | NI Eng & Delivery Programme Director |  | Engineering & Delivery

## Pivot Table
Count of Planned End Date / Report published | Column Labels
| Amber | Amber Total | Blue |  | Blue Total | Green |  | Green Total | N/C | N/C Total | (blank) | (blank) Total | Grand Total
Row Labels | N/C |  | Amber | Green |  | Green | N/C |  | N/C |  | (blank)
Alvin Soomary | [6 empty] | 9 | 9 | 1 | 1 |  |  | 10
Christopher Thompson |  |  |  | 1 | 1 |  |  |  | 3 | 3 |  |  | 4
Clare Proctor | [8 empty] | 1 | 1 |  |  | 1
Emma Wells | [5 empty] | 1 | 4 | 5 | 4 | 4 |  |  | 9
Hilary Best | [8 empty] | 1 | 1 |  |  | 1
James Costello |  |  | 1 | 1 | 2 |  |  |  | 3 | 3 |  |  | 5
Katie Anderson-Cousins | [8 empty] | 2 | 2 |  |  | 2
Paul Gomar |  |  |  | 1 | 1 |  | 3 | 3 | 1 | 1 |  |  | 5
Sam Bulmer |  |  | 4 | 4 | 8 |  | 6 | 6 | 21 | 21 |  |  | 35
Stephen Mason |  |  | 2 | 3 | 5 |  | 1 | 1 | 6 | 6 |  |  | 12
Stephen Roast | [8 empty] | 3 | 3 |  |  | 3
Thomas Brazendale |  |  | 1 | 4 | 5 |  |  |  | 13 | 13 |  |  | 18
Vanessa Tsanang | 1 | 1 | 1 | 2 | 3 |  | 1 | 1 | 26 | 26 |  |  | 31
(blank)
Grand Total | 1 | 1 | 9 | 16 | 25 | 1 | 24 | 25 | 85 | 85 |  |  | 136

## Archive 2024
SS&A Assurance Tracker
*This tracker contains all SS&A Assurance activity to be shared within the SZC Integrated Assurance and Audit Plan (IAAP). Formal sharing with the IAAP currently covers activities with start dates running till the end of June 2025 . TC Ref: 101388569.
*Please ensure you Column F (Commentary) to initial, date, and comment on any changes to current activities, along with dating, initialling and commenting on new activities added. Any removal of entries, or sharing of the tracker, needs to be cleared through Alex Boyce or Fran Gradie.
Planning Information | [18 empty] | Assurance Outputs | [18 empty] | Internal Quality Audit information
Activity ID | Task / Assurance or Audit Activity Name | Assurance Activity Description | Commentary - Please use to indicate date and new additions, and any changes. | Category (See Category Types sheet) | Interest from the Regulator? | Will this activity Necessitate site access and support? | Assuring Function | Line of Defence | Planned Start Date | Planned End Date / Report published | Head of Function | Manager | Assurance Tool Used (See Assurance Tools sheet) | Function Assured | Linked Milestone | Linked Risk | Progress BRAG Status | Outcome RAG Status | Key findings/Comments | Related Licence Condition (If applicable) | Environmental Permit or Consent Linkage | Hold Point Linkage ID (If applicable) | Teamcenter document number | Insight Learning Report number | Number of Areas for Improvement (AFI's) | Number of observations | No of Opportunities for Improvement (OFI's) | No of Good Practices | No of Minor Non-conformances at end of activity | No of Minor Non-conformances LIVE | No of Major Non-conformances at end of activity | No of Major Non-conformances LIVE | Due date for Major non-conformances to be closed out | Actual date Major non-conformances closed out | No of Process Non-conformances at end of activity | No of Process Non-conformances LIVE | No of Material Non-conformances at end of activity | No of Material Non-conformances LIVE | Insight Audit Report Number | Lead Auditor | 2nd auditor / observer | SME/Technical expert | Lead Auditee | Source | Level 1 ID | Level 2 ID | Related Prodcures | Procedures
1 | Development and approval of the SZC Project Security Strategy | Self assessment | 16.10.24 - AW: Update, SZC Security Strategy completed on 30/08/2024, approved on 17/09/2024 and a copy sent to ONR on 27/09/2024. Level 2 Milestone achieved. IAAP now updated. | C | Yes | No | SS&A - Security & Conventional Safety Assurance | Line 4 - External | 2021-07-01 | 2024-08-21 | Andrew Wilkinson | Andrew Wilkinson | Self Assessment | Overall Project | SZC Project Security Strategy - Developed and approved |  | Blue | Green | 16.10.24 - AW: Update, SZC Security Strategy completed on 30/08/2024, approved on 17/09/2024 and a copy sent to ONR on 27/09/2024. Level 2 Milestone achieved. IAAP now updated. |  | N/A |  | 100902724 | N/A | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  |  | N/A
900 | 3rd party ISO45001 Gap analysis | ISO 45001 Gap analysis | 11.3.25 - AB: Retrospectively added to catpure curren major non-conformances. 24/05/2025 - PL: Record updated in line with closure of insight records on 23/05/25. All the major nc were closed. | R | No | Yes | External Review - LRQA | Line 4 - External | 2024-03-04 | 2024-03-05 | Andrew Wilkinson | Stephen Mason | Audit | Overall Project | N/A - No specific Milestone | Reputation (Social Licence) | Blue | Red | Action plan in place, support being provided by Peter Long and Christopher Thompson. Each of these findings is being discussed on weekly basis in the run-up to the ISO 45001 Stage 1 audit, hopeful that we can close each of these major non-conformances out by the 31st March 2025. Main owners are Sam Parker, Steve Mason, and Andrew Wilkinson. | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 2025-03-31 | 2025-06-24 | 0 | 0 | 0 | 0 | AUD-2028 | Peter Long (on behalf of (LRQA) |  | Stephen Mason | Sam Parker
57 | IMS Development | IMS Development - Review of the IMS Development Plan | 8.11.24 CT: On-track, just finishing off the report for Jo and Chris to review, then to be checked and signed off by Camila and Peter. 12.11.24 AG: Just waiting for Jo to confirm satisfaction of action re-wording, but almost complete. | C | Yes | No | SS&A - Quality Assurance | Line 2 - Corporate Functions | 2024-07-08 | 2024-11-05 | Fran Gradie | Christopher Thompson | Audit | SS&A - Quality Assurance | N/A - No specific Milestone | Quality | Blue | Red | Main findings are related to how the project was set up in the first place. Note this was outside of the control of the current team. Basic project control documentation such as Project Definition Document etc missing, that lead to other basic project management short falls. See audit report in Insight for full details. The report outlines Six non-conformances, and all Six non-conformances have now been resolved moving into the next stage of the IMS Project plan. Status of the actions is in Green. | N/A | N/A | N/A | N/A | N/A | 0 | 3 | 3 | 0 | 6 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | AUD-2282 | Camila | Adrian | N/A | Jo klepka | One-off audits | 8.0 - Assurance, Compliance & Quality | 8.2 - Assurance
2 | Perform Environmental Monitoring Procedure | Self assessment of procedure. | 16.10.24 AB: Contained within IAAP, following discussion with Sam Bulmer, status updated to complete, as completed this week. | C | No | Yes | SS&A - Environmental Services and Assurance | Line 1 - Corporate Functions | 2024-08-26 | 2024-09-20 | Stuart Woodings | Sam Bulmer | Self Assessment | SS&A - Environmental Services and Assurance | N/A - No specific Milestone | Environment | Blue | Green | A limited number of observations, non-conformances, process non-conformances, opportunities for improvement have been identified as part of this self-assessment. Good practice has also been observed and noted in this report. No major non-conformances have been identified. The common findings shared between the environmental disciplines are as follows: i) There is no formal briefing or training on the PEMP. Monitoring strategies have either been recommended by third party consultants, contractors and/or drawn from best practice and statutory guidance. ii) The new Sustainability Tool for the repository of monitoring data (launched August 2024) needs to be developed and understood by those involved in environmental monitoring. iii) Geographic Information Systems (GIS) are underutilised and communicating spatial data is not standardised. The PEMP is not being fully implemented with regards to the workflow process. This has been exacerbated by the absence of formal training on the procedure. The infrastructure and resources required to meet the standards outlined in the PEMP is insufficient. Shortfalls in data collection, storage and communication are anticipated to be addressed with the use of new monitoring technology and the creation of a share data platform for environmental monitoring. | N/A | N/A | N/A | 101366511 | 30090 | 0 | 3 | 11 | 4 | 0 | 0 | 0 | 0 |  |  | 2 | 2 | 0 | 0 |  |  |  | N/A
74 | e-SHA Cat A* MoC | RWA Assessment for permitting impacts |  | B | No | No | SS&A - Operational Permits | Line 1 - Corporate Functions | 2024-10-01 | 2024-10-11 | Stuart Woodings | Emma Wells | Assessment | SS&A - Operational Permits | N/A - No specific Milestone | Environment | Blue | Green | 12.12.24 BH: 3 opportinies identified. Provide a formal notification letter to the EA under RSR Condition 4.3.5 related to the implementation of the ESHA Management of Change proposal, ssign the Nuclear Licensed Board Member role training profile (TPR130) to the Environmental Baseline to demonstrate the significance of decision-making at that level on environmental permit compliance and Ensure that the EA are provided copies of updated documentation as specified within the Implementation Plan. deadlines for these actions are due at financial close. No insight report raised as findings were not major |  | N/A |  | 101357817 | N/A | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  |  | N/A
901 | MEH Alliance Cat A MoC | RWA Assessment for permitting impacts | 6.3.25 AB - BH to check, as this line if complete from 2024, just needs to be added to archive sheet, and potentially new line added for 2025 activity. 13.03.25 was completed in 2024. This line to be archived to 2024 tab. 14.3.25 - AB - Action for Becky: Please can you check with Emma if this line is 2025, as I think item 74 (if you see archive tab), which looks similar was the one archived and belive this is for 2025?. 3.4.25 BH - Leave in for now will check with Emma next month. 3.4.25 bh - established that this should be in 2024 so moved to archive, in line 901. | B | No | No | SS&A - Operational Permits | Line 1 - Corporate Functions | 2024-10-20 | 2024-10-30 | Stuart Woodings | Emma Wells | Assessment | SS&A - Operational Permits | MEHA – Contract Signed | Environment | Blue | Green | 12.12.24 BH: 1 opportunity identified, Informally engage with the EA on this topic to make them aware of the change opportunities completed. No insight report raised as findings were not major |  | N/A |  | 101373169 | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  |  | N/A
3 | 3rd Party PAS2080 Certification - Stage 1 Audit | Certification of Management System Against PAS2080 | 8.11.24 AD/CT: Finalising remaining fieldwork, will be added to Insight once the new categories have been added (new categories as shown on LRQA report) by HPC. 12.11.24: PL - Fieldwork complete, on-track to complete suggested actions. 17.01.25: AB - An error entered on the metrics, and delay to report resulted in the 2 MNC's, being mis-reported as since being 0, it's now been advised these are still open, we shall update once these have been resolved. 09.04.25 PL - all findings closed during stage 2 PAS 2080 audit now reflected in this tracker | R | No | No | External Review - LRQA | Line 4 - External | 2024-10-22 | 2024-10-23 | Fran Gradie | Vanessa Tsanang | Audit | Overall Project | PAS 2080 - gap analysis complete | Reputation (Social Licence) | Blue | Red | SZC is successfully developing its carbon management framework to meet the requirements of PAS 2080. Stage 2 verification is deemed viable, provided the 2 MNCN's are resolved (1 other non-conformance found which would not stop the Stage 2 from proceeding). PAS 2080 findings have some different categories, system is being altered prior to us adding the report to allow for the new categorisation to be accurately shown. Lengthy conversations have taken place with LRQA and the ESG team to negotiate a number of days in March (Last day in March till the 4th April), we believe the length of time between now and March will be sufficient to allow the ESG team to adequately address the MNCN’s, which the ESG Team have said they are confident in delivering on. For further details see Insight Report. | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 1 | 0 | 2 | 0 | 2025-10-31 | 4th April 2025 | 0 | 0 | 0 | 0 | AUD-2697 | Graham Colebeck (LRQA) | Peter Long | Alice Lidell | Alice Lidell
4 | 3rd party ISO9001 Certification audit | LRQA 9001 recertification audit | 12.12.24 - Audit result is just awaiting 'validation', pre-validated results indicate 2 minor NC's, and 3 OFI's. 18.12.24 - ACG - Added Metric Data. Technical review concluded. 24.6.25 - AB - 2 live minor's from this audit have been moved to the live picture for June 2025 Audit and zero'd from here. | R | No | Yes | External Review - LRQA | Line 4 - External | 2024-11-21 | 2024-11-29 | Fran Gradie | Vanessa Tsanang | Audit | Overall Project | ISO 9001: Re-Certification Audit | Reputation (Social Licence) | Blue | Green | NCR 1: The process to review the effectiveness of corrective actions is not fully effective, NCR2:The process for reviewing the outputs from the management review are not fully effective. For fully details of the NCR's and the other Findings go to report linked in Insight. Report: LRQ00004289/5829020 - 29-November-2024 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 3 | 0 | 2 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | AUD-2638 |  |  | N/A
6 | 3rd party ISO14001 Surveillance audit | ISO 14001 Dec 2024 | 18.12.24 - ACG - Added Metric Data 23.06.25 - PL: As a result on jun/2025 external audits, both nc are now closed according the LRQA report AR-3442. | R | No | Yes | External Review - LRQA | Line 4 - External | 2024-12-09 | 2024-12-12 | Fran Gradie | Vanessa Tsanang | Audit | Overall Project | ISO 14001: Surveillance Audit | Reputation (Social Licence) | Blue | Green | No new NCR's. 1 NCR's closed and the remaining 2 making good progrees. For fully details of the rollover NCR's and the other Findings go to report linked in Insight. Report: LRQ00004289/6273508 - 12-December-2024 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 9 | 0 | 2 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | AUD-2639 |  |  | N/A
902 |  |  |  |  | No | [9 empty] | N/A - No specific Milestone | [5 empty] | N/A | [20 empty] | N/A
903 |  |  |  |  | No | [9 empty] | N/A - No specific Milestone | [5 empty] | N/A | [20 empty] | N/A
904 |  |  |  |  | No | [9 empty] | N/A - No specific Milestone | [5 empty] | N/A | [20 empty] | N/A
905 |  |  |  |  | No | [9 empty] | N/A - No specific Milestone | [5 empty] | N/A | [20 empty] | N/A
906 |  |  |  |  | No | [9 empty] | N/A - No specific Milestone | [5 empty] | N/A | [20 empty] | N/A
907 |  |  |  |  | No | [9 empty] | N/A - No specific Milestone | [5 empty] | N/A | [20 empty] | N/A
908 |  |  |  |  | No | [9 empty] | N/A - No specific Milestone | [5 empty] | N/A | [20 empty] | N/A
909 |  |  |  |  | No | [9 empty] | N/A - No specific Milestone | [5 empty] | N/A | [20 empty] | N/A
910 |  |  |  |  | No | [9 empty] | N/A - No specific Milestone | [5 empty] | N/A | [20 empty] | N/A
911 |  |  |  |  | No | [9 empty] | N/A - No specific Milestone | [5 empty] | N/A | [20 empty] | N/A
912 |  |  |  |  | No | [9 empty] | N/A - No specific Milestone | [5 empty] | N/A | [20 empty] | N/A
913 |  |  |  |  | No | [9 empty] | N/A - No specific Milestone | [5 empty] | N/A | [20 empty] | N/A
914 |  |  |  |  | No | [9 empty] | N/A - No specific Milestone | [5 empty] | N/A | [20 empty] | N/A
915 |  |  |  |  | No | [9 empty] | N/A - No specific Milestone | [5 empty] | N/A | [20 empty] | N/A
916 |  |  |  |  | No | [9 empty] | N/A - No specific Milestone | [5 empty] | N/A | [20 empty] | N/A
917 |  |  |  |  | No | [9 empty] | N/A - No specific Milestone | [5 empty] | N/A | [20 empty] | N/A
918 |  |  |  |  | No | [9 empty] | N/A - No specific Milestone | [5 empty] | N/A | [20 empty] | N/A
919 |  |  |  |  | No | [9 empty] | N/A - No specific Milestone | [5 empty] | N/A | [20 empty] | N/A
920 |  |  |  |  | No | [9 empty] | N/A - No specific Milestone | [5 empty] | N/A | [20 empty] | N/A
921 |  |  |  |  | No | [9 empty] | N/A - No specific Milestone | [5 empty] | N/A | [20 empty] | N/A
922 |  |  |  |  | No | [9 empty] | N/A - No specific Milestone | [5 empty] | N/A | [20 empty] | N/A
923 |  |  |  |  | No | [9 empty] | N/A - No specific Milestone | [5 empty] | N/A | [20 empty] | N/A
924 |  |  |  |  | No | [9 empty] | N/A - No specific Milestone | [5 empty] | N/A | [20 empty] | N/A
925 |  |  |  |  | No | [9 empty] | N/A - No specific Milestone | [5 empty] | N/A | [20 empty] | N/A
926 |  |  |  |  | No | [9 empty] | N/A - No specific Milestone | [5 empty] | N/A | [20 empty] | N/A
927 |  |  |  |  | No | [9 empty] | N/A - No specific Milestone | [5 empty] | N/A | [20 empty] | N/A
928 |  |  |  |  | No | [9 empty] | N/A - No specific Milestone | [5 empty] | N/A | [20 empty] | N/A
929 |  |  |  |  | No | [9 empty] | N/A - No specific Milestone | [5 empty] | N/A | [20 empty] | N/A
930 |  |  |  |  | No | [9 empty] | N/A - No specific Milestone | [5 empty] | N/A | [20 empty] | N/A
931 |  |  |  |  | No | [9 empty] | N/A - No specific Milestone | [5 empty] | N/A | [20 empty] | N/A
932 |  |  |  |  | No | [9 empty] | N/A - No specific Milestone | [5 empty] | N/A | [20 empty] | N/A
933 |  |  |  |  | No | [9 empty] | N/A - No specific Milestone | [5 empty] | N/A | [20 empty] | N/A
934 |  |  |  |  | No | [9 empty] | N/A - No specific Milestone | [5 empty] | N/A | [20 empty] | N/A
935 |  |  |  |  | No | [9 empty] | N/A - No specific Milestone | [5 empty] | N/A | [20 empty] | N/A
936 |  |  |  |  | No | [9 empty] | N/A - No specific Milestone | [5 empty] | N/A | [20 empty] | N/A
937 |  |  |  |  | No | [9 empty] | N/A - No specific Milestone | [5 empty] | N/A | [20 empty] | N/A
938 |  |  |  |  | No | [9 empty] | N/A - No specific Milestone | [5 empty] | N/A | [20 empty] | N/A
939 |  |  |  |  | No | [9 empty] | N/A - No specific Milestone | [5 empty] | N/A | [20 empty] | N/A
940 |  |  |  |  | No | [9 empty] | N/A - No specific Milestone | [5 empty] | N/A | [20 empty] | N/A
941 |  |  |  |  | No | [9 empty] | N/A - No specific Milestone | [5 empty] | N/A | [20 empty] | N/A
942 |  |  |  |  | No | [9 empty] | N/A - No specific Milestone | [5 empty] | N/A | [20 empty] | N/A
943 |  |  |  |  | No | [9 empty] | N/A - No specific Milestone | [5 empty] | N/A | [20 empty] | N/A
944 |  |  |  |  | No | [9 empty] | N/A - No specific Milestone | [5 empty] | N/A | [20 empty] | N/A
945 |  |  |  |  | No | [9 empty] | N/A - No specific Milestone | [5 empty] | N/A | [20 empty] | N/A
946 |  |  |  |  | No | [9 empty] | N/A - No specific Milestone | [5 empty] | N/A | [20 empty] | N/A
947 |  |  |  |  | No | [9 empty] | N/A - No specific Milestone | [5 empty] | N/A | [20 empty] | N/A
948 |  |  |  |  | No | [9 empty] | N/A - No specific Milestone | [5 empty] | N/A | [20 empty] | N/A
949 |  |  |  |  | No | [9 empty] | N/A - No specific Milestone | [5 empty] | N/A | [20 empty] | N/A
950 |  |  |  |  | No | [9 empty] | N/A - No specific Milestone | [5 empty] | N/A | [20 empty] | N/A
951 |  |  |  |  | No | [9 empty] | N/A - No specific Milestone | [5 empty] | N/A | [20 empty] | N/A
952 |  |  |  |  | No | [9 empty] | N/A - No specific Milestone | [5 empty] | N/A | [20 empty] | N/A
953 |  |  |  |  | No | [9 empty] | N/A - No specific Milestone | [5 empty] | N/A | [20 empty] | N/A
954 |  |  |  |  | No | [9 empty] | N/A - No specific Milestone | [5 empty] | N/A | [20 empty] | N/A
955 |  |  |  |  | No | [9 empty] | N/A - No specific Milestone | [5 empty] | N/A | [20 empty] | N/A
956 |  |  |  |  | No | [9 empty] | N/A - No specific Milestone | [5 empty] | N/A | [20 empty] | N/A
957 |  |  |  |  | No | [9 empty] | N/A - No specific Milestone | [5 empty] | N/A | [20 empty] | N/A
958 |  |  |  |  | No | [9 empty] | N/A - No specific Milestone | [5 empty] | N/A | [20 empty] | N/A
959 |  |  |  |  | No | [9 empty] | N/A - No specific Milestone | [5 empty] | N/A | [20 empty] | N/A
960 |  |  |  |  | No | [9 empty] | N/A - No specific Milestone | [5 empty] | N/A | [20 empty] | N/A
961 |  |  |  |  | No | [9 empty] | N/A - No specific Milestone | [5 empty] | N/A | [20 empty] | N/A
962 |  |  |  |  | No | [9 empty] | N/A - No specific Milestone | [5 empty] | N/A | [20 empty] | N/A
963 |  |  |  |  | No | [9 empty] | N/A - No specific Milestone | [5 empty] | N/A | [20 empty] | N/A
964 |  |  |  |  | No | [9 empty] | N/A - No specific Milestone | [5 empty] | N/A | [20 empty] | N/A
965 |  |  |  |  | No | [9 empty] | N/A - No specific Milestone | [5 empty] | N/A | [20 empty] | N/A
966 |  |  |  |  | No | [9 empty] | N/A - No specific Milestone | [5 empty] | N/A | [20 empty] | N/A
967 |  |  |  |  | No | [9 empty] | N/A - No specific Milestone | [5 empty] | N/A | [20 empty] | N/A
968 |  |  |  |  | No | [9 empty] | N/A - No specific Milestone | [5 empty] | N/A | [20 empty] | N/A
969 |  |  |  |  | No | [9 empty] | N/A - No specific Milestone | [5 empty] | N/A | [20 empty] | N/A
970 |  |  |  |  | No | [9 empty] | N/A - No specific Milestone | [5 empty] | N/A | [20 empty] | N/A
971 |  |  |  |  | No | [9 empty] | N/A - No specific Milestone | [5 empty] | N/A | [20 empty] | N/A
972 |  |  |  |  | No | [9 empty] | N/A - No specific Milestone | [5 empty] | N/A | [20 empty] | N/A
973 |  |  |  |  | No | [9 empty] | N/A - No specific Milestone | [5 empty] | N/A | [20 empty] | N/A
974 |  |  |  |  | No | [9 empty] | N/A - No specific Milestone | [5 empty] | N/A | [20 empty] | N/A
975 |  |  |  |  | No | [9 empty] | N/A - No specific Milestone | [5 empty] | N/A | [20 empty] | N/A
976 |  |  |  |  | No | [9 empty] | N/A - No specific Milestone | [5 empty] | N/A | [20 empty] | N/A
977 |  |  |  |  | No | [9 empty] | N/A - No specific Milestone | [5 empty] | N/A | [20 empty] | N/A
978 |  |  |  |  | No | [9 empty] | N/A - No specific Milestone | [5 empty] | N/A | [20 empty] | N/A
979 |  |  |  |  | No | [9 empty] | N/A - No specific Milestone | [5 empty] | N/A | [20 empty] | N/A
980 |  |  |  |  | No | [9 empty] | N/A - No specific Milestone | [5 empty] | N/A | [20 empty] | N/A
981 |  |  |  |  | No | [9 empty] | N/A - No specific Milestone | [5 empty] | N/A | [20 empty] | N/A
982 |  |  |  |  | No | [9 empty] | N/A - No specific Milestone | [5 empty] | N/A | [20 empty] | N/A
983 |  |  |  |  | No | [9 empty] | N/A - No specific Milestone | [5 empty] | N/A | [20 empty] | N/A
984 |  |  |  |  | No | [9 empty] | N/A - No specific Milestone | [5 empty] | N/A | [20 empty] | N/A
985 |  |  |  |  | No | [9 empty] | N/A - No specific Milestone | [5 empty] | N/A | [20 empty] | N/A
986 |  |  |  |  | No | [9 empty] | N/A - No specific Milestone | [5 empty] | N/A | [20 empty] | N/A
987 |  |  |  |  | No | [9 empty] | N/A - No specific Milestone | [5 empty] | N/A | [20 empty] | N/A
988 |  |  |  |  | No | [9 empty] | N/A - No specific Milestone | [5 empty] | N/A | [20 empty] | N/A
989 |  |  |  |  | No | [9 empty] | N/A - No specific Milestone | [5 empty] | N/A | [20 empty] | N/A
990 |  |  |  |  | No | [9 empty] | N/A - No specific Milestone | [5 empty] | N/A | [20 empty] | N/A
991 |  |  |  |  | No | [9 empty] | N/A - No specific Milestone | [5 empty] | N/A | [20 empty] | N/A
992 |  |  |  |  | No | [9 empty] | N/A - No specific Milestone | [5 empty] | N/A | [20 empty] | N/A
993 |  |  |  |  | No | [9 empty] | N/A - No specific Milestone | [5 empty] | N/A | [20 empty] | N/A
N/A
Formulas:
Planned End Date / Report published = Table75[[#This Row],[Planned Start Date ]]+120
Note on M11: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Almost complete, report published when Camila returns
Note on F15: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Alex Boyce updates to metrics complete.